## DFP-Com
Detailed Financial Plan - Commitments
| Country: |  | Guatemala
| Accountable Entity: |  | PRONACOM
| Grant Number: |  | TR14GTM15001
| Date Submitted: |  | 2017-11-24
| Quarter # |  | 7
| Forecasted Commitments for -> | Cumulative | Current Period | Next Period | [12 empty] | TOTAL | TOTAL | Variance
|  | Actual Cumulative Commitments at Beginning of Current Period | Projected Commitments during Current Period | Grant Quarter #7 |  |  |  | Grant Quarter #8 | Grant Quarter #9 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Commitments As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)* | Projections vs. Approved Plan Under / (Over) Budget Difference
| Date/Month/Quarter -> | Sep´ 2017 | Oct '17 Dic '17 | Jan´18 | Feb`18 | Mar´18 | Jan '18 Mar '18 | Apr '18 Jun '18 | Jul '18 Sep '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20
| Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 | 1.1 Improving the Quality of Education (0277) | 7593016.0878 | 0 | 4000000 | 0 | 200000 | 4200000 | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11999016.0878 | 12000000 | 983.9122
1.1.a | 1.1.a Education Project Implementation Contract | 7593016.0878 | 0 | 0 |  | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7993016.0878
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 0 | 4000000 |  |  | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4000000
1.1.c | 1.1.c Other |  | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6000
1.2 | 1.2 Developing Technical and Vocational Education and Training (0400) | 35002.5 | 2400000 | 0 | 1000000 | 0 | 1000000 | 435002.5 | 0 | 0 | 0 | 24300.4 | 0 | 0 | 0 |  | 3894305.4 | 4300000 | 405694.6
1.2.a | 1.2.a TVET | 35002.5 | 2400000 |  | 1000000 |  | 1000000 | 435002.5 | 0 | 0 | 0 | 24300.4 | 0 | 0 | 0 |  | 3894305.4
1.3 | 1.3 Strengthening Institutional and Planning Capacity (0043) | 2813276.1822 | 25000 | 45758 | 2000 | 3000 | 50758 | 0 | 0 | 25000 | 43758 | 0 | 0 | 8000 | 17755.2 |  | 2983547.3822 | 3000000 | 16452.6178
1.3.a | 1.3.a Education Project Implementation Contract | 2772876.1822 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2772876.1822
1.3.b | 1.3.b Education Project Coordination team* | 40400 | 25000 | 43758 |  |  | 43758 | 0 | 0 | 25000 | 43758 | 0 | 0 | 8000 | 17755.2 |  | 203671.2
1.3.c | 1.3.c Other |  | 0 | 2000 | 2000 | 3000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7000
TOTA | TOTAL - Education | 10441294.77 | 2425000 | 4045758 | 1002000 | 203000 | 5250758 | 641002.5 | 0 | 25000 | 43758 | 24300.4 | 0 | 8000 | 17755.2 |  | 18876868.87 | 19300000 | 423131.13
2. R | 2. Resource Mobilization Project (REV RFRM)
2.1 | 2.1 Improving Tax and Customs Administration (0443)** | 140500 | 0 | 348759 | 175135.5 | 37498.5 | 561393 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 741893 | 800000 | 58107
2.1.a | 2.1.a Tax and Customs | 140500 | 0 | 348759 | 175135.5 | 37498.5 | 561393 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 741893
2.2 | 2.2 Strengthening Public-Private Partnership Capacity (0414) | 586817.91 | 1030229 | 0 | 1745000 | 0 | 1745000 | 0 | 147000 | 73500 | 0 | 0 | 0 | 0 | 0 |  | 3582546.91 | 3600000 | 17453.09
2.2.a | 2.2.a Advisors | 580856.27 | 0 | 0 |  |  | 0 | 0 | 147000 | 73500 | 0 | 0 | 0 | 0 | 0 |  | 801356.27
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | 0 | 1030229 |  | 1745000 |  | 1745000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2775229
2.2.c | 2.2.c Other | 5961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5961.64
TOTA | TOTAL - Resource Mobilization | 727317.91 | 1030229 | 348759 | 1920135.5 | 37498.5 | 2306393 | 40000 | 147000 | 73500 | 0 | 0 | 0 | 0 | 0 |  | 4324439.91 | 4400000 | 75560.09
3. M | 3. M&E (MON & Eval)
M | Monitoring and Evaluation (0016) | 96340.16 | 6000 | 2000 | 32000 | 802000 | 836000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 |  | 1095700 | 1700000 | 604300
3.1.a | 3.1.a Student Assessment | 95700 | 0 |  | 30000 | 800000 | 830000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 925700
3.1.b | 3.1.b Teacher Evaluations | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 |  | 170000
3.1.d | 3.1 d Other | 640.16 | 6000 | 2000 | 2000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12640.16
| TOTAL - M&E | 96340.16 | 6000 | 2000 | 32000 | 802000 | 836000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 |  | 1095700 | 1700000 | 604300
4. Program Admin (PGM ADMIN)
| Program Administration (0017) | 313625.9 | 31391 | 164749 | 1700 | 1700 | 168149 | 34391 | 29400 | 34391 | 78149 | 2400 | 43964.76 | 24218.4 | 32016.4 |  | 792096.46 | 797500 | 5403.54
4.1.a | 4.1.a Staff Compensation* | 282984 | 29991 | 73749 |  |  | 73749 | 29991 | 25000 | 29991 | 73749 | 0 | 41564.76 | 21818.4 | 29684.4 |  | 638522.56
4.1.b | 4.1.b Travel* | 2945.3 | 0 | 1000 | 1000 | 1000 | 3000 | 3000 | 3000 | 3000 | 3000 | 1000 | 1000 | 1000 | 1000 |  | 21945.3
4.1.c | 4.1.c Audit | 0 | 0 | 90000 |  |  | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 90000
4.1.d | 4.1.d Other | 27696.6 | 1400 |  | 700 | 700 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 |  | 41628.6
| TOTAL - Program Admin | 313625.9 | 31391 | 164749 | 1700 | 1700 | 168149 | 34391 | 29400 | 34391 | 78149 | 2400 | 43964.76 | 24218.4 | 32016.4 |  | 792096.46 | 797500 | 5403.54
| TOTAL MCA-Managed Threshold Funds | 11578578.74 | 3492620 | 4561266 | 2955835.5 | 1044198.5 | 8561300 | 715393.5 | 176400 | 132891 | 121907 | 26700.4 | 43964.76 | 32218.4 | 219771.6 |  | 25089105.24 | 26197500 | 1108394.76
* This activity has MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.
78000

## DFP-CASH
Detailed Financial Plan - Cash
Country: |  | Guatemala
Accountable Entity: |  | PRONACOM
Grant Number: |  | TR14GTM15001
Date Submitted: |  | 2017-12-08
Quarter # |  | 7
Forecasted Cash for -> | Cumulative | Current Period | Next Period | [12 empty] | TOTAL | TOTAL | Variance
| Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period | Grant Quarter #7 |  |  |  | Grant Quarter #8 | Grant Quarter #9 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Cash Disbursements As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)** | Projections vs. Approved Plan Under / (Over) Budget Difference
Date/Month/Quarter -> | Sep´ 2017 | Oct '17 Dic '17 | Jan´18 | Feb`18 | Mar´18 | Jan '18 Mar '18 | Apr '18 Jun '18 | Jul '18 Sep '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20
Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | 725612.46 | 621953.54 | 544209.34 | 0 | 525914.7307 | 500000 | 806000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 100000 | 0 | 5753566 | 12000000 | 6246434
1.1.a Education Project Implementation Contract | 725612.46 | 621953.54 | 544209.34 | 0 | 125914.7307 | 100000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1747566
1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 0 |  |  | 400000 | 400000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 100000 | 0 | 4000000
1.1.c Other |  | 0 |  |  |  | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
1.2 Developing Technical and Vocational Education and Training (0400) | 8041.6 | 8430 | 2968 | 2968 | 442967.2 | 208903.2 | 108400 | 208400 | 208400 | 208400 | 208400 | 108400 | 108400 | 106929 | 0 | 1491103.8 | 4300000 | 2808896.2
1.2.a TVET | 8041.6 | 8430 | 2968 | 2968 | 442967.2 | 208903.2 | 108400 | 208400 | 208400 | 208400 | 208400 | 108400 | 108400 | 106929 | 0 | 1491103.8
1.3 Strengthening Institutional and Planning Capacity (0043) | 29632.64 | 222288.85 | 162988.38 | 111158.9227 | 215817.8454 | 23500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 0 | 407421.49 | 3000000 | 2592578.51
1.3.a Education Project Implementation Contract | 0 | 207317.85 | 155488.38 | 103658.9227 | 207317.8454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207317.85
1.3.b Education Project Coordination team* | 29632.64 | 14971 | 5500 | 5500 | 5500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 0 | 193103.64
1.3.c Other | 0 | 0 | 2000 | 2000 | 3000 | 7000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7000
TOTAL - Education | 763286.7 | 852672.39 | 710165.72 | 114126.9227 | 1184699.7761 | 732403.2 | 930900 | 724900 | 724900 | 724900 | 724900 | 624900 | 624900 | 223429 | 0 | 7652091.29 | 19300000 | 11647908.71
2. Resource Mobilization Project (REV RFRM)
2.1 Improving Tax and Customs Administration (0443)** | 84271.6 | 34617 | 21042.8 | 21042.8 | 97769.55 | 114971.945 | 160348.25 | 160348.25 | 126168.25 | 39556.305 | 0 | 0 | 0 | 0 | 0 | 720281.6 | 800000 | 79718.4
2.1.a Tax and Customs | 84271.6 | 34617 | 21042.8 | 21042.8 | 97769.55 | 114971.945 | 160348.25 | 160348.25 | 126168.25 | 39556.305 | 0 | 0 | 0 | 0 | 0 | 720281.6
2.2 Strengthening Public-Private Partnership Capacity (0414) | 159338.99 | 162838.94 | 12250 | 480966.6 | 361250 | 349000 | 698000 | 698000 | 98000 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 2287677.93 | 3600000 | 1312322.07
2.2.a Advisors | 153377.35 | 110432 | 12250 | 68875 | 12250 | 0 | 0 | 0 | 98000 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 484309.35
2.2.b Feasiblity Studies/ Transaction Advisory Services | 0 | 52406.94 |  | 412091.6 | 349000 | 349000 | 698000 | 698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1797406.94
2.2.c Other | 5961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5961.64
TOTAL - Resource Mobilization | 243610.59 | 197455.94 | 33292.8 | 502009.4 | 459019.55 | 463971.945 | 858348.25 | 858348.25 | 224168.25 | 76306.305 | 36750 | 36750 | 12250 | 0 | 0 | 3007959.53 | 4400000 | 1392040.47
3. M&E (MON & Eval)
Monitoring and Evaluation (0016) | 30175 | 35250 | 4000 | 4000 | 205500 | 207500 | 207500 | 207500 | 213500 | 0 | 42500 | 42500 | 42500 | 42500 | 0 | 1065425 | 1700000 | 634575
3.1.a Student Assessment | 30175 | 35250 | 2000 | 2000 | 203500 | 201500 | 207500 | 207500 | 213500 | 0 | 0 | 0 | 0 | 0 | 0 | 895425
3.1.b Teacher Evaluations |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c Voc Ed Tracer Studies |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 42500 | 42500 | 42500 | 42500 | 0 | 170000
3.1 d Other |  | 0 | 2000 | 2000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
TOTAL - M&E | 30175 | 35250 | 4000 | 4000 | 205500 | 207500 | 207500 | 207500 | 213500 | 0 | 42500 | 42500 | 42500 | 42500 | 0 | 1065425 | 1700000 | 634575
4. Program Admin (PGM ADMIN)
Program Administration (0017) | 162040.45 | 48500 | 13880 | 14220 | 39399 | 67499 | 42500 | 51500 | 36500 | 57500 | 55500 | 40500 | 40500 | 64432 | 0 | 666971.45 | 797500 | 130528.55
4.1.a Staff Compensation* | 143137.67 | 45000 | 12700 | 12700 | 12700 | 38100 | 38100 | 32100 | 32100 | 38100 | 38100 | 38100 | 38100 | 32100 | 0 | 513037.67
4.1.b Travel* | 3518.51 | 1000 | 1000 | 1000 | 1000 | 3000 | 3000 | 3000 | 3000 | 3000 | 1000 | 1000 | 1000 | 1000 | 0 | 23518.51
4.1.c Audit | 0 | 0 |  |  | 15000 | 15000 | 0 | 15000 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 90000
4.1.d Other | 15384.27 | 2500 | 180 | 520 | 10699 | 11399 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 40415.27
TOTAL - Program Admin | 162040.45 | 48500 | 13880 | 14220 | 39399 | 67499 | 42500 | 51500 | 36500 | 57500 | 55500 | 40500 | 40500 | 64432 | 0 | 666971.45 | 797500 | 130528.55
TOTAL MCA-Managed Threshold Funds | 1199112.74 | 1133878.33 | 761338.52 | 634356.3227 | 1888618.3261 | 1471374.145 | 2039248.25 | 1842248.25 | 1199068.25 | 858706.305 | 859650 | 744650 | 720150 | 330361 | 0 | 12392447.27 | 26197500 | 13805052.73
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.
Note on G22: Josue Andreé Ricart Vásquez: ENCA+ANACELI+FORMACIÓN P TRABAJO
Note on G24: Josue Andreé Ricart Vásquez: pagos fhi
Note on H18: Josue Andreé Ricart Vásquez: pago de tablets y modificación fhi
Note on H19: Josue Andreé Ricart Vásquez: universidades
Note on H25: Josue Andreé Ricart Vásquez: LISETH Y KARLA

## QFR - A
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2017-12-08
Schedule A. Multi-Year Financial Plan Adjustment Request Form
Disbursement Period:01-ene-18 to 31-mar-18
Amounts Expressed In US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Current Approved Multi-Year Financial Plan | Proposed Adjustments (Display all #'s as positive) |  | Proposed Adjusted Multi-Year Financial Plan
Project (code) |  | (from Schedule B, Final Column) | Increase (+) | Decrease (-) | (2+3-4)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | 19300000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 12000000 |  |  | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | 4300000 |  |  | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 3000000 |  |  | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 4400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 |  |  | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | 3600000 |  |  | 3600000
3. M&E (MON & EVAL) | 1700000 | 1700000 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 1700000 |  |  | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 797500 | 0 | 0 | 797500
Program Administration (0017) | 800000 | 797500 |  | 0 | 797500
Grand Total | 26200000 | 26197500 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 1800000 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 | 1800000 |  |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 2500 | 0 | 0 | 2500
Program Administration (0017) | 0 | 2500 | 0 |  | 2500
Grand Total | 1800000 | 1802500 | 0 | 0 | 1802500

## QFR - B
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2017-12-08
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-ene-18 to 31-mar-18
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (Q6 - 10/11/2017) | Adjustment Reported/ Approved (insert date) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 0 | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | 3600000
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | 0 | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 0 | -2500 | 0 | 797500
Program Administration (0017) | 800000 | 0 | -2500 | 0 | 797500
Grand Total | 26200000 | 0 | -2500 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  | 0 |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 0 | 2500 | 0 | 2500
Program Administration (0017) |  |  | 2500 |  | 2500
Grand Total | 1800000 | 0 | 0 | 0 | 1802500

## THP DR
DISBURSEMENT REQUEST
THRESHOLD PROGRAM GRANT AGREEMENT
Country | Guatemala
Projects | Theshold Program / Program Administration and Monitoring and Evaluation
Threshold Program Grant Agreement Date/ Entry into Force Date | April 8, 2015/May 15, 2016
Threshold Program Number | TR14GTM15001
Accountable Entity | PRONACOM
Fiscal Agent | MCC (Acting Fiscal Agent)
Request Date | 2017-12-08
Disbursement Period Beginning Date | 2018-01-01
Disbursement Period Ending Date | 2018-03-31
Disbursement Number | 7
Currency (Expressed in USD) | US Dollars
Exchange Rate used to calculate U.S. Dollar equivalent of any local currency balance for purposes of this MCC Disbursement Request
A. Disbursement Request: The undersigned hereby requests the Millennium Challenge Corporation to disburse funds under the Threshold Grant Agreement, dated as of August 28,2013 as follows:
1. Forecasted Cash Disbursement Requirements (from DFP Cash Column) | 1471374.145
2. Interest to be Returned to the USG for Next Period (Interest Sum, Line 7)
3. Working Capital (FOR MCC USE ONLY)
4. Cash Balance at the End of the Current Period (Cash Req, Line 7) | 0
5. Disbursement Request Amount (Lines 1+2-4) | 1471374.145
6. Amount Requested in Words | three million two hundred eighty-four thousand three hundred thirteen dollars and nineteen cents
C. Compliance: the undersigned confirms that the MCC Disbursement requested herby is in accordance with the terms and conditions set forth in the Threshold Program Agreement, including the limitations on the use or treatment of MCC Funding set out in Section 2.4.
D. Authorization: the undersigned acknowledges that funds disbursed in accordance with this request will be either made (i) directly to third-party vendors for goods, works and services received by the accountable entity upon presentation of valid invoices utilizing MCC's Common Payment System, (ii) to the Permitted Account, or (iii) to the Petty Cash Account.
E. Certificates: Attached hereto are the certificates required under Section 5.2 and 5.3 of the Threshold Program Agreement.
F. Definitions: Capitalized terms used herein shall have the meanings assigned to such terms in the Threshold Program Agreement by and between the Government of Guatemala and the United States, acting through the Millennium Challenge Corporation, dated April 8, 2015, and entered into force on May 15, 2016.
Signed by the Acting Executive Director of PRONACOM
By: _______________________________________________________________
Name: Aimeé Rivas Godoy de Palma
Date: December 8, 2017
Certified by the vice Minister of Economy in charge of the office
By: _______________________________________________________________
Name: Giovanni Verbena
Date: _____________________________________________________________
By: _______________________________________________________________
Name:
Date:

## Contract level (hidden)
[5 empty] | Percent of disbursements by quarter | [15 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# |  |  |  |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 |  | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  |  |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 |  | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 1.1.a Education Project Implementation Contract |  |  | q4 |  |  |  | 0% | 9.556% | 8.191% | 7.509% | 6.826% | 0.3413% | 9.556% | 0 | 9.556% | 10.24% | 9.556% | 9.556% | 19.11% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | tablets (modification to FHI contract) | 200000 | q7 | [5 empty] | 0% | 50% | 50% | 0% | 0% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | Pedagogical Resource centers | 200000 | q8 | [6 empty] | 0% | 100% | 0% | 0% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Diplomado Training | 4000000 | q7 | [6 empty] | 10% | 12.5% | 12.5% | 12.5% |  | 12.5% | 12.5% | 12.5% | 12.5% | 2.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.c | 1.1.c Other | Travel | 6000 | q8 |  |  |  |  | 0% | 0% | 0% | 100% | [8 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET |  |  | q6 | [5 empty] | 0% | 10% | 10% | 10% | 10% | 0 | 10% | 10% | 10% | 10% | 20% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET place holder | 400000 | q8 | [8 empty] | 25% | 25% |  | 25% | 25% |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | A-TVET place holder | 1000000 | q7 | [5 empty] | 0% | 20% | 10% | 10% | 10% |  | 10% | 10% | 10% | 10% | 10% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract |  |  | q4 |  |  |  | 0% |  | 7.477% | 16.82% | 3.738% | 50.47% | 7.477% | 0 | 0% | 8.411% | 0% | 0% | 5.607% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 1.3.c Other | Travel | 7000 | q7 |  |  |  |  | 0% | 0% | 100% |  |  | 7410147741 | [6 empty] | 7410147742 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 51871034187000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51871034187000
2.1.a | 2.1.a Tax and Customs |  |  | q3 |  |  |  | 25% | 25% | 25.64% | 24.36% | 0% |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for audit (mauricio) 2 option | 37498.5 | q7 | [6 empty] | 0% | 25% | 25% | 25% |  | 25% |  |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9374.625 | 9374.625 | 9374.625 | 9374.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37498.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Asistente Bilingüe (Lilian) | 18759 | q7 | [6 empty] | 25% | 25% | 25% | 25% |  | 0% |  |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 4689.75 | 4689.75 | 4689.75 | 4689.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT Architecture Consultant | 72000 | q7 | [5 empty] | 0% | 25% | 25% | 25% | 6% |  | 19% |  |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 4320 | 13680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Customs system study (firm or individual consultant) | 100000 | q7 | [6 empty] | 25.5% | 25% | 25% | 24.5% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 25000 | 25000 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | One (1) consultant for Project Management (Project Management Office enhancement, desingn project audit model, training and training curriculum design | 40000 | q8 | [5 empty] | 0% | 0% | 50% | 50% | 0% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs |  |  | q3 |  |  | 100% | [7 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs |  |  | q3 |  |  | 0% | 33.33% | 24.75% | 25.64% | 16.28% |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants (Keny, Alvaro y Edgar) option | 103135.5 | q7 | [6 empty] | 9% | 25% | 25% | 25% |  | 0.16 |  |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9282.195 | 25783.875 | 25783.875 | 25783.875 | 16501.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103135.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Two (2) consultants to assist with training and mentoring Investigations and Customs Security personnel | 230000 | q7 | [5 empty] | 0% | 25% | 25% | 25% | 25% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 57500 | 57500 | 57500 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs |  |  | q4 |  |  |  | 100% |  | 0% |  |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors |  |  | q4 |  |  |  |  | 3.868% | 20% | 15% | 61.13% |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors |  |  | q5 |  |  |  |  | 50% | 37.5% | 12.5% |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors |  |  | q3 |  |  |  | 33.33% | 16.67% | 33.33% | 16.67% |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors |  |  | q5 |  |  |  |  | 16.67% | 25% | 25% | 25% | 8.333% | 0% | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 2 | 147000 | q9 | [9 empty] | 16.67% |  | 25% | 25% | 25% | 8.333% |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors |  |  | q2 |  | 0% | 40% | 60% | 0% | [5 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 1 | 73500 | q10 |  |  |  |  | 0% | 0% |  |  |  | 100% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  |  | q6 | [5 empty] | 0% | 40% | 40% | 20% | 0% | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Metro Riel Transaction Advisor | 1745000 | q7 | [5 empty] | 0% | 20% | 40% | 40% | [7 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 349000 | 698000 | 698000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1745000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 2.2.c Other |  |  | q4 |  |  |  | 100% | [6 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 2.2.c Other |  |  | q5 |  |  |  |  | 100% | [5 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment |  |  | q5 | [5 empty] | 100% |  |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Firma para recopilación de datos para linea base | 800000 | q7 | [6 empty] | 24.25% | 25% | 25% | 25.75% |  | 0% |  |  |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 194000 | 200000 | 200000 | 206000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment |  |  | q4 |  |  |  | 0% | 50% | 50% |  |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment |  |  | q4 |  |  |  | 0% | 50% | 50% |  |  |  |  | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment |  |  | q3 |  |  |  | 25% | 75% | [5 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment |  |  | q3 |  |  |  | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 0 | 11.54% | 7.692% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Experto en escala vertical | 30000 | q7 | [6 empty] | 25% | 25% | 25% | 25% | [6 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 170000 | q15 | [12 empty] | 25% | 25% | 25% | 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42500 | 42500 | 42500 | 42500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0
3.1.d | 3.1 d Other |  |  | q6 | [5 empty] | 100% |  |  |  |  | 0 |  | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q7 | 6000 | q7 | [6 empty] | 100% | [5 empty] | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.c | 4.1.c Audit | Audit | 90000 | q7 | [5 empty] | 0% | 16.67% |  | 16.67% |  |  | 16.67% | 16.67% |  |  | 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other |  |  | q2 |  | 67% | 33% | [7 empty] | 0 | [5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 |  | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [36 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 1.3.b Education Project Coordination team* |  |  | q2 |  | 4400 | 9000 | 9000 | 11310 | 10771.2 | 10500 | 10500 | 10500 | 10500 | 42000 | 10500 | 10500 | 10500 | 10500 | 10500 | 180981.2 | 0 | 4400 | 9000 | 9000 | 11310 | 10771.2 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 33710 | 0 | 0 | 0 | 0 | 43758 | 0 | 0 | 0 | 43758 | 0 | 0 | 0 | 17755.2 | 0
1.3.b | 1.3.b Education Project Coordination team* |  |  | q6 |  |  |  |  | 0 | 4000 | 6000 | 6000 | 6000 | 6000 | 24000 | 6000 | 6000 | 6000 | 6000 | 6000 | 82000 | 0 | 0 | 0 |  | 0 | 4000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 8000 | 0 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q1 | 10000 | 15000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000 | 10000 | 15000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q6 | 0 | 0 | 0 | 0 | 0 | 4800 | 7200 | 7200 | 7200 | 7200 | 24823.32 | 7200 | 7200 | 7200 | 7200 | 7200 | 94423.32 | 0 | 0 | 0 | 0 | 0 | 4800 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 9618 | 0 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q3 |  | 0 | 375 | 6039.2 | 4848 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15375.2 | 0 | 0 | 375 | 6039.2 | 4848 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15375.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 3950 | 10500 | 10500 | 10500 | 10500 | 10500 | 150950 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 0 | 43758 | 0 | 0 | 0 | 43758 | 0 | 0 | 0 | 17484 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q2 |  | 3960 |  | 3691.2 | 7751.52 | 7382.4 | 7200 | 7200 | 7200 | 7200 | 11411.96 | 7200 | 7200 | 7200 | 7200 | 7200 | 98997.08 | 0 | 3960 |  | 3691.2 | 7751.52 | 7382.4 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 15402.72 | 0 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 0 | 29991 | 0 | 12200.4 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q2 |  | 3960 | 6600 | 6600 | 7752 | 7382.4 | 7200 | 7200 | 7200 | 7200 | 28800 | 7200 | 7200 | 7200 | 7200 | 7200 | 125894.4 | 0 | 3960 | 6600 | 6600 | 7752 | 7382.4 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 24912 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 29991 | 0 | 0 | 12200.4 | 0 | 0
4.1.a | 4.1.a Staff Compensation* |  |  | q4 |  |  |  | 4922.88 | 3897.28 | 6153.6 | 6000 | 6000 | 0 | 0 | 13640.48 | 6000 | 6000 | 6000 | 6000 | 0 | 64614.24 | 0 | 0 | 0 | 4922.88 | 3897.28 | 6153.6 | 6000 | 6000 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 11573.76 | 0 | 0 | -12000
4.1.d | 4.1.d Other |  |  | q3 | [5 empty] | 0 | 9999 |  |  |  | 9999 | [5 empty] | 19998 | 0 | 0 | 0 |  | 0 | 0 | 9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET |  |  | q4 |  |  |  | 2010.4 | 9046.8 | 8616 | 8903.2 | 8400 | 8400 | 8400 | 15903.7 | 8400 | 8400 | 8400 | 8400 | 6929 | 110209.1 | 0 | 0 | 0 | 2010.4 | 9046.8 | 8616 | 8903.2 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 6929 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 24300.4 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [51 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 24200 |  |  | 1267.82 | 2800 | 4800 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 |  | 1400 | 1400 | 1400 | 1400 | 1332 | 24199.82 | 0 | 1267.82 | 2800 | 4800 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2800 | 4800 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 4.1.b Travel* | Travel | 22795 |  |  | 0 | 0 | 3518.51 | 276.14 | 0 | 3000 | 3000 | 3000 | 3000 |  | 3000 | 1000 | 1000 | 1000 | 1000 | 22794.65 | 0 | 0 | 0 | 3518.51 | 276.14 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 3518.51 | 276.14 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 1000 | 1000 | 1000 | 1000 | 0
| Total Comprometido a la fecha |  | 9522888
1.1.a | 1.1.a Education Project Implementation Contract |  | 400000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 4000000
1.2.a | 1.2.a TVET |  | 1400000
1.3.a | 1.3.a Education Project Implementation Contract |  | 0
1.3.b | 1.3.b Education Project Coordination team* |  | 0
| Education Project Total |  | 5800000 | 19300000 | 13500000
2.1.a | 2.1.a Tax and Customs |  | 601393
| Tax and Customs |  | 601393 | 800000 | 198607
2.2.a | 2.2.a Advisors |  | 220500
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 1745000
| PPPs |  | 1965500 | 3600000 | 1634500
3.1.a | 3.1.a Student Assessment |  | 830000
3.1.b | 3.1.b Teacher Evaluations |  | 0
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 170000
3.1.d | 3.1 d Other |  | 6000
| M&E |  | 1006000 | 1700000 | 694000
4.1.a | 4.1.a Staff Compensation* |  | 0
4.1.b | 4.1.b Travel* |  | 22795
4.1.c | 4.1.c Audit |  | 90000
4.1.d | 4.1.d Other |  | 24200
| Program Admin |  | 136995 | 797500 | 660505
[10 empty] | Educación | 81903.7
[10 empty] | mov rec | 0
[10 empty] | Monitoreo | 0
[10 empty] | admon | 92624.76
Note on C4: Josue Andreé Ricart Vásquez: FHI
Note on C5: Josue Andreé Ricart Vásquez: pregunta a John si lo dejamos en q7 o q8
Note on C7: Josue Andreé Ricart Vásquez: Universidades Programas de Formación
Note on C9: CAMBIA EL MONTO ADJUDICADO DE 2,800,000 A 2,400,000 GOPA
Note on C11: Josue Andreé Ricart Vásquez: Firma Consultora para la Revisión de dos carreras y creación de dos nuevas ENCA
Note on C12: Josue Andreé Ricart Vásquez: FHI
Note on C14: Josue Andreé Ricart Vásquez:contrato finalizá febrero 2017
Note on C15: Josue Andreé Ricart Vásquez: el primer pago (mes de marzo) se realizará en los primero días de abril
Note on C16: Josue Andreé Ricart Vásquez: Lilian Merlo contrato 2018
Note on C17: Josue Andreé Ricart Vásquez: en fase inicial se pretendió adquirir sus servicios en el q6 pero sigue en fase de TDR´s por lo que se traslada al q7
Note on C18: Josue Andreé Ricart Vásquez: consultor en sistema de aduanas
Note on C19: Josue Andreé Ricart Vásquez: esta en fase de tdr
Note on C20: Josue Andreé Ricart Vásquez: LAS DATABASE YA FUERON PAGADAS
Note on C21: Josue Andreé Ricart Vásquez: PAGOS DICIEMBRE Y ENERO
Note on C22: Josue Andreé Ricart Vásquez: CONTRATACIONES 2018 Y PAGO DE FEBRERO 2018
Note on C23: investigadores de aduanas
Note on C24: pagado
Note on C26: UNIVERSIDAD INTERNACIONES
Note on C29: no se quien es el
Note on C30: Josue Andreé Ricart Vásquez: ya fue pagado en su totalidad PU-MCC-002-2016
Note on C31: probablemente un tercer contrato de sergio bravo
Note on C32: Josue Andreé Ricart Vásquez: Deloitte
Note on C33: Josue Andreé Ricart Vásquez: ya están los terminos de referencia
Note on C34: Josue Andreé Ricart Vásquez: MGO
Note on C35: Josue Andreé Ricart Vásquez: QUINTOS TRAVEL
Note on C37: Se agrupa con los de endline y cambian los montos de 350K a 800K
Note on C42: Experto en escala vertical
Note on C53: julio
Note on D7: Josue Andreé Ricart Vásquez: Cambia de 3M a 4M ya estaba platicado con John
Note on E5: Josue Andreé Ricart Vásquez: Según hablé con rubén no se tiene planes de realizar este año, voy a trasladar para q7
Note on J52: Josue Andreé Ricart Vásquez: Solo aumente para este trimestre porque no se que sucede si hago que uamenten los montos en los compromisos de todos,

## Error checks (hidden)
Column Number | total
| com-cash |  | cash before Com | [7 empty] | cash before Com
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.a Education Project Implementation Contract | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.b Grants to Universities for Teacher Training (Diplomados) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2 Developing Technical and Vocational Education and Training (0400) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2.a TVET | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3 Strengthening Institutional and Planning Capacity (0043) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.a Education Project Implementation Contract | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.b Education Project Coordination team* | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Education | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2. Resource Mobilization Project (REV RFRM) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1 Improving Tax and Customs Administration (0443)** | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1.a Tax and Customs | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2 Strengthening Public-Private Partnership Capacity (0414) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.a Advisors | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.b Feasiblity Studies/ Transaction Advisory Services | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Resource Mobilization | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3. M&E (MON & Eval) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Monitoring and Evaluation (0016) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.a Student Assessment | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.b Teacher Evaluations | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.c Voc Ed Tracer Studies | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error
3.1 d Other | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - M&E | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4. Program Admin (PGM ADMIN) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Program Administration (0017) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.a Staff Compensation* | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.b Travel* | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error
4.1.c Audit | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.d Other | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error | error | error | error | error | error
TOTAL - Program Admin | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL MCA-Managed Threshold Funds

## Historico (hidden)
|  |  | 23584570 |  | Percent of disbursements by quarter | [14 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# |  | Contract name | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  | Contract name |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 1.1.a Education Project Implementation Contract | Exito Escolar 1.1 | 8500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 255000 | 425000 | 425000 | 425000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 0 | 0 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | Pedagogical Resource centers | 200000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Diplomado Training | 3000000 | q6 | 2018-01-01: 12.5%; 2018-04-01: 12.5%; 2018-07-01: 12.5%; 2018-10-01: 12.5%; 2019-01-01: 12.5%; 2019-04-01: 12.5%; 2019-07-01: 12.5%; 2019-10-01: 12.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET place holder | 4000000 | q5 |  |  |  |  | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 100% | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 200000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract | Exito Escolar 1.3 | 2500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit | 140000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit (option 1) | 140000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 4000 | q3 | 2017-01-01: 100% | 100% | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants | 100000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | [18 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training | 150000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training option | 150000 | q6 | 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach | 73500 | q3 | 2017-01-01: 16.67%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 8.333% | 100% | 0 | 0 | 12250 | 18375 | 18375 | 18375 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 1 | 147000 | q6 | 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 2 | 147000 | q8 | 2018-10-01: 16.67%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) | 61250 | q2 | 2016-10-01: 20%; 2017-01-01: 60%; 2017-04-01: 20% | 100% | 0 | 12250 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Feasiblity Study | 500000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Transaction Advisor | 200000 | q3 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Feasiblity Study | 350000 | [16 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Transaction Advisor | 200000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Feasiblity Study | 350000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 87500 | 87500 | 87500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Transaction Advisor | 50000 | q5 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 500000 | q12 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 3 validadores para Pruebas de Educación de Nivel Medio | 7200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 2160 | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 6 redactores para Pruebas de Educación de Nivel Medio. | 19200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 5760 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 1 curriculista para Pruebas de Educación de Nivel Medio. | 8000 | q3 | 2017-01-01: 50%; 2017-04-01: 50% | 100% | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. | 72000 | q3 |  |  | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% |  | 100% | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 100000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.d | 3.1 d Other | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
4.1.c | 4.1.c Audit | Audit | 90000 | q5 | 2018-01-01: 16.67%; 2018-04-01: 16.67%; 2019-01-01: 16.67%; 2019-04-01: 16.67%; 2020-01-01: 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 11500 | q2 | 2016-10-01: 67%; 2017-01-01: 33% | 100% | 0 | 7705 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [35 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 1.3.b Education Project Coordination team* | Director de Proyecto de Educación | 121400 | q2 |  | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 121400 | 0 | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 31400 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 18000 | 0 | 0
1.3.b | 1.3.b Education Project Coordination team* | Asistente de Proyecto de Educación | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador MCC-THP | 181000 | q1 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 181000 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 49000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asistente Administrativo Bilingüe | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista de Monitoreo y Evaluación | 147000 | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147000 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 21000 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador Administrativo Financiero (Especialista financiero) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en Adquisiciones MCC (Especialista en adquisiciones) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista Economista | 72000 | q4 |  |  |  | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 |  |  |  |  | 72000
1.2.a | 1.2.a TVET | FxT Coordinator | 144000 | q4 |  |  | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [50 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 20000 |  |  | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 19999.82 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 4.1.b Travel* | Travel | 35000 |  |  | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
| Total Comprometido a la fecha |  | 23584570
1.1.a | 1.1.a Education Project Implementation Contract |  | 8700000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 3000000
1.2.a | 1.2.a TVET |  | 4144000
1.3.a | 1.3.a Education Project Implementation Contract |  | 2500000
1.3.b | 1.3.b Education Project Coordination team* |  | 178400
| Education Project Total |  | 18522400 | 19300000 | 777600
2.1.a | 2.1.a Tax and Customs |  | 384000
| Tax and Customs |  | 384000 | 800000 | 416000
2.2.a | 2.2.a Advisors |  | 728750
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 1650000
| PPPs |  | 2378750 | 3600000 | 1221250
3.1.a | 3.1.a Student Assessment |  | 706400
3.1.b | 3.1.b Teacher Evaluations |  | 300000
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 300000
3.1.d | 3.1 d Other |  | 200000
| M&E |  | 1506400 | 1700000 | 193600
4.1.a | 4.1.a Staff Compensation* |  | 636520
4.1.b | 4.1.b Travel* |  | 35000
4.1.c | 4.1.c Audit |  | 90000
4.1.d | 4.1.d Other |  | 31500
| Program Admin |  | 793020 | 797500 | 4480