## DFP-Com
Detailed Financial Plan - Commitments
| Country: |  | Guatemala
| Accountable Entity: |  | PRONACOM
| Grant Number: |  | TR14GTM15001
| Date Submitted: |  | 2019-06-03
| Quarter # |  | 13
| Forecasted Commitments for -> | Cumulative | Current Period | Next Period | [9 empty] | TOTAL | TOTAL | Variance
|  | Actual Cumulative Commitments at Beginning of Current Period | Projected Commitments during Current Period | Grant Quarter #13 |  |  | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Grant Quarter #17 | Grant Quarter #18 | CLOSE OUT Grant Quarter #19 | Commitments As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)* | Projections vs. Approved Plan Under / (Over) Budget Difference
| Date/Month/Quarter -> | Mar '2019 | Apr '19 Jun '19 | Jul '19 | Aug`19 | Sep ´19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20 | Jul '20 Sep '20 | Oct '20 Dec '20 | Jan '21 Mar '21
| Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 | 1.1 Improving the Quality of Education (0277) | 11786956.34 | -31858.47 | 0 | 229065.33 | 0 | 229065.33 | 0 | 0 | 0 |  |  |  | 11984163.2 | 12000000 | 15836.8
1.1.a | 1.1.a Education Project Implementation Contract | 7593016.09 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7593016.09 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | 4193410.79 | -31858.47 | 0 | 229065.33 | 0 | 229065.33 | 0 | 0 | 0 | 0 | 0 | 0 | 4390617.65 | 0
1.1.c | 1.1.c Other | 529.46 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0
1.2 | 1.2 Developing Technical and Vocational Education and Training (0400) | 3600319.61 | 34679.4 | 369604.82 | 0 | 8000 | 377604.82 | 205000 | 55000 | 23295.5 | 0 | 0 | 0 | 4295899.33 | 4300000 | 4100.67
1.2.a | 1.2.a TVET | 3600319.61 | 34679.4 | 369604.82 |  | 8000 | 377604.82 | 205000 | 55000 | 23295.5 | 0 | 0 | 0 | 4295899.33 | 0
1.3 | 1.3 Strengthening Institutional and Planning Capacity (0043) | 2963462.39 | 0 | 0 | 0 | 0 | 0 | 29991 | 48122 | 0 | 0 | 1486.28 | 2277.2 | 3045338.87 | 3046000 | 661.13
1.3.a | 1.3.a Education Project Implementation Contract | 2772876.18 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772876.18
1.3.b | 1.3.b Education Project Coordination team* | 190169.6 | 0 | 0 | 0 |  | 0 | 29991 | 48122 | 0 | 0 | 1486.28 | 2277.2 | 272046.08
1.3.c | 1.3.c Other | 416.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416.61
TOTA | TOTAL - Education | 18350738.34 | 2820.93 | 369604.82 | 229065.33 | 8000 | 606670.15 | 234991 | 103122 | 23295.5 | 0 | 1486.28 | 2277.2 | 19325401.4 | 19346000 | 20598.6
2. R | 2. Resource Mobilization Project (REV RFRM)
2.1 | 2.1 Improving Tax and Customs Administration (0443)** | 498628.09 | 1369.14 | 70005 | 3630.86 | 0 | 73635.86 | 39526.5 | 0 | 0 | 0 | 0 | 0 | 613159.59 | 800000 | 186840.41
2.1.a | 2.1.a Tax and Customs | 498628.09 | 1369.14 | 70005 | 3630.86 | 0 | 73635.86 | 39526.5 | 0 | 0 | 0 | 0 | 0 | 613159.59
2.2 | 2.2 Strengthening Public-Private Partnership Capacity (0414) | 1648270.55 | -65850.11 | 0 | 3000 | 0 | 3000 | 1484550 | 0 | 0 | 0 | 0 | 0 | 3069970.44 | 3560000 | 490029.56
2.2.a | 2.2.a Advisors | 587282.03 | -75734.36 |  | 3000 |  | 3000 | 184550 | 0 | 0 | 0 | 0 | 0 | 699097.67
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | 1030229 | 0 |  |  |  | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 2330229
2.2.c | 2.2.c Other | 30759.52 | 9884.25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40643.77
TOTA | TOTAL - Resource Mobilization | 2146898.64 | -64480.97 | 70005 | 6630.86 | 0 | 76635.86 | 1524076.5 | 0 | 0 | 0 | 0 | 0 | 3683130.03 | 4360000 | 676869.97
3. M | 3. M&E (MON & Eval)
M | Monitoring and Evaluation (0016) | 448997.11 | -6498 | 93000 | 17000 | 3000 | 113000 | 330000 | 100000 | 30000 | 0 | 0 | 0 | 1015499.11 | 1431000 | 415500.89
3.1.a | 3.1.a Student Assessment | 428403.75 | -6498 | 70000 |  |  | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 491905.75
3.1.b | 3.1.b Teacher Evaluations | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | 20593.36 | 0 | 23000 | 17000 | 3000 | 43000 | 330000 | 100000 | 30000 | 0 | 0 | 0 | 523593.36
| TOTAL - M&E | 448997.11 | -6498 | 93000 | 17000 | 3000 | 113000 | 330000 | 100000 | 30000 | 0 | 0 | 0 | 1015499.11 | 1431000 | 415500.89
4. Program Admin (PGM ADMIN)
| Program Administration (0017) | 673779.13 | 106625.15 | 29991 | 2000 | 59712.32 | 91703.32 | 2240.63 | 67988 | 23830.9 | 74679.28 | 3000 | 14679.91 | 1058526.32 | 1060500 | 1973.68
4.1.a | 4.1.a Staff Compensation* | 484918.67 | 60625.15 | 29991 |  | 49998 | 79989 | 0 | 65988 | 22503 | 67679.28 | 0 | 14679.91 | 796383.01
4.1.b | 4.1.b Travel* | 28298.4 | 6539.03 |  | 2000 | 2000 | 4000 | 240.63 | 0 | 0 | 0 | 0 | 0 | 39078.06
4.1.c | 4.1.c Audit | 120000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
4.1.d | 4.1.d Other | 40562.06 | 39460.97 |  |  | 7714.32 | 7714.32 | 2000 | 2000 | 1327.9 | 7000 | 3000 | 0 | 103065.25
| TOTAL - Program Admin | 673779.13 | 106625.15 | 29991 | 2000 | 59712.32 | 91703.32 | 2240.63 | 67988 | 23830.9 | 74679.28 | 3000 | 14679.91 | 1058526.32 | 1060500 | 1973.68
| TOTAL MCA-Managed Threshold Funds | 21620413.22 | 38467.11 | 562600.82 | 254696.19 | 70712.32 | 888009.33 | 2091308.13 | 271110 | 77126.4 | 74679.28 | 4486.28 | 16957.11 | 25082556.86 | 26197500 | 1114943.14
* This activity has MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.
-27462.79
442963.68

## DFP-CASH
Detailed Financial Plan - Cash
Country: |  | Guatemala
Accountable Entity: |  | PRONACOM
Grant Number: |  | TR14GTM15001
Date Submitted: |  | 2019-06-03
Quarter # |  | 13
Forecasted Cash for -> | Cumulative | Current Period | Next Period | [9 empty] | TOTAL | TOTAL | Variance
| Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period | Grant Quarter #13 |  |  | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Grant Quarter #17 | Grant Quarter #18 | CLOSE OUT Grant Quarter #19 | Cash Disbursements As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)** | Projections vs. Approved Plan Under / (Over) Budget Difference
Date/Month/Quarter -> | Mar '2019 | Apr '19 Jun '19 | Jul '19 | Aug`19 | Sep ´19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20 | Jul '20 Sep '20 | Oct '20 Dec '20 | Jan '21 Mar '21
Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | 4689108.13 | 1829993.9789 | 25914.73 | 207219.9 | 692052.67 | 925187.301 | 1210678.5017 | 827164.1881 | 530991.9603 | 726372.2562 | 1244666.8665 | 0.018275 | 11984163.2011 | 12000000 | 15836.7989
1.1.a Education Project Implementation Contract | 3161597.13 | 1243907.0689 | 25914.73 | 0 | 518294.61 | 544209.341 | 570124.0717 | 0 | 518294.6103 | 518294.6203 | 1036589.2306 | 0.018275 | 7593016.0911 | 0
1.1.b Grants to Universities for Teacher Training (Diplomados) | 1526981.54 | 586086.91 | 0 | 207219.9 | 173758.06 | 380977.96 | 640554.43 | 827164.1881 | 12697.35 | 208077.6359 | 208077.6359 | 0 | 4390617.65 | 0
1.1.c Other | 529.46 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0
1.2 Developing Technical and Vocational Education and Training (0400) | 1184038.1 | 362761.15 | 26310.67 | 397153.51 | 111939.48 | 535403.664 | 596751.895 | 388801.205 | 883702.525 | 327640.791 | 8400 | 8400 | 4295899.33 | 4300000 | 4100.67
1.2.a TVET | 1184038.1 | 362761.15 | 26310.67 | 397153.51 | 111939.48 | 535403.664 | 596751.895 | 388801.205 | 883702.525 | 327640.791 | 8400 | 8400 | 4295899.33 | 0
1.3 Strengthening Institutional and Planning Capacity (0043) | 1685737.79 | 434604.1681 | 6409.6 | 32965.29 | 110389.01 | 149763.8934 | 122408.9226 | 18750 | 485215.1518 | 122408.9226 | 18750 | 7700.0135 | 3045338.8621 | 3046000 | 661.1379
1.3.a Education Project Implementation Contract | 1554883.82 | 414635.6881 | 0 | 25914.73 | 103658.92 | 129573.6534 | 103658.9226 | 0 | 466465.1518 | 103658.9226 | 0 | 0.013521 | 2772876.1721 | 0
1.3.b Education Project Coordination team* | 130437.36 | 19968.48 | 6409.6 | 7050.56 | 6730.09 | 20190.24 | 18750 | 18750 | 18750 | 18750 | 18750 | 7700 | 272046.08 | 0
1.3.c Other | 416.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416.61 | 0
TOTAL - Education | 7558884.02 | 2627359.297 | 58635 | 637338.7 | 914381.16 | 1610354.8584 | 1929839.3193 | 1234715.3931 | 1899909.6371 | 1176421.9699 | 1271816.8665 | 16100.0318 | 19325401.3932 | 19346000 | 20598.6068
2. Resource Mobilization Project (REV RFRM)
2.1 Improving Tax and Customs Administration (0443)** | 336192.26 | 55275.98 | 16071.44 | 24165.58 | 22021.92 | 62258.94 | 68362.1775 | 48366.8925 | 32821.725 | 9881.625 | 0 | 0 | 613159.6 | 800000 | 186840.4
2.1.a Tax and Customs | 336192.26 | 55275.98 | 16071.44 | 24165.58 | 22021.92 | 62258.94 | 68362.1775 | 48366.8925 | 32821.725 | 9881.625 | 0 | 0 | 613159.6
2.2 Strengthening Public-Private Partnership Capacity (0414) | 906564.68 | 221516.13 | 412091.6 | 20000 | 0 | 432091.6 | 452198.03 | 439200 | 593700 | 24700 | 0 | 0 | 3069970.44 | 3560000 | 490029.56
2.2.a Advisors | 463692.56 | 5607.08 |  | 20000 | 0 | 20000 | 62198.03 | 49200 | 73700 | 24700 | 0 | 0 | 699097.67
2.2.b Feasiblity Studies/ Transaction Advisory Services | 412112.6 | 206024.8 | 412091.6 | 0 |  | 412091.6 | 390000 | 390000 | 520000 | 0 | 0 | 0 | 2330229
2.2.c Other | 30759.52 | 9884.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40643.77
TOTAL - Resource Mobilization | 1242756.94 | 276792.11 | 428163.04 | 44165.58 | 22021.92 | 494350.54 | 520560.2075 | 487566.8925 | 626521.725 | 34581.625 | 0 | 0 | 3683130.04 | 4360000 | 676869.96
3. M&E (MON & Eval)
Monitoring and Evaluation (0016) | 308499.11 | 27462.79 | 3000 | 45220 | 20220 | 68440 | 431764.81 | 143972.4 | 11600 | 11600 | 12160 | 0 | 1015499.11 | 1431000 | 415500.89
3.1.a Student Assessment | 287849.7 | 27462.79 | 0 | 28220 | 17220 | 45440 | 99764.81 | 8972.4 | 6600 | 6600 | 9160 | 0 | 491849.7
3.1.b Teacher Evaluations | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c Voc Ed Tracer Studies | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 d Other | 20649.41 | 0 | 3000 | 17000 | 3000 | 23000 | 332000 | 135000 | 5000 | 5000 | 3000 | 0 | 523649.41
TOTAL - M&E | 308499.11 | 27462.79 | 3000 | 45220 | 20220 | 68440 | 431764.81 | 143972.4 | 11600 | 11600 | 12160 | 0 | 1015499.11 | 1431000 | 415500.89
4. Program Admin (PGM ADMIN)
Program Administration (0017) | 476516.57 | 71196.1 | 29077.7 | 22057.26 | 29798.7 | 80933.66 | 85709.21 | 110468.5806 | 67796.48 | 59825.72 | 54540 | 51540 | 1058526.3206 | 1060500 | 1973.6794
4.1.a Staff Compensation* | 379911.27 | 51267.52 | 19434.84 | 17414.4 | 19155.84 | 56005.08 | 51540 | 51540 | 51540 | 51540 | 51540 | 51540 | 796423.87
4.1.b Travel* | 27475.04 | 6284.33 | 0 | 2000 | 2000 | 4000 | 240.63 | 0 | 0 | 0 | 0 | 0 | 38000
4.1.c Audit | 31000 | 12000 | 6000 | 0 | 6000 | 12000 | 20000 | 45000.0006 | 0 | 0 | 0 | 0 | 120000.0006
4.1.d Other | 38130.26 | 1644.25 | 3642.86 | 2642.86 | 2642.86 | 8928.58 | 13928.58 | 13928.58 | 16256.48 | 8285.72 | 3000 | 0 | 104102.45
TOTAL - Program Admin | 476516.57 | 71196.1 | 29077.7 | 22057.26 | 29798.7 | 80933.66 | 85709.21 | 110468.5806 | 67796.48 | 59825.72 | 54540 | 51540 | 1058526.3206 | 1060500 | 1973.6794
TOTAL MCA-Managed Threshold Funds | 9586656.64 | 3002810.297 | 518875.74 | 748781.54 | 986421.78 | 2254079.0584 | 2967873.5469 | 1976723.2662 | 2605827.8421 | 1282429.3149 | 1338516.8665 | 67640.0318 | 25082556.8638 | 26197500 | 1114943.1362
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.

## QFR - A
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2019-06-07
Schedule A. Multi-Year Financial Plan Adjustment Request Form
Disbursement Period:01-jul-19 to 30-sep-19
Amounts Expressed In US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Current Approved Multi-Year Financial Plan | Proposed Adjustments (Display all #'s as positive) |  | Proposed Adjusted Multi-Year Financial Plan
Project (code) |  | (from Schedule B, Final Column) | Increase (+) | Decrease (-) | (2+3-4)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | 19346000 | 0 | 0 | 19346000
1.1 Improving the Quality of Education (0277) | 12000000 | 12000000 |  | 0 | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | 4300000 | 0 |  | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 3046000 | 0 |  | 3046000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 4360000 | 0 | 0 | 4360000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 |  |  | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | 3560000 |  |  | 3560000
3. M&E (MON & EVAL) | 1700000 | 1431000 | 0 | 0 | 1431000
Monitoring and Evaluation (0016) | 1700000 | 1431000 |  | 0 | 1431000
4. Program Admin (PGM ADMIN) | 800000 | 1060500 | 0 | 0 | 1060500
Program Administration (0017) | 800000 | 1060500 |  | 0 | 1060500
Grand Total | 26200000 | 26197500 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 1800000 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 | 1800000 |  |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 2500 | 0 | 0 | 2500
Program Administration (0017) | 0 | 2500 | 0 |  | 2500
Grand Total | 1800000 | 1802500 | 0 | 0 | 1802500

## QFR - B
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2019-06-07
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-jul-19 to 30-sep-19
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (Q6 - 10/11/2017) | Adjustment Reported/ Approved (Q10 - 05/11/2018) | Adjustment Reported/ Approved (Q12- 01/04/2019) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 |  | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 46000 | 0 | 19346000
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 |  | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 |  | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 46000 |  | 3046000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | -40000 | 4360000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 |  | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | -40000 | 3560000
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | -269000 | 0 | 1431000
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | -269000 |  | 1431000
4. Program Admin (PGM ADMIN) | 800000 | 0 | -2500 | 223000 | 40000 | 1060500
Program Administration (0017) | 800000 | 0 | -2500 | 223000 | 40000 | 1060500
Grand Total | 26200000 | 0 | -2500 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 |  | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  | 0 |  |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 0 | 2500 | 0 |  | 2500
Program Administration (0017) |  |  | 2500 |  |  | 2500
Grand Total | 1800000 | 0 | 2500 | 0 |  | 1802500

## THP DR
DISBURSEMENT REQUEST
THRESHOLD PROGRAM GRANT AGREEMENT
Country | Guatemala
Projects | Threshold Program / Program Administration and Monitoring and Evaluation
Threshold Program Grant Agreement Date/ Entry into Force Date | April 8, 2015/May 16, 2016
Threshold Program Number | TR14GTM15001
Accountable Entity | PRONACOM
Fiscal Agent | MCC (Acting Fiscal Agent)
Request Date | 2019-02-27
Disbursement Period Beginning Date | 2019-07-01
Disbursement Period Ending Date | 2019-09-30
Disbursement Number | 13
Currency (Expressed in USD) | US Dollars
Exchange Rate used to calculate U.S. Dollar equivalent of any local currency balance for purposes of this MCC Disbursement Request
A. Disbursement Request: The undersigned hereby requests the Millennium Challenge Corporation to disburse funds under the Threshold Grant Agreement, dated as of August 28,2013 as follows:
1. Forecasted Cash Disbursement Requirements (from DFP Cash Column) | 2254079.0584
2. Interest to be Returned to the USG for Next Period (Interest Sum, Line 7)
3. Working Capital (FOR MCC USE ONLY)
4. Cash Balance at the End of the Current Period (Cash Req, Line 7) | 0
5. Disbursement Request Amount (Lines 1+2-4) | 2254079.0584
6. Amount Requested in Words | Two million two hundred fifty-four thousand seventy-nine and six hundredths
C. Compliance: the undersigned confirms that the MCC Disbursement requested herby is in accordance with the terms and conditions set forth in the Threshold Program Agreement, including the limitations on the use or treatment of MCC Funding set out in Section 2.4.
D. Authorization: the undersigned acknowledges that funds disbursed in accordance with this request will be either made (i) directly to third-party vendors for goods, works and services received by the accountable entity upon presentation of valid invoices utilizing MCC's Common Payment System, (ii) to the Permitted Account, or (iii) to the Petty Cash Account.
E. Certificates: Attached hereto are the certificates required under Section 5.2 and 5.3 of the Threshold Program Agreement.
F. Definitions: Capitalized terms used herein shall have the meanings assigned to such terms in the Threshold Program Agreement by and between the Government of Guatemala and the United States, acting through the Millennium Challenge Corporation, dated April 8, 2015, and entered into force on May 15, 2016.
Signed by the THP Deputy Executive Director
By: _______________________________________________________________
Name: Manfredo Octavio Chocano
Date: June 20, 2019
Certified by the Executive Director of PRONACOM
By: _______________________________________________________________
Name: Francisca de Jesús Cárdenas Morán
Date: June 20, 2019____________________________________________________
By: _______________________________________________________________
Name:
Date:

## Contract level (hidden)
|  | Q13 check | 25082556.87 |  | Percent of disbursements by quarter | [17 empty] | Close Out | Total |  |  | Cash by quarter | [17 empty] | Close Out | Committments by quarter
Act# |  | Contract name | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 |  |  |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | check Cash=comm
Act# |  | Contract name |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | 19 |  |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16
1.1.a | 1.1.a Education Project Implementation Contract | Exito Escolar 1.1 | 7593016.09 | q4 |  |  |  | 0% | 9.556% | 8.191% | 7.509% |  | 6.826% | 0% | 9.556% | 16.38% | 7.167% | 7.509% | 0% | 6.826% | 6.826% | 13.65% | 2.407e-07% | 100% |  |  | 0 | 0 | 0 | 0 | 725612.46 | 621953.53 | 570124.07 | 0 | 518294.61 | 0 | 725612.4589 | 1243907.0689 | 544209.341 | 570124.0717 | 0 | 518294.6103 | 518294.6203 | 1036589.2306 | 0.018275 | 0 | 0 | 0 | 7593016.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Equipo de técnología informatica para los docentes del profesorado. | 229065.33 | q13 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 75.86%; 2019-10-01: 18.6%; 2020-04-01: 5.543% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173758.06 | 42609.92 | 0 | 12697.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229065.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | PEM Training INTERNACIONES PU-MCC-SNC-002-2017 | 1866155 | q9 | 2018-07-01: 15%; 2018-10-01: 15%; 2019-01-01: 5%; 2019-04-01: 15%; 2019-07-01: 5%; 2019-10-01: 15%; 2020-01-01: 20%; 2020-07-01: 5%; 2020-10-01: 5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279923.25 | 279923.25 | 93307.75 | 279923.25 | 93307.75 | 279923.25 | 373231 | 0 | 93307.75 | 93307.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | PEM Training UVG MCC-SUBV-002-2018 | 1109637.32 | q9 | 2018-07-01: 13.14%; 2018-10-01: 17.72%; 2019-01-01: 5.343%; 2019-04-01: 14.77%; 2019-07-01: 4.923%; 2019-10-01: 14.77%; 2020-01-01: 19.34%; 2020-07-01: 5%; 2020-10-01: 5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145812.42 | 196636.07 | 59288 | 163872.46 | 54624.15 | 163872.46 | 214567.9881 | 0 | 55481.8859 | 55481.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109637.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | PEM Training UPANA MCC-SUBV-003-2018 | 1185760 | q9 | 2018-07-01: 0%; 2018-10-01: 35%; 2019-01-01: 4.813%; 2019-04-01: 12%; 2019-07-01: 5%; 2019-10-01: 13%; 2020-01-01: 20.19%; 2020-07-01: 5%; 2020-10-01: 5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415016 | 57074.8 | 142291.2 | 59288 | 154148.8 | 239365.2 | 0 | 59288 | 59288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.c | 1.1.c Other | Travel Renta de vehículos | 529.46 | q8 | 2017-07-01: 0%; 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 100%; 2018-07-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | GOPA (MINEDUC) TVET contract MCC-FC-003-2017 | 2329506.84 | q6 | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 2% | 8% | 11% | 14% | 8% | 13% | 10% | 0% | 20% | 8% | 0% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 139770.41 | 46590.14 | 186360.55 | 256245.77 | 326130.96 | 186360.55 | 302835.9 | 232950.69 | 0 | 465901.32 | 186360.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2329506.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | A-TVET (GOPA - ENCA) MCC-FC-002-2018 | 1200000 | q9 | 2018-10-01: 10%; 2019-01-01: 4%; 2019-04-01: 14%; 2019-07-01: 10%; 2019-10-01: 9%; 2020-01-01: 19%; 2020-04-01: 26%; 2020-07-01: 8% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 48000 | 168000 | 120000 | 108000 | 228000 | 312000 | 96000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Equipo para 20 centros | 150000 | q14 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 100%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Libros INTECAP | 8000 | q13 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 100%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET Training of Trainers (INTECAP) | 244604.82 | q13 | 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 20%; 2019-10-01: 25%; 2020-01-01: 25%; 2020-04-01: 25%; 2020-07-01: 5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48920.964 | 61151.205 | 61151.205 | 61151.205 | 12230.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244604.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Programa de formación en inglés (Inglés) FORMADORES ACOMPAÑANTES | 50000 | q13 | 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 7.2%; 2019-10-01: 25%; 2020-01-01: 25%; 2020-04-01: 25%; 2020-07-01: 17.8% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 12500 | 12500 | 12500 | 8900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Programa de formación en inglés (Inglés) coordinador | 40000 | q13 | 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 20%; 2019-10-01: 25%; 2020-01-01: 25%; 2020-04-01: 25%; 2020-07-01: 5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 10000 | 10000 | 10000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Programa de formación en inglés (Inglés) compra de libros | 35000 | q13 | 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 100%; 2019-10-01: 0%; 2020-01-01: 0%; 2020-04-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Programa de formación en inglés (Inglés) compra de libros fase 2 | 55000 | q15 | 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 100%; 2020-04-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | Contratación de Transporte para formación de docentes | 55000 | q14 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13750 | 13750 | 13750 | 13750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract | Exito Escolar 1.3 | 2772876.18 | q4 |  |  |  | 0% |  | 7.477% | 5.607% | 7.477% | 3.738% | 26.17% | 5.607% | 14.95% | 4.673% | 3.738% | 0% | 16.82% | 3.738% |  | 4.876e-07% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 207317.8452 | 155488.38 | 207317.84 | 103658.92 | 725612.46 | 155488.3827 | 414635.6881 | 129573.6534 | 103658.9226 | 0 | 466465.1518 | 103658.9226 | 0 | 0.013521 | 0 | 0 | 0 | 2772876.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 1.3.c Other | Gastos de Representación | 23.99 | q7 | 2017-07-01: 0%; 2017-10-01: 0%; 2018-01-01: 100%; 2018-04-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 1.3.c Other | Perdiem | 56.92 | q7 | 2017-07-01: 0%; 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for audit (mauricio) | 36998.88 | q3 | 2017-04-01: 24.33%; 2017-07-01: 26.2%; 2017-10-01: 23.7%; 2018-01-01: 25.78%; 2018-04-01: 0% | 100% |  |  | 0 | 0 | 0 | 9000 | 9691.92 | 8768.88 | 9538.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36998.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants (Keny, Alvaro y Edgar) | 99851.16 | q3 | 2017-01-01: 0%; 2017-04-01: 33.05%; 2017-07-01: 27.12%; 2017-10-01: 26.27%; 2018-01-01: 13.56% | 100% |  |  | 0 | 0 | 0 | 33000 | 27079.68 | 26231.64 | 13539.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99851.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 4000 | q3 | 2017-01-01: 100% | 100% |  |  | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Database subscriptions Base de datos datasur | 1500 | q4 | 2017-04-01: 100%; 2017-10-01: 0% | 100% |  |  | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for audit (mauricio) 2 option | 43134 | q7 | 2018-01-01: 0%; 2018-04-01: 24.62%; 2018-07-01: 26.26%; 2018-10-01: 25.44%; 2019-01-01: 23.69% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10617.6 | 11325.44 | 10971.52 | 10219.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Asistente Bilingüe (Lilian 2018) | 18489.64 | q7 | 2018-01-01: 17.48%; 2018-04-01: 24.35%; 2018-07-01: 27.06%; 2018-10-01: 25.7%; 2019-01-01: 5.411% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 4502.16 | 5002.4 | 4752.28 | 1000.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18489.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 1800 | q7 | 2017-01-01: 0%; 2018-01-01: 100%; 2018-04-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants (Keny, Alvaro y Edgar) ENM 2 | 111566.08 | q7 | 2018-01-01: 8.43%; 2018-04-01: 0.26744; 2018-07-01: 27.62%; 2018-10-01: 27.03%; 2019-01-01: 10.17% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9405.28 | 29837.44 | 30810.4 | 30161.76 | 11351.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111566.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Per diem | 7725.48 | q7 | 2017-10-01: 0%; 2018-01-01: 100%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | rental of computer equipment for training | 1241.07 | q8 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 100%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Per diem | 167.23 | q9 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 100%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for audit (mauricio) 3 option | 35945 | q11 | 2016-07-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 30.52%; 2019-07-01: 31.02%; 2019-10-01: 25.44%; 2020-01-01: 13.03% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10971.52 | 11148.48 | 9142.9333 | 4682.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Asistente Bilingüe (Lilian) | 18759 | q11 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 17.23%; 2019-04-01: 25.33%; 2019-07-01: 26.67%; 2019-10-01: 25.33%; 2020-01-01: 5.436% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 4752.28 | 5002.4 | 4752.28 | 1019.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Consultor duda razonable (Guerra) | 9982.8 | q11 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 100%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9982.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9982.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Consultor duda razonable | 35002.5 | q13 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 17.23%; 2019-10-01: 25%; 2020-01-01: 25%; 2020-04-01: 32.77% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6031.2 | 8750.625 | 8750.625 | 11470.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Consultor duda razonable | 35002.5 | q13 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 17.23%; 2019-10-01: 25%; 2020-01-01: 25%; 2020-04-01: 32.77% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6031.2 | 8750.625 | 8750.625 | 11470.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Consultor Riesgo Mario Ramirez | 35002.5 | q11 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 25.44%; 2019-07-01: 26.67%; 2019-10-01: 24.72%; 2020-01-01: 23.18% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8903.2 | 9334 | 8651.9 | 8113.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Consultor duda razonable (Reemplazo de Edgar Coordinador TI) | 39526.5 | q14 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9881.625 | 9881.625 | 9881.625 | 9881.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39526.5 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants (Keny, Alvaro) ENM 3 | 72465.26 | q11 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 8.951%; 2019-04-01: 26.63%; 2019-07-01: 29.09%; 2019-10-01: 25.44%; 2020-01-01: 9.893% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6486.4 | 19297.04 | 21080.8 | 18432.1892 | 7168.8308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72465.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) Primer contrato sergio bravo | 61250 | q2 | 2016-10-01: 0%; 2017-01-01: 40%; 2017-04-01: 60%; 2017-07-01: 0% | 100% |  |  | 0 | 0 | 24500 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach (valdez) | 121200 | q3 | 2017-04-01: 33.33%; 2017-07-01: 16.67%; 2017-10-01: 33.33%; 2018-01-01: 16.67% | 100% |  |  | 0 | 0 | 0 | 40399.9996 | 20199.9992 | 40399.9996 | 20200.0016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training (honorarios 4 facilitadores) | 124265.64 | q4 | 2017-07-01: 0%; 2017-10-01: 33.77%; 2018-01-01: 7.544%; 2018-04-01: 5.794%; 2018-07-01: 4.989%; 2018-10-01: 4.172%; 2019-01-01: 5.225%; 2019-04-01: 4.512%; 2019-07-01: 13.68%; 2019-10-01: 20.32% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 41958.49 | 9374.56 | 7200 | 6199.74 | 5184.57 | 6493.17 | 5607.08 | 17000 | 25248.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124265.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 2.2.c Other | PPP Conference | 5000 | q4 | 2017-04-01: 100% | 100% |  |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training option (gastos de capacitación en APP) | 57832.03 | q5 | 2017-07-01: 33.33%; 2017-10-01: 44.44%; 2018-01-01: 22.22%; 2019-10-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 19277.35 | 25703.12 | 12851.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57832.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) (sergio bravo segundo contrato) | 147000 | q5 | 2017-07-01: 8.333%; 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 33.33%; 2018-07-01: 16.67%; 2018-10-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 12250 | 24500 | 36750 | 49000 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 2.2.c Other | PPP Conference | 961.64 | q5 | 2017-07-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Feasiblity Study (Deloitte) | 1030229 | q6 | 2017-10-01: 0%; 2018-01-01: 10%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 30%; 2019-01-01: 0%; 2019-04-01: 20%; 2019-07-01: 40% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 103022.9 | 0 | 0 | 309089.7 | 0 | 206024.8 | 412091.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | gastos de capacitación en APP con Eduardo Escobal | 3000 | q13 | [19 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2016-07-01 to 2021-01-01
2.2.c | 2.2.c Other | PPP APP Conference UK | 24797.88 | q10 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24797.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24797.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) (sergio bravo tercer contrato) | 85750 | q14 | 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 14.29%; 2020-01-01: 28.57%; 2020-04-01: 57.14% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12250 | 24500 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85750 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 2.2.c Other | PPP APP Conference UK (IPA) | 9884.25 | q12 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9884.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9884.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach Asesor Minfin | 98800 | q14 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24700 | 24700 | 24700 | 24700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98800 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Metro Riel Transaction Advisor Fase 1 | 1300000 | q14 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 30%; 2020-01-01: 30%; 2020-04-01: 40% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 390000 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 1 curriculista para Pruebas de Educación de Nivel Medio. Patricia zuleta | 8000 | q3 | 2017-04-01: 50%; 2017-07-01: 50% | 100% |  |  | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. Francisco Ureta | 52000 | q3 |  |  |  | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 7.692% | 0% | 0% | 0% |  |  |  |  | 100% |  |  | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 3 validadores para Pruebas de Educación de Nivel Medio | 8100 | q4 | 2017-04-01: 0%; 2017-07-01: 41.67%; 2017-10-01: 58.33% | 100% |  |  | 0 | 0 | 0 | 0 | 3375 | 4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 6 redactores para Pruebas de Educación de Nivel Medio. | 18700 | q4 | 2017-04-01: 0%; 2017-07-01: 36.36%; 2017-10-01: 63.64% | 100% |  |  | 0 | 0 | 0 | 0 | 6800 | 11900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 9 enumertors for Pilot | 13200 | q5 | 2017-10-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q5 (payed q6) | 640.16 | q5 | 2017-10-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q6 | 13864.72 | q6 | 2017-10-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q7 | 475.49 | q7 | 2018-01-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea base (HOTEL) | 49165.09 | q7 | 2018-01-01: 0%; 2018-04-01: 88.21%; 2018-07-01: 0%; 2018-10-01: 7.632%; 2019-01-01: 4.163% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43366.39 | 0 | 3752.1 | 2046.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49165.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea base (ARRENDAMIENTO DE VEHÍCULOS) | 38502 | q7 | 2018-01-01: 0%; 2018-04-01: 10.95%; 2018-07-01: 89.05%; 2018-10-01: 0%; 2019-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216 | 34286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea base (PERDIEM) | 68334.49 | q8 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 100%; 2018-10-01: 0%; 2019-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68334.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68334.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea base (IMPRESIONES) | 7848.12 | q8 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 100%; 2018-10-01: 0%; 2019-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q8 | 203.63 | q8 | 2018-01-01: 0%; 2018-04-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Servicio de Traducción Jurada | 179.46 | q8 | 2018-01-01: 0%; 2018-04-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Experto en escala vertical 1 | 28000 | q9 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Servicio de Arrendamiento de vehículos (no linea base) | 2009.07 | q9 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 42.58%; 2018-10-01: 57.42%; 2019-01-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855.52 | 1153.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q9 | 563.15 | q9 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Perdiem q10 | 2713.73 | q10 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 100%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea intermedia (Hotel linea intermedia 2) | 50000 | q11 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 22.26%; 2019-07-01: 58%; 2019-10-01: 15%; 2020-01-01: 4.745% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11127.6 | 29000 | 7500 | 2372.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | recopilación de datos para linea intermedia (Alquiler de vehículos linea intermedia 2) | 80000 | q11 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 15.42%; 2019-07-01: 2.5%; 2019-10-01: 82.08%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12335.19 | 2000 | 65664.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. | 40000 | q13 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 16.5% | 16.5% | 16.5% | 16.5% | 22.9% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4440 | 6600 | 6600 | 6600 | 6600 | 9160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Experto en escala vertical 2 opción | 30000 | q13 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 33.33%; 2019-10-01: 66.67% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Vehículos para monitoreo | 20000 | q13 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 25% | 25% | 25% | 15% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 5000 | 5000 | 5000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Training Capacitaciones para M&E | 9000 | q13 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 100%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | SPSS LICENCE | 14000 | q13 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 100%; 2019-10-01: 0%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | SAT Data collection | 80000 | q14 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 100%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | DQR | 250000 | q14 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 100%; 2020-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Evaluation Training | 100000 | q15 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | Evaluation Dissemination Activities | 30000 | q16 | 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 0%; 2019-01-01: 0%; 2019-04-01: 0%; 2019-07-01: 0%; 2019-10-01: 0%; 2020-01-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
4.1.c | 4.1.c Audit | Audit | 120000 | q8 | 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 8.333%; 2018-07-01: 4.167%; 2018-10-01: 4.167%; 2019-01-01: 9.167%; 2019-04-01: 10%; 2019-07-01: 10%; 2019-10-01: 16.67%; 2020-01-01: 37.5% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.9996 | 4999.9998 | 5000 | 11000 | 12000 | 12000 | 20000 | 45000.0006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 7666.96 | q2 | 2016-10-01: 100%; 2017-01-01: 0%; 2017-04-01: 0% | 100% |  |  | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 1124.38 | q3 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 100% | 100% |  |  | 0 | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking | 982.1 | q3 | 2016-10-01: 0%; 2017-01-01: 18.18%; 2017-04-01: 27.27%; 2017-07-01: 27.27%; 2017-10-01: 27.27% | 100% |  |  | 0 | 0 | 178.5636 | 267.8455 | 267.8455 | 267.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asistente Administrativo Bilingüe | 15389.66 | q3 |  | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15389.66 |  |  | 0 | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14495 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | CONSULTOR IPMS Patrick Cronin | 7222.5 | q3 | 2017-10-01: 0; 2018-01-01: 0; 2018-04-01: 0; 2018-07-01: 0; 2018-10-01: 7222.2 | 7222.2 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7222.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7222.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Furniture, fixtures and equipment | 505.16 | q4 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 100%; 2017-07-01: 0%; 2017-10-01: 0%; 2018-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asesor Legal | 104650.16 | q4 |  |  |  | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6153.6 | 7295.78 | 6828.72 | 6997.9 | 7505.44 | 7720.76 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 104650.16 |  |  | 0 | 0 | 0 | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6153.6 | 7295.78 | 6828.72 | 6997.9 | 7505.44 | 7720.76 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 3384.48 | 24260.44 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 17023.24 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Licences | 1630 | q5 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2017-07-01: 100% | 100% |  |  | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Furniture, fixtures and equipment | 739.99 | q6 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2017-07-01: 0; 2017-10-01: 100%; 2018-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Furniture, fixtures and equipment | 1232.14 | q6 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2017-07-01: 0%; 2017-10-01: 100%; 2018-01-01: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking | 1071.43 | q2 | 2016-10-01: 25%; 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 0% | 100% |  |  | 0 | 267.8575 | 267.8575 | 267.8575 | 267.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking (Contract PU-MCC-SNC-003-2017) | 982.15 | q6 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2017-10-01: 27.27%; 2018-01-01: 27.27%; 2018-04-01: 9.091%; 2018-07-01: 0%; 2018-10-01: 36.36% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 267.85 | 267.87 | 89.29 | 0 | 357.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en seguimiento y control MCC-THP | 30021.76 | q6 | 2016-07-01: 0; 2016-10-01: 0; 2017-01-01: 0; 2017-04-01: 0; 2017-07-01: 0; 2017-10-01: 2706.88; 2018-01-01: 7628.48; 2018-04-01: 7505.44; 2018-07-01: 7751.52; 2018-10-01: 4429.44 | 30021.76 |  |  | 0 | 0 | 0 | 0 | 0 | 2706.88 | 7628.48 | 7505.44 | 7751.52 | 4429.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 30.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking (CONTRACT PU-MCC-SNC-001-2018) | 714.25 | q7 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2018-01-01: 37.5%; 2018-04-01: 12.5%; 2018-07-01: 0%; 2018-10-01: 50% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 267.84 | 89.28 | 0 | 357.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking (NEW CONTRACT) PU-MCC-SNC-015-2018 | 7714.32 | q9 | 2016-10-01: 0%; 2017-01-01: 0%; 2017-04-01: 0%; 2017-10-01: 0%; 2018-01-01: 0%; 2018-04-01: 0%; 2018-07-01: 0%; 2018-10-01: 33.33%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 16.67% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.44 | 1928.58 | 1928.58 | 1285.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | Parking (NEW CONTRACT) PU-MCC-SNC-xx-2018 | 7714.32 | q13 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 25% | 25% | 25% | 16.67% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.86 | 1928.58 | 1928.58 | 1928.58 | 1285.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 |  |  |  | Total | [40 empty] | 0
Salary Type Expenses | [45 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |  | 0
1.3.c | 1.3.c Other | Perdiem | 198.71 | q8 |  |  |  |  | 0% | 0% | 0% | 100% | [11 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 1.3.c Other | Perdiem | 136.99 | q9 |  |  |  |  | 0% | 0% | 0% | 0% | 100% | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.b | 1.3.b Education Project Coordination team* | Director de Proyecto de Educación | 185577.8 | q2 |  | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11848.32 | 10232.64 | 10985.28 | 12340 | 12438.72 | 11550 | 11550 | 11550 | 11550 | 11550 | 7700 | 185577.8 |  |  | 0 | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11848.32 | 10232.64 | 10985.28 | 12340 | 12438.72 | 11550 | 11550 | 11550 | 11550 | 11550 | 7700 | 0 | 43635.2 | 0 | 0 | 0 | 0 | 43421.4 | 0 | 0 | 0 | 48122 | 0 | 0 | 0 | 48122 | 0 | 0 | 0 | 2277.2 | 0
1.3.b | 1.3.b Education Project Coordination team* | Asistente de Proyecto de Educación | 86468.28 | q6 |  |  |  |  | 0 | 2358.88 | 6256.16 | 6410 | 6486.92 | 6193.92 | 7382.4 | 7628.48 | 7751.52 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 86468.28 |  |  | 0 | 0 | 0 |  | 0 | 2358.88 | 6256.16 | 6410 | 6486.92 | 6193.92 | 7382.4 | 7628.48 | 7751.52 | 7200 | 7200 | 7200 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 1486.28 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Per diem | 5000 | q12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 3630.86 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 3630.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 3630.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador MCC-THP / Sub Director PU | 170715.96 | q1 | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 0 | 12204.64 | 11666.2 | 12512.32 | 13332.8 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 170715.96 |  |  | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 0 | 12204.64 | 11666.2 | 12512.32 | 13332.8 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 45000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 49998 | 0 | 0 | 0 | 49998 | 0 | 0 | 0 | 21719.96 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista de Monitoreo y Evaluación | 172841.95 | q2 |  | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 10053.12 | 11489.28 | 9469.68 | 10950.72 | 11489.28 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 172841.95 |  |  | 0 | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 10053.12 | 11489.28 | 9469.68 | 10950.72 | 11489.28 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 7000 | 0 | 3440.43 | 3949.44 | 0 | 43758 | 0 | 0 | 43758 | 0 | 0 | 0 | 0 | 28936.08 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador Administrativo Financiero (Especialista financiero) | 125064.36 | q2 |  | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7351.64 | 8059.12 | 7382.4 | 7653.76 | 8392.32 | 8798.4 | 7920 | 7920 | 7920 | 7920 | 7920 | 7920 | 125064.36 |  |  | 0 | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7351.64 | 8059.12 | 7382.4 | 7653.76 | 8392.32 | 8798.4 | 7920 | 7920 | 7920 | 7920 | 7920 | 7920 | 0 | 6160 | 0 | 29991 | 0 | 0 | 0 | 18517.52 | 0 | 0 | 32994 | 0 | 0 | 0 | 32994 | 0 | 0 | 0 | 4407.84 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en Adquisiciones MCC (Especialista en adquisiciones) | 131954.1 | q2 |  | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7997.6 | 7505.44 | 7395.36 | 8121.6 | 8663.04 | 7920 | 7920 | 7920 | 7920 | 7920 | 7920 | 131954.1 |  |  | 0 | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7997.6 | 7505.44 | 7395.36 | 8121.6 | 8663.04 | 7920 | 7920 | 7920 | 7920 | 7920 | 7920 | 0 | 32185.6 | 0 | 0 | 0 | 0 | 29914.1 | 0 | 0 | 0 | 32994 | 0 | 0 | 0 | 32994 | 0 | 0 | 0 | 3866.4 | 0
4.1.d | 4.1.d Other | IT Equipment (incluye licencias Q10) | 6802.75 | q10 |  | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 100% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6802.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6802.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Finance Assistant | 45785.92 | q12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3785.12 | 6000.8 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 45785.92 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3785.12 | 6000.8 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16877.25 | 0 | 0 | 0 | 22503 | 0 | 0 | 6405.67 | 0
4.1.d | 4.1.d Other | Asesor Político | 40000 | q12 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 17.5% | 25% | 25% | 32.5% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 10000 | 10000 | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | A-TVET Per diem | 318.43 | q8 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | A-TVET Workshops | 884.24 | q8 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | FxT Coordinator | 127585 | q4 |  |  |  | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 9190.4 | 8616 | 8185.2 | 8400.6 | 9046.8 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 127585 |  |  | 0 | 0 | 0 | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 9190.4 | 8616 | 8185.2 | 8400.6 | 9046.8 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 0 | 0 | 0 | 34607.6 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 34679.4 | 0 | 0 | 0 | 23295.5 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [64 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 18000 |  |  | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1327.9 | 7000 | 3000 |  | 18000 |  |  | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1327.9 | 7000 | 3000 | 0 | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1327.9 | 7000 | 3000 | 0 | 0
4.1.b | 4.1.b Travel* | Travel | 38000 |  |  | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 15956.99 | 4226.4 | 3646.67 | 134.66 | 6000 | 4000 | 240.63 | 0 | 0 |  |  |  | 38000 |  |  | 0 | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 15956.99 | 4226.4 | 3646.67 | 134.66 | 6000 | 4000 | 240.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 15956.99 | 4226.4 | 3646.67 | 134.66 | 6000 | 4000 | 240.63 | 0 | 0 | 0 | 0 | 0 | 0
| Total Comprometido a la fecha |  | 25082556.87
1.1.a | 1.1.a Education Project Implementation Contract |  | 7593016.09 | [61 empty] | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 4390617.65 | [61 empty] | 0
1.2.a | 1.2.a TVET |  | 4295899.33 | [61 empty] | 0
1.3.a | 1.3.a Education Project Implementation Contract |  | 2772876.18 | [61 empty] | 0
1.3.b | 1.3.b Education Project Coordination team* |  | 272046.08 | [61 empty] | 0 | bar: Q3
| Education Project Total |  | 19324455.33 | 19346000 | 21544.67 | [59 empty] | 0
2.1.a | 2.1.a Tax and Customs |  | 613159.6 | [61 empty] | 0
| Tax and Customs |  | 613159.6 | 800000 | 186840.4 | [59 empty] | 0
2.2.a | 2.2.a Advisors |  | 699097.67 | [61 empty] | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 2330229 | [61 empty] | 0
| PPPs |  | 3029326.67 | 3560000 | 530673.33 | [59 empty] | 0
3.1.a | 3.1.a Student Assessment |  | 491849.7 | [61 empty] | 0
3.1.b | 3.1.b Teacher Evaluations |  | 0 | [61 empty] | 0
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 0 | [61 empty] | 0
3.1.d | 3.1 d Other |  | 523649.41 | [61 empty] | 0
| M&E |  | 1015499.11 | 1431000 | 415500.89 | [59 empty] | 0
4.1.a | 4.1.a Staff Compensation* |  | 796423.87 | [61 empty] | 0 | bar: Q1 to Q3
4.1.b | 4.1.b Travel* |  | 38000 | [61 empty] | 0
4.1.c | 4.1.c Audit |  | 120000 | [61 empty] | 0
4.1.d | 4.1.d Other |  | 104102.45 | [61 empty] | 0
| Program Admin |  | 1058526.32 | 1060500 | 1973.68 | [59 empty] | 0
|  |  | 100247047.8 | 26197500 | 1166532.97 | 24587.92 | 41876.8318 | 50463.8152 | 60088.8105 | 62773.399 | 58781.0811 | 70677.8193 | 72917.1463 | 85758.6269 | 69873.1287 | 87010.819 | 92883.2983 | 80940.7706 | 80698.2237 | 80022.7687 |  |  |  | 1264377.15 | 0 | 0 | 10000 | 32521.4875 | 70821.4211 | 188272.4126 | 897497.4321 | 1112435.7903 | 1158632.7316 | 493105.2296 | 1507988.4098 | 2492850.45 | 1622530.9816 | 3002810.297 | 2254079.0584 | 2967873.5469 | 1976723.2662 | 2605827.8421 | 1282429.3149 | 1338516.8665 | 67640.0318 | 45000 | 194969.19 | 345873.72 | 10605031.42 | 249524.27 | 3435262.41 | 348937.88 | 269214.62 | 5528116.48 | 67982.79 | 416399.22 | 152568.04 | 888009.33 | 2091308.13 | 271110 | 77126.4 | 74679.28 | 4486.28 | 16957.11 | 0
[27 empty] | 10000 | 42521.4875 | 113342.9086 | 301615.3212 | 1199112.7533 | 2311548.5436 | 3470181.2752 | 3963286.5048 | 5471274.9146 | 7964125.3646 | 9586656.3462 | 12589466.6432 | 14843545.7016 | 17811419.2485 | 19788142.5147 | 22393970.3568 | 23676399.6717 | 25014916.5382 | 25082556.57 | 45000 | 239969.19 | 585842.91 | 11190874.33 | 11440398.6 | 14875661.01 | 15224598.89 | 15493813.51 | 21021929.99 | 21089912.78 | 21506312 | 21658880.04 | 22546889.37 | 24638197.5 | 24909307.5 | 24986433.9 | 25061113.18 | 25065599.46 | 25082556.57
|  |  | #REF! | [11 empty] | 20% | [21 empty] | 379911.27 | [8 empty] | Q3: 448997.11; Q4: -21057314.89
[18 empty] | 0 | [18 empty] | 9206745.0762
|  |  | 18071.38 | [23 empty] | CASH - DEVENGADO - | [18 empty] | Q1: Compromisos
17000
|  |  | 13.68% |  | 0.1368 | [9 empty] | 3000 | [25 empty] | 4944596.8131
[6 empty] | #N/A | 0.17226 | [7 empty] | 2.414% | [30 empty] | Q3: 57974.9
#N/A
442499.11
|  |  |  | 448997.11 | [41 empty] | Q3: 21489434.76
|  |  |  | -6498 | [41 empty] | Q4: ojo con el contrato de karla hay que ver si se reversó aquí interno | 11.54
22503
[56 empty] | 0.12 | 0.1
[55 empty] | 4140 | 496.8 | 414 | 5050.8
[55 empty] | 320 | 38.4 | 32 | 390.4
5441.2
Note on C4: Josue Andreé Ricart Vásquez: FHI
Note on C6: Josue Andreé Ricart Vásquez: Universidades Programas de Formación
Note on C11: Josue Andreé Ricart Vásquez: Firma Consultora para la Revisión de dos carreras y creación de dos nuevas ENCA
Note on C20: Josue Andreé Ricart Vásquez: FHI
Note on C24: Josue Andreé Ricart Vásquez: PAGOS DICIEMBRE Y ENERO
Note on C25: Josue Andreé Ricart Vásquez: LAS DATABASE YA FUERON PAGADAS
Note on C26: pagado
Note on C28: Josue Andreé Ricart Vásquez: Lilian Merlo contrato 2018
Note on C30: Josue Andreé Ricart Vásquez: CONTRATACIONES 2018 Y PAGO DE FEBRERO 2018
Note on C40: Josue Andreé Ricart Vásquez: esta en fase de tdr
Note on C41: investigadores de aduanas
Note on C42: Josue Andreé Ricart Vásquez: ya fue pagado en su totalidad PU-MCC-002-2016
Note on C45: Josue Andreé Ricart Vásquez: MGO
Note on C46: UNIVERSIDAD INTERNACIONES
Note on C49: Josue Andreé Ricart Vásquez: Deloitte
Note on C50: UNIVERSIDAD INTERNACIONES
Note on C52: Probablemente Sergio Bravo
Note on C55: Josue Andreé Ricart Vásquez: ya están los terminos de referencia
Note on C62: Josue Andreé Ricart Vásquez: incluye pago de corporación abiansha por 1652.68
Note on C63: Josue Andreé Ricart Vásquez: Incluye pago de rustika
Note on C70: Experto en escala vertical
Note on C86: Josue Andreé Ricart Grupo Sega
Note on C87: Josue Andreé Ricart Vásquez: Tecnasa
Note on C88: Josue Andreé Ricart Vásquez: 01-2017
Note on C91: Josue Andreé Ricart Vásquez: Reparación Impresora
Note on C94: Josue Andreé Ricart Vásquez: poliycom phone
Note on C95: Josue Andreé Ricart Vásquez: compra de credenzas
Note on C96: Josue Andreé Ricart Vásquez: PU-MCC-SNC-001-2016
Note on C97: Josue Andreé Ricart Vásquez: 03-2017
Note on C99: Josue Andreé Ricart Vásquez: 01-2018
Note on D6: Josue Andreé Ricart Vásquez: Cambia de 3M a 4M ya ***** ADJUDICADO*** UPANA 1,185,760.00 INTERNACIONES 1,866,155.00 UNIVERSIDAD DEL VALLE 972,082.83
Note on D11: Josue Andreé Ricart Vásquez: actualizar a 1,200,000.00 actualizado
Note on D18: Josue Andreé Ricart Vásquez: solo 35,000 resto pasar a otra linea de los 90000 iniciales
Note on D19: Josue Andreé Ricart Vásquez: inicialmente tenía 90 oeri es necesario rebajar porque si no se desfinancia el componente
Note on D51: Josue Andreé Ricart Vásquez: Este monto surgió de una rebaja en el monto estimado de Metro Riel, ya que al momento de realizar la SD no se tenían monto suficiente para cubrir este compromiso.
Note on D55: Josue Andreé Ricart Vásquez: ES NECESARIO REBAJAR EL MONTO POR 75,000 DEBIDO A LA CAPACITACIÓN QUE TENDRAN CONGRESISTAS DE GUATEMALA EN EL REINO UNIDO, CASO CONTRARIO SE DESFINANCIA EL PROYECTO. ***De acuerdo a una nueva gestión se dividirá en dos fases Metro Riel. la primera se tiene un estimado de 900,000. y de la segunda desconozco el monto aun. según nueva información para el siguiente trimestre, estiman que el valor de la consultoría será de 1.3 millones (18 de febrero 2019)
Note on D64: Josue Andreé Ricart Vásquez: PARA LA ELABORACIÓN DEL Q13 CONSIGNAR VALOR PAGADO TOTAL DE 47118.49, PARA QUE AJUSTE CON MCDR DE ENERO
Note on D65: Josue Andreé Ricart Vásquez: original 45,000, se dejó de utilizar 6498.00 se reversó
Note on BA108: Josue Andreé Ricart Vásquez: ojo se debe quitar un usd 1.00 solo ejecuto 24999

## Error checks (hidden)
Column Number
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | -0.0011 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.a Education Project Implementation Contract | -0.0011 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.b Grants to Universities for Teacher Training (Diplomados) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2 Developing Technical and Vocational Education and Training (0400) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2.a TVET | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3 Strengthening Institutional and Planning Capacity (0043) | 0.0079336 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.a Education Project Implementation Contract | 0.0079336 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.b Education Project Coordination team* | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Education | 0.0068336 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2. Resource Mobilization Project (REV RFRM) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1 Improving Tax and Customs Administration (0443)** | -0.01 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1.a Tax and Customs | -0.01 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2 Strengthening Public-Private Partnership Capacity (0414) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.a Advisors | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.b Feasiblity Studies/ Transaction Advisory Services | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Resource Mobilization | -0.01 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3. M&E (MON & Eval) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Monitoring and Evaluation (0016) | -1.1642e-10 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.a Student Assessment | 56.05 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.b Teacher Evaluations | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.c Voc Ed Tracer Studies | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1 d Other | -56.05 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - M&E | -1.1642e-10 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4. Program Admin (PGM ADMIN) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Program Administration (0017) | -0.0006 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.a Staff Compensation* | -40.86 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.b Travel* | 1078.06 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.c Audit | -0.0006 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.d Other | -1037.2 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Program Admin | -0.0006 | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL MCA-Managed Threshold Funds

## Historico (hidden)
|  |  | 23584570 |  | Percent of disbursements by quarter | [14 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# |  | Contract name | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  | Contract name |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 1.1.a Education Project Implementation Contract | Exito Escolar 1.1 | 8500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 255000 | 425000 | 425000 | 425000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 0 | 0 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | Pedagogical Resource centers | 200000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Diplomado Training | 3000000 | q6 | 2018-01-01: 12.5%; 2018-04-01: 12.5%; 2018-07-01: 12.5%; 2018-10-01: 12.5%; 2019-01-01: 12.5%; 2019-04-01: 12.5%; 2019-07-01: 12.5%; 2019-10-01: 12.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET place holder | 4000000 | q5 |  |  |  |  | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 100% | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 200000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract | Exito Escolar 1.3 | 2500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit | 140000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit (option 1) | 140000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 4000 | q3 | 2017-01-01: 100% | 100% | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants | 100000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | [18 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training | 150000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training option | 150000 | q6 | 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach | 73500 | q3 | 2017-01-01: 16.67%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 8.333% | 100% | 0 | 0 | 12250 | 18375 | 18375 | 18375 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 1 | 147000 | q6 | 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 2 | 147000 | q8 | 2018-10-01: 16.67%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) | 61250 | q2 | 2016-10-01: 20%; 2017-01-01: 60%; 2017-04-01: 20% | 100% | 0 | 12250 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Feasiblity Study | 500000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Transaction Advisor | 200000 | q3 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Feasiblity Study | 350000 | [16 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Transaction Advisor | 200000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Feasiblity Study | 350000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 87500 | 87500 | 87500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Transaction Advisor | 50000 | q5 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 500000 | q12 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 3 validadores para Pruebas de Educación de Nivel Medio | 7200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 2160 | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 6 redactores para Pruebas de Educación de Nivel Medio. | 19200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 5760 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 1 curriculista para Pruebas de Educación de Nivel Medio. | 8000 | q3 | 2017-01-01: 50%; 2017-04-01: 50% | 100% | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. | 72000 | q3 |  |  | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% |  | 100% | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 100000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.d | 3.1 d Other | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
4.1.c | 4.1.c Audit | Audit | 90000 | q5 | 2018-01-01: 16.67%; 2018-04-01: 16.67%; 2019-01-01: 16.67%; 2019-04-01: 16.67%; 2020-01-01: 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 11500 | q2 | 2016-10-01: 67%; 2017-01-01: 33% | 100% | 0 | 7705 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [35 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 1.3.b Education Project Coordination team* | Director de Proyecto de Educación | 121400 | q2 |  | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 121400 | 0 | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 31400 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 18000 | 0 | 0
1.3.b | 1.3.b Education Project Coordination team* | Asistente de Proyecto de Educación | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador MCC-THP | 181000 | q1 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 181000 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 49000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asistente Administrativo Bilingüe | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista de Monitoreo y Evaluación | 147000 | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147000 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 21000 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador Administrativo Financiero (Especialista financiero) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en Adquisiciones MCC (Especialista en adquisiciones) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista Economista | 72000 | q4 |  |  |  | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 |  |  |  |  | 72000
1.2.a | 1.2.a TVET | FxT Coordinator | 144000 | q4 |  |  | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [50 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 20000 |  |  | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 19999.82 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 4.1.b Travel* | Travel | 35000 |  |  | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
| Total Comprometido a la fecha |  | 23584570
1.1.a | 1.1.a Education Project Implementation Contract |  | 8700000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 3000000
1.2.a | 1.2.a TVET |  | 4144000
1.3.a | 1.3.a Education Project Implementation Contract |  | 2500000
1.3.b | 1.3.b Education Project Coordination team* |  | 178400
| Education Project Total |  | 18522400 | 19346000 | 823600
2.1.a | 2.1.a Tax and Customs |  | 384000
| Tax and Customs |  | 384000 | 800000 | 416000
2.2.a | 2.2.a Advisors |  | 728750
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 1650000
| PPPs |  | 2378750 | 3560000 | 1181250
3.1.a | 3.1.a Student Assessment |  | 706400
3.1.b | 3.1.b Teacher Evaluations |  | 300000
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 300000
3.1.d | 3.1 d Other |  | 200000
| M&E |  | 1506400 | 1431000 | -75400
4.1.a | 4.1.a Staff Compensation* |  | 636520
4.1.b | 4.1.b Travel* |  | 35000
4.1.c | 4.1.c Audit |  | 90000
4.1.d | 4.1.d Other |  | 31500
| Program Admin |  | 793020 | 1060500 | 267480