## DFP-Com
Detailed Financial Plan - Commitments
| Country: |  | Guatemala
| Accountable Entity: |  | PRONACOM
| Grant Number: |  | TR14GTM15001
| Date Submitted: |  | 2017-11-24
| Quarter # |  | 9
| Forecasted Commitments for -> | Cumulative | Current Period | Next Period | [10 empty] | TOTAL | TOTAL | Variance
|  | Actual Cumulative Commitments at Beginning of Current Period | Projected Commitments during Current Period | Grant Quarter #9 |  |  | Grant Quarter #9 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Commitments As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)* | Projections vs. Approved Plan Under / (Over) Budget Difference
| Date/Month/Quarter -> | Mar '18 | Apr '18 Jun '18 | Jul´18 | Aug`18 | Sep´18 | Jul '18 Sep '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20
| Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 | 1.1 Improving the Quality of Education (0277) | 7593016.09 | 0 | 4002000 | 2000 | 2000 | 4029997.83 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 12023013.92 | 12000000 | -23013.92
1.1.a | 1.1.a Education Project Implementation Contract | 7593016.09 | 0 | 0 |  | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 7993016.09 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | 0 | 0 | 4000000 |  |  | 4023997.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023997.83 | 0
1.1.c | 1.1.c Other | 0 | 0 | 2000 | 2000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0
1.2 | 1.2 Developing Technical and Vocational Education and Training (0400) | 2364509.34 | 35320.93 | 1200000 | 94000 | 2000 | 1296000 | 400000 | 0 | 22253 | 0 | 0 | 0 | 0 | 4118083.27 | 4300000 | 181916.73
1.2.a | 1.2.a TVET | 2364509.34 | 35320.93 | 1200000 | 94000 | 2000 | 1296000 | 400000 | 0 | 22253 | 0 | 0 | 0 | 0 | 4118083.27 | 0
1.3 | 1.3 Strengthening Institutional and Planning Capacity (0043) | 2885879.75 | 198.71 | 0 | 0 | 0 | 0 | 24000 | 42000 | 0 | 0 | 14320.16 | 17640.88 | 0 | 2984039.5 | 3000000 | 15960.5
1.3.a | 1.3.a Education Project Implementation Contract | 2772876.18 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2772876.18
1.3.b | 1.3.b Education Project Coordination team* | 112393.2 | 0 | 0 | 0 |  | 0 | 24000 | 42000 | 0 | 0 | 14320.16 | 17640.88 | 0 | 210354.24
1.3.c | 1.3.c Other | 610.37 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809.08
TOTA | TOTAL - Education | 12843405.18 | 35519.64 | 5202000 | 96000 | 4000 | 5325997.83 | 824000 | 42000 | 22253 | 0 | 14320.16 | 17640.88 | 0 | 19125136.69 | 19300000 | 174863.31
2. R | 2. Resource Mobilization Project (REV RFRM)
2.1 | 2.1 Improving Tax and Customs Administration (0443)** | 317258.46 | 16330.63 | 0 | 2000 | 0 | 2000 | 442000 | 0 | 0 | 0 | 0 | 0 | 0 | 777589.09 | 800000 | 22410.91
2.1.a | 2.1.a Tax and Customs | 317258.46 | 16330.63 |  | 2000 | 0 | 2000 | 442000 | 0 | 0 | 0 | 0 | 0 | 0 | 777589.09
2.2 | 2.2 Strengthening Public-Private Partnership Capacity (0414) | 1623472.71 | 0 | 0 | 75000 | 147000 | 222000 | 973500 | 0 | 0 | 0 | 770000 | 0 | 0 | 3588972.71 | 3600000 | 11027.29
2.2.a | 2.2.a Advisors | 587282.07 | 0 | 0 | 0 | 147000 | 147000 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 807782.07
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | 1030229 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 770000 | 0 | 0 | 2700229
2.2.c | 2.2.c Other | 5961.64 | 0 | 0 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80961.64
TOTA | TOTAL - Resource Mobilization | 1940731.17 | 16330.63 | 0 | 77000 | 147000 | 224000 | 1415500 | 0 | 0 | 0 | 770000 | 0 | 0 | 4366561.8 | 4400000 | 33438.2
3. M | 3. M&E (MON & Eval)
M | Monitoring and Evaluation (0016) | 209980.37 | 74370.4 | 36000 | 3000 | 4000 | 38000 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 482350.77 | 1700000 | 1217649.23
3.1.a | 3.1.a Student Assessment | 195000 | 73987.31 | 33000 |  |  | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296987.31
3.1.b | 3.1.b Teacher Evaluations | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 160000
3.1.d | 3.1 d Other | 14980.37 | 383.09 | 3000 | 3000 | 4000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25363.46
| TOTAL - M&E | 209980.37 | 74370.4 | 36000 | 3000 | 4000 | 38000 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 482350.77 | 1700000 | 1217649.23
4. Program Admin (PGM ADMIN)
| Program Administration (0017) | 329165.52 | 189953.34 | 50000 | 24000 | 5000 | 84991 | 29300 | 31800 | 75609 | 27553.66 | 19344.36 | 13992.84 | 2222.82 | 803932.54 | 797500 | -6432.54
4.1.a | 4.1.a Staff Compensation* | 292856.61 | 56616 | 50000 | 24000 | 0 | 79991 | 28800 | 28800 | 69609 | 22848.31 | 16344.36 | 10992.84 | 894.92 | 607753.04
4.1.b | 4.1.b Travel* | 6912.46 | 13337.34 |  |  | 5000 | 5000 | 500 | 3000 | 1000 | 2705.35 | 1000 | 1000 | 0 | 34455.15
4.1.c | 4.1.c Audit | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
4.1.d | 4.1.d Other | 29396.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2000 | 2000 | 2000 | 1327.9 | 41724.35
| TOTAL - Program Admin | 329165.52 | 189953.34 | 50000 | 24000 | 5000 | 84991 | 29300 | 31800 | 75609 | 27553.66 | 19344.36 | 13992.84 | 2222.82 | 803932.54 | 797500 | -6432.54
| TOTAL MCA-Managed Threshold Funds | 15323282.24 | 316174.01 | 5288000 | 200000 | 160000 | 5672988.83 | 2268800 | 73800 | 97862 | 27553.66 | 803664.52 | 191633.72 | 2222.82 | 24777981.8 | 26197500 | 1419518.2
* This activity has MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.
78000

## DFP-CASH
Detailed Financial Plan - Cash
Country: |  | Guatemala
Accountable Entity: |  | PRONACOM
Grant Number: |  | TR14GTM15001
Date Submitted: |  | 2018-06-22
Quarter # |  | 9
Forecasted Cash for -> | Cumulative | Current Period | Next Period | [10 empty] | TOTAL | TOTAL | Variance
| Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period | Grant Quarter #9 |  |  | Grant Quarter #9 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Cash Disbursements As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)** | Projections vs. Approved Plan Under / (Over) Budget Difference
Date/Month/Quarter -> | Mar '18 | Apr '18 Jun '18 | Jul´18 | Aug`18 | Sep´18 | Jul '18 Sep '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Sep '19 | Oct '19 Dec '19 | Jan '20 Mar '20 | Apr '20 Jun '20
Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | 1373480.72 | 544209.34 | 520294.61 | 2000 | 502000 | 1027294.3387 | 1654526.9179 | 1228612.1879 | 1280441.6492 | 1228612.1879 | 1731611.9166 | 1954224.647 | 0 | 12023013.9052 | 12000000 | -23013.9052
1.1.a Education Project Implementation Contract | 1373480.72 | 544209.34 | 518294.61 | 0 | 0 | 518294.61 | 1151527.1891 | 725612.4591 | 777441.9205 | 725612.4591 | 725612.4591 | 1451224.9182 | 0 | 7993016.0752 | 0
1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 0 | 0 | 0 | 500000 | 502999.7288 | 502999.7288 | 502999.7288 | 502999.7288 | 502999.7288 | 1005999.4575 | 502999.7288 | 0 | 4023997.83 | 0
1.1.c Other |  | 0 | 2000 | 2000 | 2000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0
1.2 Developing Technical and Vocational Education and Training (0400) | 25130 | 195294.9768 | 28228.4 | 144703.74 | 59023.48 | 231955.62 | 743621.0904 | 553735.8892 | 623621.0944 | 476350.684 | 620721.0944 | 647652.8208 | 0 | 4118083.27 | 4300000 | 181916.73
1.2.a TVET | 25130 | 195294.9768 | 28228.4 | 144703.74 | 59023.48 | 231955.62 | 743621.0904 | 553735.8892 | 623621.0944 | 476350.684 | 620721.0944 | 647652.8208 | 0 | 4118083.27 | 0
1.3 Strengthening Institutional and Planning Capacity (0043) | 422575.41 | 225614.34 | 5865.87 | 213183.71 | 5865.9 | 224915.48 | 1312236.5379 | 16500 | 249732.5759 | 16500 | 16500 | 482965.1609 | 16500 | 2984039.5048 | 3000000 | 15960.4952
1.3.a Education Project Implementation Contract | 366755.66 | 203368.4 |  | 207317.84 |  | 207317.84 | 1295736.5379 | 0 | 233232.5759 | 0 | 0 | 466465.1609 | 0 | 2772876.1748 | 0
1.3.b Education Project Coordination team* | 55795.76 | 21460.84 | 5865.87 | 5865.87 | 5865.9 | 17597.64 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 210354.24 | 0
1.3.c Other | 23.99 | 785.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809.09 | 0
TOTAL - Education | 1821186.13 | 965118.6568 | 554388.88 | 359887.45 | 566889.38 | 1484165.4387 | 3710384.5462 | 1798848.0771 | 2153795.3195 | 1721462.8719 | 2368833.011 | 3084842.6287 | 16500 | 19125136.6799 | 19300000 | 174863.3201
2. Resource Mobilization Project (REV RFRM)
2.1 Improving Tax and Customs Administration (0443)** | 162713.12 | 49835.08 | 15716.22 | 17716.22 | 15716.22 | 49148.6738 | 139648.6738 | 137243.5381 | 110500 | 110500 | 18000 | 0 | 0 | 777589.0857 | 800000 | 22410.9143
2.1.a Tax and Customs | 162713.12 | 49835.08 | 15716.22 | 17716.22 | 15716.22 | 49148.6738 | 139648.6738 | 137243.5381 | 110500 | 110500 | 18000 | 0 | 0 | 777589.0857
2.2 Strengthening Public-Private Partnership Capacity (0414) | 463774.28 | 66525.34 | 515135.5 | 218295.8 | 87250 | 820681.3 | 767274.8 | 523500 | 36750 | 76750 | 448716.95 | 385000 | 0 | 3588972.67 | 3600000 | 11027.33
2.2.a Advisors | 332362.4 | 66525.34 |  | 12250 | 12250 | 24500 | 111250 | 73500 | 36750 | 76750 | 63716.95 | 0 | 0 | 785354.69
2.2.b Feasiblity Studies/ Transaction Advisory Services | 125450.24 | 0 | 515135.5 | 206045.8 |  | 721181.3 | 656024.8 | 450000 | 0 | 0 | 385000 | 385000 | 0 | 2722656.34
2.2.c Other | 5961.64 | 0 |  |  | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80961.64
TOTAL - Resource Mobilization | 626487.4 | 116360.42 | 530851.72 | 236012.02 | 102966.22 | 869829.9738 | 906923.4738 | 660743.5381 | 147250 | 187250 | 466716.95 | 385000 | 0 | 4366561.7557 | 4400000 | 33438.2443
3. M&E (MON & Eval)
Monitoring and Evaluation (0016) | 86980.4 | 49499.4 | 125987.31 | 16000 | 17000 | 153987.31 | 21883.69 | 6000 | 4000 | 0 | 0 | 160000 | 0 | 482350.8 | 1700000 | 1217649.2
3.1.a Student Assessment | 72000 | 49116.31 | 122987.31 | 13000 | 13000 | 143987.31 | 21883.69 | 6000 | 4000 | 0 | 0 | 0 | 0 | 296987.31
3.1.b Teacher Evaluations |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c Voc Ed Tracer Studies |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 160000
3.1 d Other | 14980.4 | 383.09 | 3000 | 3000 | 4000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25363.49
TOTAL - M&E | 86980.4 | 49499.4 | 125987.31 | 16000 | 17000 | 153987.31 | 21883.69 | 6000 | 4000 | 0 | 0 | 160000 | 0 | 482350.8 | 1700000 | 1217649.2
4. Program Admin (PGM ADMIN)
Program Administration (0017) | 239243.71 | 55474.46 | 42380 | 16880 | 27003 | 86263 | 52068.42 | 74300 | 77300 | 44005.35 | 62300 | 77300.0004 | 35677.6 | 803932.5404 | 797500 | -6432.5404
4.1.a Staff Compensation* | 217199.81 | 28803.24 | 22200 | 16700 | 16699.71 | 55599.71 | 51300.58 | 51300 | 51300 | 39300 | 39300 | 39300 | 34349.7 | 607753.04
4.1.b Travel* | 3794.65 | 15956.99 | 5000 | 0 | 0 | 5000 | 500 | 3000 | 1000 | 2705.35 | 1000 | 1000 | 0 | 33956.99
4.1.c Audit | 0 | 10000 | 15000 | 0 | 0 | 15000 | 0 | 20000 | 20000 | 0 | 20000 | 35000.0004 | 0 | 120000.0004
4.1.d Other | 18249.25 | 714.23 | 180 | 180 | 10303.29 | 10663.29 | 267.84 | 0 | 5000 | 2000 | 2000 | 2000 | 1327.9 | 42222.51
TOTAL - Program Admin | 239243.71 | 55474.46 | 42380 | 16880 | 27003 | 86263 | 52068.42 | 74300 | 77300 | 44005.35 | 62300 | 77300.0004 | 35677.6 | 803932.5404 | 797500 | -6432.5404
TOTAL MCA-Managed Threshold Funds | 2773897.64 | 1186452.9368 | 1253607.91 | 628779.47 | 713858.6 | 2594245.7225 | 4691260.13 | 2539891.6152 | 2382345.3195 | 1952718.2219 | 2897849.961 | 3707142.6291 | 52177.6 | 24777981.776 | 26197500 | 1419518.224
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.

## QFR - A
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2018-06-22
Schedule A. Multi-Year Financial Plan Adjustment Request Form
Disbursement Period:01-jul-18 to 30-sep-18
Amounts Expressed In US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Current Approved Multi-Year Financial Plan | Proposed Adjustments (Display all #'s as positive) |  | Proposed Adjusted Multi-Year Financial Plan
Project (code) |  | (from Schedule B, Final Column) | Increase (+) | Decrease (-) | (2+3-4)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | 19300000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 12000000 |  |  | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | 4300000 |  |  | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 3000000 |  |  | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 4400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 |  |  | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | 3600000 |  |  | 3600000
3. M&E (MON & EVAL) | 1700000 | 1700000 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 1700000 |  |  | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 797500 | 0 | 0 | 797500
Program Administration (0017) | 800000 | 797500 |  | 0 | 797500
Grand Total | 26200000 | 26197500 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 1800000 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 | 1800000 |  |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 2500 | 0 | 0 | 2500
Program Administration (0017) | 0 | 2500 | 0 |  | 2500
Grand Total | 1800000 | 1802500 | 0 | 0 | 1802500

## Hoja1
techos presupuestarios

## QFR - B
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2018-06-22
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-jul-18 to 30-sep-18
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (Q6 - 10/11/2017) | Adjustment Reported/ Approved (insert date) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 0 | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | 3600000
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | 0 | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 0 | -2500 | 0 | 797500
Program Administration (0017) | 800000 | 0 | -2500 | 0 | 797500
Grand Total | 26200000 | 0 | -2500 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  | 0 |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 0 | 2500 | 0 | 2500
Program Administration (0017) |  |  | 2500 |  | 2500
Grand Total | 1800000 | 0 | 0 | 0 | 1802500

## THP DR
DISBURSEMENT REQUEST
THRESHOLD PROGRAM GRANT AGREEMENT
Country | Guatemala
Projects | Threshold Program / Program Administration and Monitoring and Evaluation
Threshold Program Grant Agreement Date/ Entry into Force Date | April 8, 2015/May 16, 2016
Threshold Program Number | TR14GTM15001
Accountable Entity | PRONACOM
Fiscal Agent | MCC (Acting Fiscal Agent)
Request Date | 2018-06-22
Disbursement Period Beginning Date | 2018-07-01
Disbursement Period Ending Date | 2018-09-30
Disbursement Number | 9
Currency (Expressed in USD) | US Dollars
Exchange Rate used to calculate U.S. Dollar equivalent of any local currency balance for purposes of this MCC Disbursement Request
A. Disbursement Request: The undersigned hereby requests the Millennium Challenge Corporation to disburse funds under the Threshold Grant Agreement, dated as of August 28,2013 as follows:
1. Forecasted Cash Disbursement Requirements (from DFP Cash Column) | 2596245.9889
2. Interest to be Returned to the USG for Next Period (Interest Sum, Line 7)
3. Working Capital (FOR MCC USE ONLY)
4. Cash Balance at the End of the Current Period (Cash Req, Line 7) | 0
5. Disbursement Request Amount (Lines 1+2-4) | 2596245.9889
6. Amount Requested in Words | two million five hundred ninety-six thousand two hundred forty-five dollars and ninety-nine cents
C. Compliance: the undersigned confirms that the MCC Disbursement requested herby is in accordance with the terms and conditions set forth in the Threshold Program Agreement, including the limitations on the use or treatment of MCC Funding set out in Section 2.4.
D. Authorization: the undersigned acknowledges that funds disbursed in accordance with this request will be either made (i) directly to third-party vendors for goods, works and services received by the accountable entity upon presentation of valid invoices utilizing MCC's Common Payment System, (ii) to the Permitted Account, or (iii) to the Petty Cash Account.
E. Certificates: Attached hereto are the certificates required under Section 5.2 and 5.3 of the Threshold Program Agreement.
F. Definitions: Capitalized terms used herein shall have the meanings assigned to such terms in the Threshold Program Agreement by and between the Government of Guatemala and the United States, acting through the Millennium Challenge Corporation, dated April 8, 2015, and entered into force on May 15, 2016.
Signed by the Executive Director of PRONACOM
By: _______________________________________________________________
Name: Francisca de Jesús Cárdenas Morán
Date: Jun 22, 2018
Certified by the Minister of Economy
By: _______________________________________________________________
Name: Acisclo Valladares Urruela
Date: _____________________________________________________________
By: _______________________________________________________________
Name:
Date:

## Contract level (hidden)
| 24785928.71 |  |  | Percent of disbursements by quarter | [15 empty] | Total |  |  | Cash by quarter | [15 empty] | Committments by quarter
Act# | Value |  |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | Apr-20 |  |  |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | check Cash=comm
Act# |  | Sign quarter |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 |  |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | 16 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16
1.1.a | 7593016.09 | q4 | va bien |  |  |  | 0% | 9.556% | 8.191% | 7.509% | 0% | 6.826% | 9.898% | 9.556% | 10.24% | 9.556% | 9.556% | 19.11% |  | 100% |  |  | 0 | 0 | 0 | 0 | 725612.4591 | 621953.5364 | 570124.075 | 0 | 518294.61 | 751527.1891 | 725612.4591 | 777441.9205 | 725612.4591 | 725612.4591 | 1451224.9182 | 0 | 0 | 0 | 0 | 7593016.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0043345
1.1.a | 200000 | q10 | Solicitar en este trimsetre que viene si se queda | [5 empty] | 0% | 0% | 0% | 0% | 100% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 200000 | q10 | lo vamos a quitar y trasladar (quitar 200) | [6 empty] | 0% | 0% | 0% | 100% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 4023997.83 | q9 | [7 empty] | 0% | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 25% | 12.5% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502999.7288 | 502999.7288 | 502999.7288 | 502999.7288 | 502999.7288 | 1005999.4575 | 502999.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023997.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.c | 6000 | q9 | preguntar si podemos seguir cargando aquí los gastos de viaje |  |  |  |  | 0% | 0% | 0% | 0% | 100% | [7 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 2329506.84 | q6 | ok | [5 empty] | 0% | 0% | 8% | 9% | 16% | 13% | 16% | 10% | 16% | 12% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186360.5468 | 209655.62 | 372721.0904 | 302835.8892 | 372721.0944 | 232950.684 | 372721.0944 | 279540.8208 | 0 | 0 | 0 | 0 | 0 | 0 | 2329506.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 90000 | q9 | [6 empty] | 0% | 0% | 0% | 8.333% | 25% | 25% | 25% | 16.67% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 22500 | 22500 | 22500 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 400000 | q10 | Se volverá 2 lineas de 200 mil cada una para intecap e iga | [8 empty] | 0% | 25% | 25% | 25% | 25% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1200000 | q9 | [6 empty] | 0% | 0% | 0% | 0% | 20% | 10% | 10% | 10% | 20% | 30% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 120000 | 120000 | 120000 | 240000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 2772876.18 | q4 |  |  |  |  | 0% |  | 7.477% | 5.607% | 7.477% | 7.477% | 46.73% | 0% | 8.411% | 0% | 0% | 16.82% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 207317.8452 | 155488.38 | 207317.84 | 207317.84 | 1295736.5379 | 0 | 233232.5759 | 0 | 0 | 466465.1609 | 0 | 0 | 0 | 0 | 2772876.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 23.98 | q7 | [5 empty] | 0% | 0% | 100% | 0% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 56.93 | q7 | [5 empty] | 0% | 0% | 0% | 100% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 36998.88 | q3 |  |  |  |  | 24.33% | 26.2% | 23.7% | 25.78% | 0% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 9000 | 9691.92 | 8768.88 | 9538.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36998.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 43134 | q7 | [7 empty] | 0% | 23.4% | 25.85% | 25.85% | 24.9% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10094.56 | 11148.48 | 11148.48 | 10742.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 18759 | q7 | [7 empty] | 17.23% | 24.21% | 25.85% | 25.85% | 6.872% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 4540.64 | 4848.48 | 4848.48 | 1289.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 72000 | q10 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 100000 | q10 | [7 empty] | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 40000 | q10 | [6 empty] | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 4000 | q3 |  |  |  | 100% | [13 empty] | 100% |  |  | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 1800 | q7 |  |  |  | 0% |  |  |  | 0% | 100% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 99851.16 | q3 |  |  |  | 0% | 33.05% | 27.12% | 26.27% | 13.56% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 33000 | 27079.68 | 26231.64 | 13539.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99851.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 118579.5 | q7 | [7 empty] | 7.932% | 27.12% | 26.27% | 26.27% | 12.41% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9405.28 | 32158.8143 | 31151.7138 | 31151.7138 | 14711.9781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118579.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 230000 | q10 | [6 empty] | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57500 | 57500 | 57500 | 57500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 7725.48 | q7 | [6 empty] | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 1241.07 | q8 | [6 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2000 | q9 | [6 empty] | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 1500 | q4 |  |  |  |  | 100% |  | 0% | [10 empty] | 100% |  |  | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 200000 | q4 | [5 empty] | 0% | 20.98% | 2.737% | 5.55% | 0% | 25% |  |  | 20% | 25.73% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 41958.49 | 5475 | 11099.56 | 0 | 50000 | 0 | 0 | 40000 | 51466.95 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 51406.27 | q5 | [5 empty] | 37.5% | 50% | 12.5% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 19277.4513 | 25703.255 | 6425.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51406.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21625
2.2.a | 6425.8 | q7 | [5 empty] | 0% | 0% | 0% | 100% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6425.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 121200 | q3 |  |  |  |  | 33.33% | 16.67% | 33.33% | 16.67% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 40399.9996 | 20199.9992 | 40399.9996 | 20200.0016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 147000 | q5 | [5 empty] | 8.333% | 16.67% | 25% | 33.33% | 16.67% | 0% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 12250 | 24500 | 36750 | 49000 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 147000 | q9 | [10 empty] | 16.67% | 25% | 25% | 25% | 8.333% |  |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 61250 | q2 |  |  | 0% | 40% | 60% | 0% | [11 empty] | 100% |  |  | 0 | 0 | 24500 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 73500 | q10 | [5 empty] | 0% | 0% |  |  |  | 50% | 50% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 1030229 | q6 | [6 empty] | 0% | 10% | 0% | 70% | 20% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 103022.9 | 0 | 721181.3 | 206024.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 900000 | q10 | [6 empty] | 0% | 0% | 0% | 0% | 50% | 50% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 770000 | q14 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 50% | 50% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770000 | 0 | 0 | 0
2.2.c | 75000 | q9 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 5000 | q4 |  |  |  |  | 100% | [12 empty] | 100% |  |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c | 961.64 | q5 | [5 empty] | 100% | [11 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 13200 | q5 | [6 empty] | 100% | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 50000 | q7 | [7 empty] | 0% | 86.23% | 0% | 13.77% | 0% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43116.31 | 0 | 6883.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 45000 | q7 | [7 empty] | 0% | 0% | 80% | 20% | 0% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 66139.19 | q8 | [7 empty] | 0% | 0% | 100% | 0% | 0% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66139.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66139.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 7848.12 | q8 | [7 empty] | 0% | 0% | 100% | 0% | 0% | [5 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 8100 | q4 |  |  |  |  | 0% | 41.67% | 58.33% | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 3375 | 4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6974e-08
3.1.a | 18700 | q4 |  |  |  |  | 0% | 36.36% | 63.64% | [10 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 6800 | 11900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.8699e-08
3.1.a | 8000 | q3 |  |  |  |  | 50% | 50% | [11 empty] | 100% |  |  | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 52000 | q3 |  |  |  |  | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 11.54% | 7.692% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 28000 | q9 | [7 empty] | 0% | 0% | 100% | 0% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 160000 | q15 | [12 empty] | 0% | 0% | 0% | 100% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0
3.1.d | 640.16 | q5 | [6 empty] | 100% | [5 empty] | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 13864.72 | q6 | [6 empty] | 100% | [5 empty] | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 475.49 | q7 | [7 empty] | 100% |  |  |  |  | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 203.63 | q8 | [7 empty] | 0% | 100% |  |  |  | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 179.46 | q8 | [7 empty] | 0% | 100% |  |  |  | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | 10000 | q9 | [7 empty] | 0% | 0% | 100% |  |  | 0% | 0% | 0% | 0% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.c | 120000 | q8 | [6 empty] | 0% | 0% | 8.333% | 12.5% |  | 16.67% | 16.67% |  | 16.67% | 29.17% |  | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999.9996 | 15000 | 0 | 20000 | 20000 | 0 | 20000 | 35000.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 7666.96 | q2 |  |  | 100% | 0% | 0% | [12 empty] | 100% |  |  | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1124.38 | q3 |  |  | 0% | 0% | 100% | [12 empty] | 100% |  |  | 0 | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1630 | q5 |  |  | 0% | 0% | 0% | 100% | [11 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 739.99 | q6 |  |  | 0% | 0% | 0% | 0 | 100% | 0% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 505.16 | q4 |  |  | 0% | 0% | 100% | 0% | 0% | 0% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1232.14 | q6 |  |  | 0% | 0% | 0% | 0% | 100% | 0% | [9 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1071.43 | q2 |  |  | 25% | 25% | 25% | 25% | 0% | [10 empty] | 100% |  |  | 0 | 267.8575 | 267.8575 | 267.8575 | 267.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 982.1 | q3 |  |  | 0% | 18.18% | 27.27% | 27.27% | 27.27% | [10 empty] | 100% |  |  | 0 | 0 | 178.5636 | 267.8455 | 267.8455 | 267.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1200 | q6 |  |  | 0% | 0% |  |  | 22.32% | 22.32% | 22.32% | 33.04% | [7 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 267.85 | 267.85 | 267.85 | 396.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 1071.36 | q7 |  |  | 0% | 0% |  |  |  | 25% | 25% | 25% | 25% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 267.84 | 267.84 | 267.84 | 267.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Total | [34 empty] | 0
Salary Type Expenses | [38 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | 0
1.3.c | 529.46 | q7 | [5 empty] | 0% | 0% | 0% | 100% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | 198.71 | q8 | [5 empty] | 0% | 0% | 0% | 100% | [8 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.b | 147034.08 | q2 |  |  | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11251.24 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147034.08 |  |  | 0 | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11251.24 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 43635.2 | 0 | 0 | 0 | 0 | 43758 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 17640.88 | 0 | 0
1.3.b | 63320.16 | q6 | [5 empty] | 0 | 2358.88 | 6256.16 | 6358.72 | 6346.4 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 63320.16 |  |  | 0 | 0 | 0 |  | 0 | 2358.88 | 6256.16 | 6358.72 | 6346.4 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 24000 | 0 | 0 | 0 | 14320.16 | 0 | 0 | 0
4.1.b | 2619.65 | q7 |  |  | 0% | 0% |  |  |  | 0% | 100% | 0% | 0% | [6 empty] | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2619.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2619.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 99000 | q1 |  | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 14000 | 12000 | 12000 | 12000 | 0 | 0 | 0 |  | 99000 |  |  | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 14000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 75135.36 | q6 |  | 0 | 0 | 0 | 0 | 0 | 2706.88 | 7628.48 | 7505.44 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 6894.56 | 75135.36 |  |  | 0 | 0 | 0 | 0 | 0 | 2706.88 | 7628.48 | 7505.44 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 6894.56 | 0 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 16344.36 | 0 | 0 | 0
4.1.a | 15389.66 | q3 |  |  | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15389.66 |  |  | 0 | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14495 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a | 140389.87 | q2 |  |  | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 14000 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 7000 | 140389.87 |  |  | 0 | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 14000 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 7000 | 0 | 42000 | 0 | 7000 | 0 | 3440.43 | 3949.44 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0
4.1.a | 94645.92 | q2 |  |  | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7520.82 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 94645.92 |  |  | 0 | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7520.82 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 0 | 6160 | 0 | 29991 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 27609 | 0 | 0 | 0 | 894.92 | 0
4.1.a | 101969.44 | q2 |  |  | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7199.71 | 7200.29 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 101969.44 |  |  | 0 | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7199.71 | 7200.29 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 0 | 32185.6 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 28800 | 0 | 0 | 0 | 10992.84 | 0 | 0
4.1.a | 81222.79 | q4 |  |  |  |  | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6256.16 | 6000 | 7200.29 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 81222.79 |  |  | 0 | 0 | 0 | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6256.16 | 6000 | 7200.29 | 7200 | 7200 | 7200 | 7200 | 7200 | 6818.38 | 0 | 0 | 0 | 3384.48 | 24999 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 22848.31 | 0 | 0 | 0 | 0
4.1.d | 9999 | q3 | [6 empty] | 0 | 0 | 0 | 9999 | [7 empty] | 9999 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 318.43 | q8 | [6 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 884.24 | q8 | [6 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 6000 | q9 | [6 empty] | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 100658 | q4 |  |  |  |  | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 8800 | 8400 | 8400 | 8400 | 8400 | 8000 | 8112 | 8400 | 100658 |  |  | 0 | 0 | 0 | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 8800 | 8400 | 8400 | 8400 | 8400 | 8000 | 8112 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 22253 | 0 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [38 empty] | 0: 0
4.1.d | 15000 |  |  |  | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2000 | 2000 | 2000 | 1327.9 | 15000 |  |  | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2000 | 2000 | 2000 | 1327.9 | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2000 | 2000 | 2000 | 1327.9 | 0
4.1.b | 30000 |  |  |  | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 13337.34 | 5000 | 500 | 3000 | 1000 | 2705.35 | 1000 | 1000 | 0 | 31337.34 |  |  | 0 | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 13337.34 | 5000 | 500 | 3000 | 1000 | 2705.35 | 1000 | 1000 | 0 | 0 | 0 | 0 | 3518.51 | 0 | 276.14 | 0 | 13337.34 | 5000 | 500 | 3000 | 1000 | 2705.35 | 1000 | 1000 | 0 | 0
24785928.71
1.1.a | 7993016.09
1.1.b | 4023997.83
1.2.a | 4127367.51
1.3.a | 2772876.18
1.3.b | 210354.24
| 19127611.85 | 19300000 |  | 172388.15
2.1.a | 777589.09
| 777589.09 | 800000 |  | 22410.91
2.2.a | 807782.07
2.2.b | 2700229
| 3508011.07 | 3600000 |  | 91988.93
3.1.a | 296987.31
3.1.b | 0
3.1.c | 160000
3.1.d | 25363.46
| 482350.77 | 1700000 |  | 1217649.23
4.1.a | 607753.04
4.1.b | 32619.65
4.1.c | 120000
4.1.d | 42222.52
| 802595.21 | 797500 |  | -5095.21
| 98968173.4 | 26197500 |  | 1509342.01 | 24587.92 | 41876.8318 | 50463.8152 | 60088.8521 | 62773.2772 | 58779.6938 | 68281.8051 | 97008.0584 | 76707.9806 | 79203.9244 | 82202.5651 | 68907.6372 | 66801.9629 | 66914.696 | 60577.6 | 975176.62 | 0 | 0 | 10000 | 32521.4875 | 70821.4211 | 188272.4126 | 897497.5325 | 1112435.9317 | 1006736.9566 | 642949.3207 | 2594245.7225 | 4691260.13 | 2539891.6152 | 2382345.3195 | 1952718.2219 | 2897849.961 | 3707142.6291 | 52177.6 | 49000 | 194969.19 | 348650.52 | 10681160.68 | 239837.07 | 3435480.26 | 373899.09 | 317343.69 | 5672988.83 | 2268800 | 73800 | 97862 | 27553.66 | 803664.52 | 191633.72 | 2222.82 | 0.21192
[10 empty] | 41.67% | 8.333% | 80% | 1 | 20%
[15 empty] | 0% | 0.39252 | 85.98%
0.04
Note on C4: Josue Andreé Ricart Vásquez: FHI
Note on C7: Josue Andreé Ricart Vásquez: Universidades Programas de Formación
Note on C9: CAMBIA EL MONTO ADJUDICADO DE 2,800,000 A 2,400,000 GOPA 25/06/2018 Monto adjudicado 2329507.00 se realizaron ajustes a los entregables
Note on C13: Josue Andreé Ricart Vásquez: Firma Consultora para la Revisión de dos carreras y creación de dos nuevas ENCA
Note on C14: Josue Andreé Ricart Vásquez: FHI
Note on C19: Josue Andreé Ricart Vásquez: Lilian Merlo contrato 2018
Note on C20: Josue Andreé Ricart Vásquez: en fase inicial se pretendió adquirir sus servicios en el q6 pero sigue en fase de TDR´s por lo que se traslada al q7 borrar el ya no va a estar
Note on C21: Josue Andreé Ricart Vásquez: consultor en sistema de aduanas
Note on C22: Josue Andreé Ricart Vásquez: esta en fase de tdr
Note on C23: Josue Andreé Ricart Vásquez: LAS DATABASE YA FUERON PAGADAS
Note on C25: Josue Andreé Ricart Vásquez: PAGOS DICIEMBRE Y ENERO
Note on C26: Josue Andreé Ricart Vásquez: CONTRATACIONES 2018 Y PAGO DE FEBRERO 2018
Note on C27: investigadores de aduanas
Note on C31: pagado
Note on C33: UNIVERSIDAD INTERNACIONES
Note on C34: Josue Andreé Ricart Vásquez: Enmienda 1
Note on C37: Probablemente Sergio Bravo
Note on C38: Josue Andreé Ricart Vásquez: ya fue pagado en su totalidad PU-MCC-002-2016
Note on C39: probablemente un tercer contrato de sergio bravo
Note on C40: Josue Andreé Ricart Vásquez: Deloitte
Note on C41: Josue Andreé Ricart Vásquez: ya están los terminos de referencia
Note on C44: Josue Andreé Ricart Vásquez: MGO
Note on C45: Josue Andreé Ricart Vásquez: QUINTOS TRAVEL
Note on C55: Experto en escala vertical
Note on C64: Josue Andreé Ricart Grupo Sega
Note on C65: Josue Andreé Ricart Vásquez: Tecnasa
Note on C67: Josue Andreé Ricart Vásquez: poliycom phone
Note on C68: Josue Andreé Ricart Vásquez: Reparación Impresora
Note on C69: Josue Andreé Ricart Vásquez: compra de credenzas
Note on C70: Josue Andreé Ricart Vásquez: PU-MCC-SNC-001-2016
Note on C71: Josue Andreé Ricart Vásquez: 01-2017
Note on C72: Josue Andreé Ricart Vásquez: 03-2017
Note on C73: Josue Andreé Ricart Vásquez: 01-2018
Note on C80: julio
Note on D7: Josue Andreé Ricart Vásquez: Cambia de 3M a 4M ya ***** ADJUDICADO*** UPANA 1,185,760.00 INTERNACIONES 1,866,155.00 UNIVERSIDAD DEL VALLE 972,082.83
Note on D13: Josue Andreé Ricart Vásquez: actualizar a 1,200,000.00 actualizado
Note on D41: Josue Andreé Ricart Vásquez: ES NECESARIO REBAJAR EL MONTO POR 75,000 DEBIDO A LA CAPACITACIÓN QUE TENDRAN CONGRESISTAS DE GUATEMALA EN EL REINO UNIDO, CASO CONTRARIO SE DESFINANCIA EL PROYECTO. ***De acuerdo a una nueva gestión se dividirá en dos fases Metro Riel. la primera se tiene un estimado de 900,000. y de la segunda desconozco el monto aun.
Note on D43: Josue Andreé Ricart Vásquez: Este monto surgió de una rebaja en el monto estimado de Metro Riel, ya que al momento de realizar la SD no se tenían monto suficiente para cubrir este compromiso.
Note on E5: Josue Andreé Ricart Vásquez: Según Liseth es probable que se ejecute en abril se traslada al Q10 según solicitud

## Error checks (hidden)
Column Number | total
| com-cash |  | cash before Com | [7 empty] | cash before Com
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.a Education Project Implementation Contract | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.b Grants to Universities for Teacher Training (Diplomados) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2 Developing Technical and Vocational Education and Training (0400) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2.a TVET | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3 Strengthening Institutional and Planning Capacity (0043) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.a Education Project Implementation Contract | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.b Education Project Coordination team* | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | ok | ok | ok | error | error
1.3.c Other | error | ok | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error
TOTAL - Education | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2. Resource Mobilization Project (REV RFRM) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1 Improving Tax and Customs Administration (0443)** | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error
2.1.a Tax and Customs | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error
2.2 Strengthening Public-Private Partnership Capacity (0414) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | ok | error | error | error | error
2.2.a Advisors | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.b Feasiblity Studies/ Transaction Advisory Services | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error | error | error | error
2.2.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Resource Mobilization | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | ok | error | error | error | error
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3. M&E (MON & Eval) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Monitoring and Evaluation (0016) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error | error | error | error
3.1.a Student Assessment | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error | error | error | error
3.1.b Teacher Evaluations | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.c Voc Ed Tracer Studies | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1 d Other | error | ok | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error | error
TOTAL - M&E | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error | error | error | error
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4. Program Admin (PGM ADMIN) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Program Administration (0017) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.a Staff Compensation* | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.b Travel* | error | ok | error | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.c Audit | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.d Other | error | ok | ok | ok | error | error | error | error | error | error | error | error | error | error | error | error | error | error
TOTAL - Program Admin | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL MCA-Managed Threshold Funds

## Hoja2 (hidden)
Techos Presupuestarios
Educación

## Historico (hidden)
|  |  | 23584570 |  | Percent of disbursements by quarter | [14 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# |  | Contract name | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  | Contract name |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 1.1.a Education Project Implementation Contract | Exito Escolar 1.1 | 8500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 255000 | 425000 | 425000 | 425000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 0 | 0 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | Pedagogical Resource centers | 200000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Diplomado Training | 3000000 | q6 | 2018-01-01: 12.5%; 2018-04-01: 12.5%; 2018-07-01: 12.5%; 2018-10-01: 12.5%; 2019-01-01: 12.5%; 2019-04-01: 12.5%; 2019-07-01: 12.5%; 2019-10-01: 12.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET place holder | 4000000 | q5 |  |  |  |  | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 100% | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 200000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract | Exito Escolar 1.3 | 2500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit | 140000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit (option 1) | 140000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 4000 | q3 | 2017-01-01: 100% | 100% | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants | 100000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | [18 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training | 150000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training option | 150000 | q6 | 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach | 73500 | q3 | 2017-01-01: 16.67%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 8.333% | 100% | 0 | 0 | 12250 | 18375 | 18375 | 18375 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 1 | 147000 | q6 | 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 2 | 147000 | q8 | 2018-10-01: 16.67%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) | 61250 | q2 | 2016-10-01: 20%; 2017-01-01: 60%; 2017-04-01: 20% | 100% | 0 | 12250 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Feasiblity Study | 500000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Transaction Advisor | 200000 | q3 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Feasiblity Study | 350000 | [16 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Transaction Advisor | 200000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Feasiblity Study | 350000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 87500 | 87500 | 87500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Transaction Advisor | 50000 | q5 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 500000 | q12 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 3 validadores para Pruebas de Educación de Nivel Medio | 7200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 2160 | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 6 redactores para Pruebas de Educación de Nivel Medio. | 19200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 5760 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 1 curriculista para Pruebas de Educación de Nivel Medio. | 8000 | q3 | 2017-01-01: 50%; 2017-04-01: 50% | 100% | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. | 72000 | q3 |  |  | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% |  | 100% | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 100000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.d | 3.1 d Other | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
4.1.c | 4.1.c Audit | Audit | 90000 | q5 | 2018-01-01: 16.67%; 2018-04-01: 16.67%; 2019-01-01: 16.67%; 2019-04-01: 16.67%; 2020-01-01: 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 11500 | q2 | 2016-10-01: 67%; 2017-01-01: 33% | 100% | 0 | 7705 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [35 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 1.3.b Education Project Coordination team* | Director de Proyecto de Educación | 121400 | q2 |  | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 121400 | 0 | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 31400 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 18000 | 0 | 0
1.3.b | 1.3.b Education Project Coordination team* | Asistente de Proyecto de Educación | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador MCC-THP | 181000 | q1 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 181000 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 49000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asistente Administrativo Bilingüe | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista de Monitoreo y Evaluación | 147000 | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147000 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 21000 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador Administrativo Financiero (Especialista financiero) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en Adquisiciones MCC (Especialista en adquisiciones) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista Economista | 72000 | q4 |  |  |  | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 |  |  |  |  | 72000
1.2.a | 1.2.a TVET | FxT Coordinator | 144000 | q4 |  |  | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [50 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 20000 |  |  | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 19999.82 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 4.1.b Travel* | Travel | 35000 |  |  | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
| Total Comprometido a la fecha |  | 23584570
1.1.a | 1.1.a Education Project Implementation Contract |  | 8700000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 3000000
1.2.a | 1.2.a TVET |  | 4144000
1.3.a | 1.3.a Education Project Implementation Contract |  | 2500000
1.3.b | 1.3.b Education Project Coordination team* |  | 178400
| Education Project Total |  | 18522400 | 19300000 | 777600
2.1.a | 2.1.a Tax and Customs |  | 384000
| Tax and Customs |  | 384000 | 800000 | 416000
2.2.a | 2.2.a Advisors |  | 728750
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 1650000
| PPPs |  | 2378750 | 3600000 | 1221250
3.1.a | 3.1.a Student Assessment |  | 706400
3.1.b | 3.1.b Teacher Evaluations |  | 300000
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 300000
3.1.d | 3.1 d Other |  | 200000
| M&E |  | 1506400 | 1700000 | 193600
4.1.a | 4.1.a Staff Compensation* |  | 636520
4.1.b | 4.1.b Travel* |  | 35000
4.1.c | 4.1.c Audit |  | 90000
4.1.d | 4.1.d Other |  | 31500
| Program Admin |  | 793020 | 797500 | 4480