## DFP-Com
Detailed Financial Plan - Commitments
| Country: |  | Guatemala
| Accountable Entity: |  | PRONACOM
| Grant Number: |  | TR14GTM15001
| Date Submitted: |  | 2021-06-14
| Quarter # |  | 21
| Forecasted Commitments for -> | Cumulative | Current Period | Next Period | [5 empty] | TOTAL | TOTAL | Variance
|  | Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period | Grant Quarter #21 |  |  | Grant Quarter #20 | Grant Quarter #21 | Grant Quarter #22 | Commitments As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)* | Projections vs. Approved Plan Under / (Over) Budget Difference
| Date/Month/Quarter -> | Dec '20 | Dec '20 Mar '21 | Apr '20 | May `20 | Jun´20 | Apr '21 Jun '21 | Jul '21 Sep '21 | Oct '21 Dec '21
| Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 19 |  |  | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 | 1.1 Improving the Quality of Education (0277) | 11984163.2 | 971794 | 0 | 200000 | 0 | 0 | 200000 | 0 | 13155957.2 | 13221955.41 | 65998.21
1.1.a | 1.1.a Education Project Implementation Contract | 7593016.09 | 0 |  |  |  | 0 | 0 | 0 | 7593016.09 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | 4390617.65 | 920870 | 0 | 200000 | 0 | 0 | 200000 | 0 | 5511487.65 | 0
1.1.c | 1.1.c Other | 529.46 | 50924 |  |  |  | 0 | 0 | 0 | 51453.46 | 0
1.2 | 1.2 Developing Technical and Vocational Education and Training (0400) | 4217885.68 | 26375.64 | 31285.86 | 0 | 0 | 0 | 31285.86 | 0 | 4275547.18 | 4279659.41 | 4112.23
1.2.a | 1.2.a TVET | 4217885.68 | 26375.64 | 31285.86 |  |  | 0 | 31285.86 | 0 | 4275547.18 | 0
1.3 | 1.3 Strengthening Institutional and Planning Capacity (0043) | 3308240.5 | 15960 | 0 | 0 | 0 | 0 | 0 | 32522.1138 | 3356722.6138 | 3387959.57 | 31236.9562
1.3.a | 1.3.a Education Project Implementation Contract | 2944197.11 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2944197.11
1.3.b | 1.3.b Education Project Coordination team* | 361783.78 | 0 | 0 | 0 |  | 0 | 0 | 32522.1138 | 394305.8937
1.3.c | 1.3.c Other | 2259.61 | 15960 | 0 | 0 | 0 | 0 | 0 | 0 | 18219.61
TOTA | TOTAL - Education | 19510289.38 | 1014129.64 | 31285.86 | 200000 | 0 | 0 | 231285.86 | 32522.1138 | 20788226.9937 | 20889574.39 | 101347.3962
2. R | 2. Resource Mobilization Project (REV RFRM)
2.1 | 2.1 Improving Tax and Customs Administration (0443)** | 1323753.64 | 0 | 0 | 37896.24 | 0 | 0 | 37896.24 | 0 | 1361649.88 | 1412145.29 | 50495.41
2.1.a | 2.1.a Tax and Customs | 1323753.64 | 0 |  | 37896.24 |  | 0 | 37896.24 | 0 | 1361649.88
2.2 | 2.2 Strengthening Public-Private Partnership Capacity (0414) | 1548175.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548175.27 | 1548175.27 | 0
2.2.a | 2.2.a Advisors | 477302.5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 477302.5
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | 1030229 | 0 | 0 |  |  | 0 | 0 | 0 | 1030229
2.2.c | 2.2.c Other | 40643.77 | 0 |  |  |  | 0 | 0 | 0 | 40643.77
TOTA | TOTAL - Resource Mobilization | 2871928.91 | 0 | 0 | 37896.24 | 0 | 0 | 37896.24 | 0 | 2909825.15 | 2960320.56 | 50495.41
3. M | 3. M&E (MON & Eval)
M | Monitoring and Evaluation (0016) | 531316.27 | 13000 | 1512.36 | 0 | 0 | 0 | 1512.36 | 0 | 545828.63 | 603518.79 | 57690.16
3.1.a | 3.1.a Student Assessment | 464127.26 | 5000 | 1512.36 |  | 0 | 0 | 1512.36 | 0 | 470639.62
3.1.b | 3.1.b Teacher Evaluations | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
3.1.d | 3.1 d Other | 67189.01 | 8000 |  | 0 |  | 0 | 0 | 0 | 75189.01
| TOTAL - M&E | 531316.27 | 13000 | 1512.36 | 0 | 0 | 0 | 1512.36 | 0 | 545828.63 | 603518.79 | 57690.16
4. Program Admin (PGM ADMIN)
| Program Administration (0017) | 1454700.96 | 34198.42 | 500 | 37000 | 81000 | 0 | 118500 | 135628.33 | 1743027.71 | 1744086.26 | 1058.55
4.1.a | 4.1.a Staff Compensation* | 1171126.39 | 0 |  |  |  | 0 | 0 | 126767.41 | 1297893.8
4.1.b | 4.1.b Travel* | 50430.1 | 344.94 | 500 | 1000 | 1000 | 0 | 2500 | 5424.72 | 58699.76
4.1.c | 4.1.c Audit | 120000 | 20000 |  |  |  | 0 | 0 | 0 | 140000
4.1.d | 4.1.d Other | 113144.47 | 13853.48 | 0 | 36000 | 80000 | 0 | 116000 | 3436.2 | 246434.15
| TOTAL - Program Admin | 1454700.96 | 34198.42 | 500 | 37000 | 81000 | 0 | 118500 | 135628.33 | 1743027.71 | 1744086.26 | 1058.55
| TOTAL MCA-Managed Threshold Funds | 24368235.52 | 1061328.06 | 33298.22 | 274896.24 | 81000 | 0 | 389194.46 | 168150.4438 | 25986908.4838 | 26197500 | 210591.5162
| * This activity has MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report) | [5 empty] | 389194.46
| ** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes. | [5 empty] | 0 |  |  |  |  | 0.00625

## DFP-CASH
Detailed Financial Plan - Cash
Country: |  | Guatemala
Accountable Entity: |  | PRONACOM
Grant Number: |  | TR14GTM15001
Date Submitted: |  | 2021-06-14
Quarter # |  | 21
Forecasted Cash for -> | Cumulative | Current Period | Next Period | [5 empty] | TOTAL | TOTAL | Variance
| Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period | Grant Quarter #21 |  |  | Grant Quarter #20 | Grant Quarter #21 | Grant Quarter #22 | Cash Disbursements As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)** | Projections vs. Approved Plan Under / (Over) Budget Difference
Date/Month/Quarter -> | Dec '20 | Dec '20 Mar '21 | Jul '21 | Ago `21 | Sep´21 | Apr '21 Jun '21 | Jul '21 Sep '21 | Oct '21 Dec '21 |  |  |  | de donde moví | a donde pasé
Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 19 |  |  | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | 11984163.2 | 812 | 566206.0033 | 102311.0033 | 210224 | 0 | 878741 | 292241 | 13155957.2 | 13221955.41 | 65998.21 | 1221955.4078 | 1287953.6178 | 1287953.6178 | 1221955.4078
1.1.a Education Project Implementation Contract | 7593016.09 | 0 |  |  |  | 0 | 0 | 0 | 7593016.09 | 0
1.1.b Grants to Universities for Teacher Training (Diplomados) | 4390617.65 | 0 | 552522 | 92087 | 200000 | 0 | 844609 | 276261 | 5511487.65 | 0
1.1.c Other | 529.46 | 812 | 13684.0033 | 10224.0033 | 10224 | 0 | 34132 | 15980 | 51453.46 | 0
1.2 Developing Technical and Vocational Education and Training (0400) | 4186209.82 | 30972.9 | 27078.6 | 31285.86 | 0 | 0 | 58364.46 | 0 | 4275547.18 | 4279659.41 | 4112.23 | -510340.59 | -506228.36 | -506228.36 | -510340.59
1.2.a TVET | 4186209.82 | 30972.9 | 27078.6 | 31285.86 | 0 | 0 | 58364.46 | 0 | 4275547.18 | 0
1.3 Strengthening Institutional and Planning Capacity (0043) | 3244445.14 | 25944.96 | 10188.2933 | 11188.2933 | 11188.2933 | 0 | 32564.88 | 53767.64 | 3356722.62 | 3387959.57 | 31236.95 | 99859.57 | 131096.52 | 131096.52 | 99859.57
1.3.a Education Project Implementation Contract | 2944197.11 |  |  |  |  | 0 | 0 | 0 | 2944197.11 | 0
1.3.b Education Project Coordination team* | 297988.42 | 23464.96 | 8188.2933 | 8188.2933 | 8188.2933 | 0 | 24564.88 | 48287.64 | 394305.9 | 0
1.3.c Other | 2259.61 | 2480 | 2000 | 3000 | 3000 | 0 | 8000 | 5480 | 18219.61 | 0
TOTAL - Education | 19414818.16 | 57729.86 | 603472.8967 | 144785.1567 | 221412.2933 | 0 | 969670.34 | 346008.64 | 20788227 | 20889574.39 | 101347.39
2. Resource Mobilization Project (REV RFRM)
2.1 Improving Tax and Customs Administration (0443)** | 1027385.08 | 136316.89 | 58183.89 | 51183.89 | 51183.89 | 0 | 160551.67 | 37396.24 | 1361649.88 | 1412145.29 | 50495.41 | 197145.29 | 25000 | 247640.7 | 197145.29
2.1.a Tax and Customs | 1027385.08 | 136316.89 | 58183.89 | 51183.89 | 51183.89 | 0 | 160551.67 | 37396.24 | 1361649.88
2.2 Strengthening Public-Private Partnership Capacity (0414) | 1548175.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548175.27 | 1548175.27 | 0 | -414224.73 | -414224.73 |  | -429224.73
2.2.a Advisors | 477302.5 | 0 |  |  | 0 | 0 | 0 | 0 | 477302.5
2.2.b Feasiblity Studies/ Transaction Advisory Services | 1030229 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1030229
2.2.c Other | 40643.77 | 0 |  | 0 | 0 | 0 | 0 | 0 | 40643.77
TOTAL - Resource Mobilization | 2575560.35 | 136316.89 | 58183.89 | 51183.89 | 51183.89 | 0 | 160551.67 | 37396.24 | 2909825.15 | 2960320.56 | 50495.41
3. M&E (MON & Eval)
Monitoring and Evaluation (0016) | 491440.41 | 18093.06 | 6665.4933 | 6665.4933 | 8665.4933 | 0 | 21996.48 | 14298.68 | 545828.63 | 603518.79 | 57690.16 | -827481.2103 | -769791.0503 | -769791.0503 | -827481.2103
3.1.a Student Assessment | 442829.66 | 7955.28 | 4665.4933 | 4665.4933 | 4665.4933 | 0 | 13996.48 | 5858.2 | 470639.62
3.1.b Teacher Evaluations | [5 empty] | 0 | 0 | 0 | 0 | [5 empty] | -223962.4203
3.1.c Voc Ed Tracer Studies | [5 empty] | 0 | 0 | 0 | 0
3.1 d Other | 48610.75 | 10137.78 | 2000 | 2000 | 4000 | 0 | 8000 | 8440.48 | 75189.01
TOTAL - M&E | 491440.41 | 18093.06 | 6665.4933 | 6665.4933 | 8665.4933 | 0 | 21996.48 | 14298.68 | 545828.63 | 603518.79 | 57690.16
4. Program Admin (PGM ADMIN)
Program Administration (0017) | 1174163.5 | 107723.44 | 37770.7333 | 38270.7333 | 68770.7333 | 0 | 144812.2 | 316328.59 | 1743027.73 | 1744086.26 | 1058.53 | 233086.2625 | 234144.7925 | 234144.7925 | 233086.2625
4.1.a Staff Compensation* | 922459.51 | 86856.82 | 33452.6333 | 33452.6333 | 33452.6333 | 0 | 100357.9 | 188219.57 | 1297893.8
4.1.b Travel* | 49615.65 | 1159.39 | 500 | 1000 | 1000 | 0 | 2500 | 5424.72 | 58699.76
4.1.c Audit | 105000 | 5000 |  |  |  | 0 | 0 | 30000 | 140000
4.1.d Other | 97088.34 | 14707.23 | 3818.1 | 3818.1 | 34318.1 | 0 | 41954.3 | 92684.3 | 246434.17
TOTAL - Program Admin | 1174163.5 | 107723.44 | 37770.7333 | 38270.7333 | 68770.7333 | 0 | 144812.2 | 316328.59 | 1743027.73 | 1744086.26 | 1058.53
TOTAL MCA-Managed Threshold Funds | 23655982.42 | 319863.25 | 706093.0133 | 240905.2733 | 350032.41 | 0 | 1297030.69 | 714032.15 | 25986908.51 | 26197500 | 210591.49 |  |  | 624816.22 | -238962.4203
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report) | [14 empty] | -863778.6403
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.

## QFR - A
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2021-06-14
Schedule A. Multi-Year Financial Plan Adjustment Request Form
Disbursement Period:01-Jul-21 to 30-sep-21
Amounts Expressed In US Dollars
Out of Cycle Report: Yes [ ] ¦ No [X ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Current Approved Multi-Year Financial Plan | Proposed Adjustments (Display all #'s as positive) |  | Proposed Adjusted Multi-Year Financial Plan
Project (code) |  | (from Schedule B, Final Column) | Increase (+) | Decrease (-) | (2+3-4)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | 20889574.39 | 0 | 0 | 20889574.39
1.1 Improving the Quality of Education (0277) | 12000000 | 13221955.41 | 0 | 0 | 13221955.41
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | 4279659.41 | 0 | 0 | 4279659.41
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 3387959.57 | 0 |  | 3387959.57
2. Resource Mobilization Project (REV RFRM) | 4000000 | 2960320.56 | 0 | 0 | 2960320.56
2.1 Improving Tax and Customs Administration (0443)* | 0 | 1412145.29 | 0 |  | 1412145.29
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | 1548175.27 | 0 | 0 | 1548175.27
3. M&E (MON & EVAL) | 1700000 | 603518.79 | 0 | 0 | 603518.79
Monitoring and Evaluation (0016) | 1700000 | 603518.79 |  | 0 | 603518.79
4. Program Admin (PGM ADMIN) | 800000 | 1744086.26 | 0 | 0 | 1744086.26
Program Administration (0017) | 800000 | 1744086.26 | 0 | 0 | 1744086.26
Grand Total | 26200000 | 26197500 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 1800000 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 | 1800000 |  |  | 1800000
4. Program Admin (PGM ADMIN) | 0 | 2500 | 0 | 0 | 2500
Program Administration (0017) | 0 | 2500 | 0 |  | 2500
Grand Total | 1800000 | 1802500 | 0 | 0 | 1802500

## QFR - B
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2021-06-14
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-oct-20 to 31-dec-20
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (Q6 - 10/11/2017) | Adjustment Reported/ Approved (Q10 - 05/11/2018) | Adjustment Reported/ Approved (Q12- 01/04/2019) | Adjustment Reported/ Approved (Q15- 31/12/2019) | Adjustment Reported/ Approved (Q16- 04/04/2020) | Adjustment Reported/ Approved (Q17- 03/08/2020) | Adjustment Reported/ Approved (Q19- 01/01/2021) | Adjustment Reported/ Approved (Q19-26/02/2021) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 | [6 empty] | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 46000 | 0 | 52100 | 490000 | 175000 | 15000 | 811474.39 | 20889574.39
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 | [5 empty] | 1221955.41 | 13221955.41
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 |  |  | 490000 |  |  | -510340.59 | 4279659.41
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 46000 |  | 52100 |  | 175000 | 15000 | 99859.57 | 3387959.57
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | -40000 | -252600 | -740000 | -175000 | -15000 | -217079.44 | 2960320.56
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 |  |  | 415000 |  |  | 197145.29 | 1412145.29
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | -40000 | -252600 | -1155000 | -175000 | -15000 | -414224.73 | 1548175.27
0
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | -269000 | 0 | 0 | 0 | 0 | 0 | -827481.21 | 603518.79
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | -269000 | [5 empty] | -827481.21 | 603518.79
0
4. Program Admin (PGM ADMIN) | 800000 | 0 | -2500 | 223000 | 40000 | 200500 | 250000 | 0 | 0 | 233086.26 | 1744086.26
Program Administration (0017) | 800000 | 0 | -2500 | 223000 | 40000 | 200500 | 250000 |  |  | 233086.26 | 1744086.26
0
Grand Total | 26200000 | 0 | -2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 | [6 empty] | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  | 0 | [7 empty] | 1800000
4. Program Admin (PGM ADMIN) | 0 | 0 | 2500 | 0 | [6 empty] | 2500
Program Administration (0017) |  |  | 2500 | [7 empty] | 2500
Grand Total | 1800000 | 0 | 2500 | 0 | [6 empty] | 1802500

## QFR - B (2) (hidden)
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2020-09-10
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-oct-20 to 31-dec-20
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (Q6 - 10/11/2017) | Adjustment Reported/ Approved (Q10 - 05/11/2018) | Adjustment Reported/ Approved (Q12- 01/04/2019) | Adjustment Reported/ Approved (Q15- 31/12/2019) | Adjustment Reported/ Approved (Q16- 04/04/2020) | Adjustment Reported/ Approved (Q17- 03/08/2020) | Adjustment Reported/ Approved (Q19- 01/01/2021) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 | [5 empty] | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 46000 | 0 | 52100 | 490000 | 175000 | 15000 | 20078100
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 | [5 empty] | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 |  |  | 490000 |  |  | 4790000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 46000 |  | 52100 |  | 175000 | 15000 | 3288100
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | -40000 | -252600 | -740000 | -175000 | -15000 | 3177400
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 |  |  | 415000 |  |  | 1215000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | -40000 | -252600 | -1155000 | -175000 | -15000 | 1962400
0
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | -269000 | 0 | 0 | 0 | 0 | 0 | 1431000
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | -269000 | [5 empty] | 1431000
0
4. Program Admin (PGM ADMIN) | 800000 | 0 | -2500 | 223000 | 40000 | 200500 | 250000 | 0 | 0 | 1511000
Program Administration (0017) | 800000 | 0 | -2500 | 223000 | 40000 | 200500 | 250000 |  |  | 1511000
0
Grand Total | 26200000 | 0 | -2500 | 0 | 0 | 0 | 0 | 0 | 0 | 26197500
* This activity (0443) is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 | [5 empty] | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  | 0 | [6 empty] | 1800000
4. Program Admin (PGM ADMIN) | 0 | 0 | 2500 | 0 | [5 empty] | 2500
Program Administration (0017) |  |  | 2500 | [6 empty] | 2500
Grand Total | 1800000 | 0 | 2500 | 0 | [5 empty] | 1802500

## THP DR
DISBURSEMENT REQUEST
THRESHOLD PROGRAM GRANT AGREEMENT
Country | Guatemala
Projects | Threshold Program / Program Administration and Monitoring and Evaluation
Threshold Program Grant Agreement Date/ Entry into Force Date | April 8, 2015/May 16, 2016
Threshold Program Number | TR14GTM15001
Accountable Entity | PRONACOM
Fiscal Agent | PRONACOM
Request Date | 2021-06-14
Disbursement Period Beginning Date | 2021-07-01
Disbursement Period Ending Date | 31/09/2021
Disbursement Number | 21
Currency (Expressed in USD) | US Dollars
Exchange Rate used to calculate U.S. Dollar equivalent of any local currency balance for purposes of this MCC Disbursement Request
A. Disbursement Request: The undersigned hereby requests the Millennium Challenge Corporation to disburse funds under the Threshold Grant Agreement, dated as of August 28,2013 as follows:
1. Forecasted Cash Disbursement Requirements (from DFP Cash Column) | 1297030.69
2. Interest to be Returned to the USG for Next Period (Interest Sum, Line 7) | 0
3. Working Capital (FOR MCC USE ONLY)
4. Cash Balance at the End of the Current Period (Cash Req, Line 7) | 0
5. Disbursement Request Amount (Lines 1+2-4) | 1297030.69
6. Amount Requested in Words | One million two hundred ninety-seven thousand thirty and 69/100 dollars
C. Compliance: the undersigned confirms that the MCC Disbursement requested herby is in accordance with the terms and conditions set forth in the Threshold Program Agreement, including the limitations on the use or treatment of MCC Funding set out in Section 2.4.
D. Authorization: the undersigned acknowledges that funds disbursed in accordance with this request will be either made (i) directly to third-party vendors for goods, works and services received by the accountable entity upon presentation of valid invoices utilizing MCC's Common Payment System, (ii) to the Permitted Account, or (iii) to the Petty Cash Account.
E. Certificates: Attached hereto are the certificates required under Section 5.2 and 5.3 of the Threshold Program Agreement.
F. Definitions: Capitalized terms used herein shall have the meanings assigned to such terms in the Threshold Program Agreement by and between the Government of Guatemala and the United States, acting through the Millennium Challenge Corporation, dated April 8, 2015, and entered into force on May 15, 2016.
Signed by the THP Director
By: _______________________________________________________________
Name: Francisca de Jesús Cárdenas Morán
Date: June 14, 2021
By: _______________________________________________________________
Name:
Date: ____________________________________________________
By: _______________________________________________________________
Name:
Date:

## Contract level (hidden)
|  |  |  | Percent of disbursements by quarter | [17 empty] | Close Out |  |  |  | Total |  | Cash by quarter | [12 empty] | 90944.77 | [9 empty] | Committments by quarter
Act# |  | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | Apr-21 | 2021-07-01 | 2021-10-01 |  |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | Apr-21 | 2021-07-01 | 2021-10-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2020-04-01 | 2020-07-01 | 2020-10-01 | 2021-01-01 | 2020-04-01 | 2021-07-01 | 2021-10-01 | check Cash=comm | check contract= com | check contract= Dev
Act# |  |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | 19 | 20 | 21 | 22 |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | 20 | 21 | 22 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22
1.1.a |  | 7593016.09 | q4 |  |  |  | 0% | 9.556% | 8.191% | 7.509% | 0% | 6.826% | 0% | 9.556% | 16.38% | 7.167% | 7.509% | 6.826% | 6.826% | 0% | 13.65% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 725612.46 | 621953.53 | 570124.07 | 0 | 518294.61 | 0 | 725612.46 | 1243907.07 | 544209.34 | 570124.07 | 518294.61 | 518294.61 | 0 | 1036589.26 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 7593016.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 1866155 | q9 | Q9: 15%; Q10: 15%; Q11: 5%; Q12: 15%; Q13: 5%; Q14: 15%; Q15: 20%; Q17: 5%; Q18: 5% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279923.25 | 279923.25 | 93307.75 | 279923.25 | 93307.75 | 279923.25 | 373231 | 0 | 93307.75 | 93307.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1866155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 1109637.32 | q9 | Q9: 13.14%; Q10: 17.72%; Q11: 5.144%; Q12: 14.77%; Q13: 4.923%; Q14: 14.77%; Q15: 4.923%; Q16: 14.77%; Q17: 4.923%; Q18: 4.923% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145812.42 | 196636.07 | 57074.8 | 163872.45 | 54624.15 | 163872.45 | 54624.15 | 163872.45 | 54624.19 | 54624.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109637.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 1185760 | q9 | Q9: 0%; Q10: 35%; Q11: 5%; Q12: 12%; Q13: 5%; Q14: 13%; Q15: 20%; Q16: 0%; Q17: 5%; Q18: 5%; 19: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415016 | 59288 | 142291.2 | 59288 | 154148.8 | 237152 | 0 | 59288 | 59288 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1185760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 229065.33 | q13 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 75.86%; Q14: 8.631%; Q15: 9.971%; Q16: 0%; Q17: 5.543% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173758.06 | 19770.86 | 22839.06 | 0 | 12697.35 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229065.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 920870 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 70% | 30% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644609 | 276261 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920870 | 0 | 0 | 0 | 0 | 0
1.1.b |  | 200000 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 100% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0
1.1.c |  | 12500 | q20 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q17: 0%; Q18: 0%; 20: 0%; 21: 60%; 22: 40% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 12500 | q20 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q17: 0%; Q18: 0%; 20: 0%; 21: 60%; 22: 40% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 12500 | q20 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q17: 0%; Q18: 0%; 20: 0%; 21: 60%; 22: 40% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 4984 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 16.29% | 83.71% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812 | 4172 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4984 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 4980 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 80.32% | 19.68% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 980 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4980 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 3460 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 100% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3460 | 0 | 0 | 0 | 0 | 0
1.1.c |  | 529.46 | q8 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 100%; Q9: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 2329506.84 | q6 | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 2% | 8% | 11% | 14% | 0% | 13% | 10% | 10% | 8% | 8% | 10% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 139770.41 | 46590.14 | 186360.55 | 256245.77 | 326130.96 | 0 | 302835.9 | 232950.69 | 232950.69 | 186360.55 | 186360.5 | 232950.68 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2329506.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 1200000 | q9 | Q10: 10%; Q11: 4%; Q12: 14%; Q13: 10%; Q14: 20%; Q15: 15%; Q16: 5%; Q17: 4%; Q18: 18% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 48000 | 168000 | 120000 | 240000 | 180000 | 60000 | 48000 | 216000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 0 | q16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-11 | 4540.18 | q13 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4540.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5085.01 | -544.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 108220.01 | q13 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 84.04%; Q15: 15.96%; Q16: 0%; Q17: 0%; Q18: 0%; 19: 0% | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90944.77 | 17275.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242045.23 | 0 | 0 | 0 | 0 | -133825.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 1762 | q13 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 100%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 9367.68 | q13 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9367.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37470.82 | -0.1 | 0 | 0 | 0 | -28103.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 1278.64 | q14 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 100%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-5 | 35220 | q13 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 22.71%; Q15: 21.12%; Q16: 24.99%; Q17: 16.52%; Q18: 11.24%; 19: 3.407% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 7440 | 8800 | 5820 | 3960 | 1200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 0 | -560 | 0 | -12080 | 0 | -140 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-5 | 2600 | q19 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 0%; 19: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-5 | 12400 | q13 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 25%; Q14: 75%; Q15: 0%; Q16: 0%; Q17: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37200 | 0 | -24800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-8.1 | 18938.4 | q13 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 100%; Q16: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18938.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21211.01 | -2272.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 19917.16 | q15 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 31.13%; Q16: 42.72%; Q17: 26.15%; Q18: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200 | 8508.58 | 5208.58 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34100 | 0 | -14182.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 11700 | q16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 86.32% | 0% | 13.68% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10100 | 0 | 1600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 0 | -800 |  | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 0 | q16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 19796.4 | q16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.09% | 54.7% | 28.21% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3384 | 10828.8 | 5583.6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19796.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 5752.8 | q18 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 58.82% | 41.18% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3384 | 2368.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768 | -1015.2 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 6768 | q19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 0 | q19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 182447.95 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182447.95 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198902.95 | -16227 | -228 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 28325.06 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28325.06 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28325.06 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 58364.46 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58364.46 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27078.6 | 31285.86 | 0 | 0 | 0 | 0
1.2.a |  | 37269.8 | q19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37269.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37269.8 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 20998.74 | q19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20998.74 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20998.74 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 396.08 | q17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396.08 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | ED-8.1 | 14356.92 | q17 | Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14356.92 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14356.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a |  | 2772876.18 | q4 |  |  |  | 0% | 0% | 7.477% | 5.607% | 7.477% | 3.738% | 26.17% | 5.607% | 14.95% | 4.673% | 0% | 14.95% | 3.738% | 0% | 5.607% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 207317.84 | 155488.38 | 207317.84 | 103658.92 | 725612.46 | 155488.38 | 414635.68 | 129573.65 | 0 | 414635.68 | 103658.92 | 0 | 155488.43 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2772876.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a |  | 171320.93 | q17 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 70% | 30% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119924.65 | 51396.28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171320.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c |  | 23.99 | q7 | Q5: 0%; Q6: 0%; Q7: 100%; Q8: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c |  | 56.92 | q7 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 56.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c | ED-16 | 1843 | q16 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q17: 100%; Q18: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c |  | 15960 | q20 | Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q17: 0%; Q18: 0%; 20: 15.54%; 21: 50.13%; 22: 34.34% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2480 | 8000 | 5480 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15960 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 36998.88 | q3 | Q4: 24.33%; Q5: 26.2%; Q6: 23.7%; Q7: 25.78%; Q8: 0% | 100% |  | 0 | 0 | 0 | 9000 | 9691.92 | 8768.88 | 9538.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 36998.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 99851.16 | q3 | Q3: 0%; Q4: 33.05%; Q5: 27.12%; Q6: 26.27%; Q7: 13.56% | 100% |  | 0 | 0 | 0 | 33000 | 27079.68 | 26231.64 | 13539.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 99851.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-4 | 4000 | q3 | Q3: 100% | 100% |  | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-6 | 1500 | q4 | Q4: 100%; Q6: 0% | 100% |  | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 43134 | q7 | Q7: 0%; Q8: 24.62%; Q9: 26.26%; Q10: 25.44%; Q11: 23.69% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10617.6 | 11325.44 | 10971.52 | 10219.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 43134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 18489.64 | q7 | Q7: 17.48%; Q8: 24.35%; Q9: 27.06%; Q10: 25.7%; Q11: 5.411% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 4502.16 | 5002.4 | 4752.28 | 1000.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 18489.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-8 | 1800 | q7 | Q3: 0%; Q7: 100%; Q8: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 111566.08 | q7 | Q7: 8.43%; Q8: 0.26744; Q9: 27.62%; Q10: 27.03%; Q11: 10.17% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 9405.28 | 29837.44 | 30810.4 | 30161.76 | 11351.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 111566.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 7725.48 | q7 | Q6: 0%; Q7: 100%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7725.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-7 | 1241.07 | q8 | Q6: 0%; Q7: 0%; Q8: 100%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 167.23 | q9 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 100%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 35745.92 | q11 | Q1: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 29.21%; Q13: 30.69%; Q14: 31.19%; Q15: 8.911% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10440.64 | 10971.52 | 11148.48 | 3185.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35945 | 0 | 0 | 0 | -199.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 18662.8 | q11 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 17.32%; Q12: 24.95%; Q13: 25.57%; Q14: 25.98%; Q15: 6.186% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3232.32 | 4656.08 | 4771.52 | 4848.48 | 1154.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18759 | 0 | 0 | -96.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-16 | 9982.8 | q11 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 100%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9982.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9982.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 22089.34 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.04% | 37.16% | 35.99% | 5.806% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648.7 | 8207.36 | 7950.88 | 1282.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22746.57 | 0 | -657.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 21993.16 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.14% | 37.32% | 35.57% | 5.977% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4648.7 | 8207.36 | 7822.64 | 1314.46 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22746.57 | 0 | -753.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 21544.32 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 38.1% | 36.9% | 5.952% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103.68 | 8207.36 | 7950.88 | 1282.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22169.49 | 0 | -625.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 16799.44 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 24.43% | 48.85% | 26.72% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4103.68 | 8207.36 | 4488.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22169.49 | 0 | -5370.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 29581.6 | q11 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 30.1%; Q13: 30.1%; Q14: 30.58%; Q15: 9.223% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8903.2 | 8903.2 | 9046.8 | 2728.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | -5420.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 42293.44 | q15 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 17.57%; Q16: 25.52%; Q17: 26.78%; Q18: 25.94%; 19: 4.184% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7432.32 | 10794.56 | 11325.44 | 10971.52 | 1769.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43134 | 0 | 0 | -840.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 71999.04 | q11 | Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 9.009%; Q12: 27.93%; Q13: 27.93%; Q14: 28.38%; Q15: 6.757% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6486.4 | 20107.84 | 20107.84 | 20432.16 | 4864.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72465.26 | 0 | 0 | -466.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 39161.64 | q15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.42% | 26.5% | 26.5% | 26.09% | 8.489% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4864.8 | 10378.24 | 10378.24 | 10216.08 | 3324.28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39526.5 | 0 | 0 | 0 | -364.86 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 39485.96 | q15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.32% | 26.28% | 26.28% | 25.87% | 9.24% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4864.8 | 10378.24 | 10378.24 | 10216.08 | 3648.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39526.5 | 0 | 0 | 0 | -40.54 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-11 | 73708.8 | q15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.18% | 18.18% | 27.27% | 27.27% | 9.091% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13401.6 | 13401.6 | 20102.4 | 20102.4 | 6700.8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93600 | 0 | 0 | 0 | -19891.2 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-12 | 51980.4 | q15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 33.33% | 33.33% | 11.11% | 11.11% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5775.6 | 17326.8 | 17326.8 | 5775.6 | 5775.6 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | 0 | 0 | -29019.6 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 20310.54 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.72% | 50.3% | 8.982% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8270.16 | 10216.08 | 1824.3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21060.53 | 0 | -749.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 10216.08 | q16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80.95% | 19.05% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8270.15 | 1945.93 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21060.53 | -10844.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 4702.64 | q17 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702.64 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4702.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 12324.16 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.47% | 85.53% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1783.76 | 10540.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13134.96 | -810.8 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-21 | 16281.4 | q17 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.17% | 63.46% | 19.37% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794.76 | 10332.92 | 3153.72 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21332.48 | 0 | -5051.08 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 36600 | q17 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60.66% | 39.34% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22200 | 14400 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | -13400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 14400 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 0 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 34643.5 | q15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.17% | 26.53% | 26.53% | 26.11% | 4.663% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600.4 | 9190.4 | 9190.4 | 9046.8 | 1615.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35002.5 | 0 | 0 | -359 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-22 | 771.82 | q17 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72.56% | 27.44% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560.03 | 211.79 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116.07 | 0 | -344.25 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 8848 | q18 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 0%; 19: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8848 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8848 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 6412 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6412 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7213.5 | -801.5 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 6444.06 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6444.06 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7213.5 | -769.44 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 6476.12 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6476.12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7213.5 | -737.38 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 9080.96 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9080.96 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9121.5 | -40.54 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 7898 | q18 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7898 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8077.5 | -179.5 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 6993.15 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6993.15 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6993.15 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 6932.34 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6932.34 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6932.34 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 23181.76 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.33% | 52.67% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10971.52 | 12210.24 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23181.76 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 23370.4 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11239.2 | 12131.2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23370.4 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 23370.4 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11239.2 | 12131.2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23370.4 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 22573.92 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10856.16 | 11717.76 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22573.92 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 16799.44 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8079.12 | 8720.32 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.44 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 16799.44 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8079.12 | 8720.32 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.44 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 16799.44 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8079.12 | 8720.32 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.44 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 23370.4 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.85% | 51.15% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11417.6 | 11952.8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23370.4 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-18 | 21242.96 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.09% | 51.91% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10216.08 | 11026.88 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21242.96 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-21 | 15384 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45% | 55% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6922.8 | 8461.2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15384 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 37500 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 32% | 68% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 25500 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-11 | 42000 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 66.67% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 28000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a |  | 7671.2 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 | 0 | 0 | 0 | 0
2.1.a |  | 7671.2 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 | 0 | 0 | 0 | 0
2.1.a |  | 7409.76 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409.76 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409.76 | 0 | 0 | 0 | 0
2.1.a |  | 7671.2 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7671.2 | 0 | 0 | 0 | 0
2.1.a |  | 6972.88 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6972.88 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6972.88 | 0 | 0 | 0 | 0
2.1.a |  | 500 | q21 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0
2.1.a | MR-22 | 1500 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 49.37% | 50.63% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740.57 | 759.43 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-22 | 476.17 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.17 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.17 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | MR-21 | 7179.2 | q19 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7179.2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7179.2 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 61250 | q2 | Q2: 0%; Q3: 40%; Q4: 60%; Q5: 0% | 100% |  | 0 | 0 | 24500 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 121200 | q3 | Q4: 33.33%; Q5: 16.67%; Q6: 33.33%; Q7: 16.67% | 100% |  | 0 | 0 | 0 | 40399.9996 | 20199.9992 | 40399.9996 | 20200.0016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 121200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 90020.47 | q4 |  |  |  |  | 0% | 46.61% | 10.41% | 7.998% | 6.887% | 5.759% | 7.213% | 6.229% | 0% | 8.89% | 0% | 0% | 0% | 0% |  |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 41958.49 | 9374.56 | 7200 | 6199.74 | 5184.57 | 6493.17 | 5607.08 | 0 | 8002.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 124265.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34245.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c |  | 5000 | q4 | Q4: 100% | 100% |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | MR-5 | 57832.03 | q5 | Q5: 33.33%; Q6: 44.44%; Q7: 22.22%; Q14: 0% | 100% |  | 0 | 0 | 0 | 0 | 19277.35 | 25703.12 | 12851.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 57832.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 147000 | q5 | Q5: 8.333%; Q6: 16.67%; Q7: 25%; Q8: 33.33%; Q9: 16.67%; Q10: 0% | 100% |  | 0 | 0 | 0 | 0 | 12250 | 24500 | 36750 | 49000 | 24500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c |  | 961.64 | q5 | Q5: 100% | 100% |  | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 961.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b |  | 1030229 | q6 | Q6: 0%; Q7: 10%; Q8: 0%; Q9: 0%; Q10: 30%; Q11: 0%; Q12: 20%; Q13: 40% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 103022.9 | 0 | 0 | 309089.7 | 0 | 206024.8 | 412091.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1030229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 0 | q14 | Q5: 0%; Q6: 0%; Q7: 0%; Q13: 0; Q14: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c |  | 24797.88 | q10 | Q4: 0%; Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 100%; Q11: 0; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24797.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24797.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.c |  | 9884.25 | q12 | Q4: 0%; Q5: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 100%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9884.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9884.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a |  | 0 | q18 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b |  | 0 | q14 | [22 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: Q6 to Q18
3.1.a | ME-3 | 8000 | q3 | Q4: 50%; Q5: 50% | 100% |  | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-2 | 52000 | q3 | Q4: 11.54%; Q5: 11.54%; Q6: 11.54%; Q7: 11.54%; Q8: 11.54%; Q9: 11.54%; Q10: 11.54%; Q11: 11.54%; Q12: 7.692%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-4 | 8100 | q4 | Q4: 0%; Q5: 41.67%; Q6: 58.33% | 100% |  | 0 | 0 | 0 | 0 | 3375 | 4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-5 | 18700 | q4 | Q4: 0%; Q5: 36.36%; Q6: 63.64% | 100% |  | 0 | 0 | 0 | 0 | 6800 | 11900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 18700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-7 | 13200 | q5 | Q6: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 640.16 | q5 | Q6: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 640.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 13864.72 | q6 | Q6: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 13864.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 475.49 | q7 | Q7: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 475.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME.11 | 49165.09 | q7 | Q7: 0%; Q8: 88.21%; Q9: 0%; Q10: 7.632%; Q11: 4.163% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43366.39 | 0 | 3752.1 | 2046.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 49165.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME.13 | 38502 | q7 | Q7: 0%; Q8: 10.95%; Q9: 89.05%; Q10: 0%; Q11: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4216 | 34286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 38502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a |  | 68334.49 | q8 | Q7: 0%; Q8: 0%; Q9: 100%; Q10: 0%; Q11: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68334.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68334.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME.15 | 7848.12 | q8 | Q7: 0%; Q8: 0%; Q9: 100%; Q10: 0%; Q11: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7848.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 203.63 | q8 | Q7: 0%; Q8: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | ME.24 | 179.46 | q8 | Q7: 0%; Q8: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a |  | 28000 | q9 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | ME.21 | 2009.07 | q9 | Q7: 0%; Q8: 0%; Q9: 42.58%; Q10: 57.42%; Q11: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855.52 | 1153.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2009.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 507.1 | q9 | Q7: 0%; Q8: 0%; Q9: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a |  | 56.05 | q9 | Q7: 0%; Q8: 0%; Q9: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 2713.73 | q10 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 100%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME.12 | 21980.11 | q11 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 50.63%; Q13: 0%; Q14: 40.35%; Q15: 9.021%; Q16: 0%; Q17: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11127.6 | 0 | 8869.75 | 1982.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | -21980.11 | -6039.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-14 | 12335.19 | q11 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 100%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 0%; 19: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12335.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | -67664.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-2.1 | 37492.96 | q13 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.88% | 17.93% | 18.53% | 20.93% | 21.05% | 5.68% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5952.32 | 6721.28 | 6949.12 | 7847.84 | 7892.64 | 2129.76 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34717.12 | 0 | 0 | 0 | 3590.16 | 0 | -814.32 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-2.1 | 5011.2 | q19 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5011.2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5011.2 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-2.1 | 22809.96 | q19 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.88% | 39.44% | 25.68% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7955.28 | 8996.48 | 5858.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21297.6 | 0 | 1512.36 | 0 | 0 | 0 | 0
3.1.a |  | 214.45 | q12 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a |  | 31800 | q14 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 35%; Q16: 0%; Q17: 0%; Q18: 65%; 19: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11130 | 0 | 0 | 20670 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d | ME.18 | 28000 | q13 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.17% | 12.91% | 0.4731% | 0% | 0% | 3.071% | 36.21% | 14.29% | 16.89% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526.63 | 3614.28 | 132.47 | 0 | 0 | 859.82 | 10137.78 | 4000 | 4729.02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0
3.1.d | ME.29 | 10000 | q18 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.66% | 12.23% | 0% | 40% | 37.11% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065.53 | 1223.01 | 0 | 4000 | 3711.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-8 | 6600 | q15 |  |  |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 16.67% | 33.33% | 33.33% | 16.67% |  |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 2200 | 2200 | 1100 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-8 | 26400 | q16 |  |  |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 33.33% | 25% | 41.67% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800 | 6600 | 11000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME.16 | 6090 | q18 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; Q16: 0%; Q17: 0%; Q18: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6090 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6090 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 14722.43 | q15 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 100%; Q17: 0%; Q18: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14722.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14722.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 1873.22 | q14 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 100%; Q15: 0%; 19: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-8 | 1500 | q19 |  |  |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a |  | 5000 | q20 |  |  |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0
3.1.a | ME-8 | 1500 | q19 |  |  |  | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0
3.1.d |  | 0 | q19 | Q7: 0%; Q8: 0%; Q9: 0%; Q10: 0%; Q11: 0%; Q12: 0%; Q13: 0%; Q14: 0%; Q15: 0%; 19: 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.c |  | 120000 | q8 | [5 empty] | 0% | 0% | 8.333% | 4.167% | 4.167% | 9.167% | 10% | 5% | 5% | 15% | 10% | 0% | 12.5% | 4.167% | 4.167% |  | 8.333% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 5000 | 5000 | 11000 | 12000 | 6000 | 6000 | 18000 | 12000 | 0 | 15000 | 5000 | 5000 | 0 | 10000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.c |  | 20000 | q20 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 7666.96 | q2 | Q2: 100%; Q3: 0%; Q4: 0% | 100% |  | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7666.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A-2 | 1124.38 | q3 | Q2: 0%; Q3: 0%; Q4: 100% | 100% |  | 0 | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1124.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.1 | 2343.78 | q15 | Q2: 0%; Q3: 0%; Q4: 0%; Q15: 0; Q16: 100%; Q17: 0 | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343.78 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 982.1 | q3 | Q2: 0%; Q3: 18.18%; Q4: 27.27%; Q5: 27.27%; Q6: 27.27% | 100% |  | 0 | 0 | 178.5636 | 267.8455 | 267.8455 | 267.8455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 982.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a |  | 15389.66 | q3 |  | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15389.66 |  | 0 | 0 | 375 | 4500 | 4848.48 | 4771.52 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 14495 | 894.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.8 | 7222.5 | q3 | Q6: 0; Q7: 0; Q8: 0; Q9: 0; Q10: 7222.5 | 7222.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7222.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 7222.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.7 | 505.16 | q4 | Q2: 0%; Q3: 0%; Q4: 100%; Q5: 0%; Q6: 0%; Q7: 0% | 100% |  | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 505.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a |  | 156905.56 | q4 | 0 | 0 | 0 | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6153.6 | 7295.78 | 6828.72 | 6997.9 | 7228.6 | 7819.84 | 8392.32 | 7529.4 | 8936.32 | 9533.44 | 9235.52 | 8964.88 | 10321.92 | 11141.12 | 21578.24 | 156905.56 |  | 0 | 0 | 0 | 2666.56 | 4615.2 | 6230.52 | 5435.68 | 6153.6 | 7295.78 | 6828.72 | 6997.9 | 7228.6 | 7819.84 | 8392.32 | 7529.4 | 8936.32 | 9533.44 | 9235.52 | 8964.88 | 10321.92 | 11141.12 | 21578.24 |  | 0 | 0 | 0 | 3384.48 | 24260.44 | 0 | 0 | 0 | 29991 | 0 | 0 | -1845.6 | 16497 | -1133.64 | 9018.36 | 26384.54 | 0 | 8932.9 | 26882.96 | 0 | 0 | 14533.12 | 0 | 0 | 0
4.1.d | A.5 | 1630 | q5 | Q2: 0%; Q3: 0%; Q4: 0%; Q5: 100% | 100% |  | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.3 | 739.99 | q6 | Q2: 0%; Q3: 0%; Q4: 0%; Q5: 0; Q6: 100%; Q7: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 739.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.8 | 1232.14 | q6 | Q2: 0%; Q3: 0%; Q4: 0%; Q5: 0%; Q6: 100%; Q7: 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1232.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 1071.43 | q2 | Q2: 25%; Q3: 25%; Q4: 25%; Q5: 25%; Q6: 0.0039% | 100% |  | 0 | 267.8157 | 267.8575 | 267.8575 | 267.8575 | 0.041786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1071.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 982.15 | q6 | Q2: 0%; Q3: 0%; Q4: 0%; Q6: 27.27%; Q7: 27.27%; Q8: 9.091%; Q9: 0%; Q10: 36.36% | 100% |  | 0 | 0 | 0 | 0 | 0 | 267.85 | 267.87 | 89.29 | 0 | 357.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 982.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a |  | 30021.76 | q6 | Q1: 0; Q2: 0; Q3: 0; Q4: 0; Q5: 0; Q6: 2706.88; Q7: 7628.48; Q8: 7505.44; Q9: 7751.52; Q10: 4429.44 | 30021.76 |  | 0 | 0 | 0 | 0 | 0 | 2706.88 | 7628.48 | 7505.44 | 7751.52 | 4429.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 29991 | 0 | 0 | 0 | 30.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 714.25 | q7 | Q2: 0%; Q3: 0%; Q4: 0%; Q7: 37.5%; Q8: 12.5%; Q9: 0%; Q10: 50% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 267.84 | 89.28 | 0 | 357.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 714.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 7714.32 | q9 | Q2: 0%; Q3: 0%; Q4: 0%; Q6: 0%; Q7: 0%; Q8: 0%; Q9: 0%; Q10: 33.33%; Q11: 25%; Q12: 25%; Q13: 16.67% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.44 | 1928.58 | 1928.58 | 1285.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7714.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 4500.02 | q13 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 57.14% | 42.86% | 0% | 0% | [5 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2571.44 | 1928.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7214 | 500.32 | -3214.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 267.87 | q15 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 11854.9 | q16 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.54% | 28.99% | 43.48% | 0% |  |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3264.4 | 3436.2 | 5154.3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13573 | 0 | 0 | 0 | -1718.1 | 0 | 0 | 0 | 0 | 0
4.1.d | A.6 | 3436.2 | q19 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 3436.2 | q20 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718.1 | 1718.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 3436.2 | q22 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 | 0 | 0 | 0
4.1.d | A.6 | 10308.6 | q20 |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 50% | 16.67% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3436.2 | 5154.3 | 1718.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10308.6 | 0 | 0 | 0 | 0 | 0
[28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | [6 empty] | Total | [46 empty] | 0 | #VALUE! | #VALUE!
Salary Type Expenses | [50 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | [10 empty] | 0 | 0 | 0
1.3.c |  | 198.71 | q8 |  |  |  |  | 0% | 0% | 0% | 100% | [14 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.c |  | 136.99 | q9 |  |  |  |  | 0% | 0% | 0% | 0% | 100% | [13 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.b |  | 253143.72 | q2 | 0 | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11848.32 | 10232.64 | 10985.28 | 11945.12 | 12438.72 | 12043.84 | 12370.7 | 12851.36 | 13473.2 | 12851.36 | 12635.12 | 13931.52 | 14584.56 | 28669.14 | 253143.72 |  | 0 | 1400 | 9000 | 9000 | 10232.64 | 11130.24 | 10367.28 | 11152.68 | 11848.32 | 10232.64 | 10985.28 | 11945.12 | 12438.72 | 12043.84 | 12370.7 | 12851.36 | 13473.2 | 12851.36 | 12635.12 | 13931.52 | 14584.56 | 28669.14 |  | 0 | 43635.2 | 0 | 0 | 0 | 0 | 43421.4 | 0 | 0 | 0 | 48122 | 0 | 0 | 4 | 50524.5 | 0 | 0 | 11723.88 | 36403.84 | 0 | 0 | 19308.8963 | 0.00375 | 0.00375 | 0
1.3.b |  | 141162.18 | q6 | 0 | 0 | 0 | 0 | 0 | 2358.88 | 6256.16 | 6410 | 6486.92 | 6193.92 | 7382.4 | 7505.44 | 7628.48 | 7881.08 | 8426.16 | 8392.32 | 8935.04 | 9235.52 | 8937.6 | 9533.44 | 9980.32 | 19618.5 | 141162.18 |  | 0 | 0 | 0 | 0 | 0 | 2358.88 | 6256.16 | 6410 | 6486.92 | 6193.92 | 7382.4 | 7505.44 | 7628.48 | 7881.08 | 8426.16 | 8392.32 | 8935.04 | 9235.52 | 8937.6 | 9533.44 | 9980.32 | 19618.5 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 29991 | 0 | -1 | 0 | 5549.76 | 32994 | 0 | 1271.6 | 7969.36 | 25174.24 | 0 | 0 | 13213.2175 | 0.0025 | 0.0025 | 0
2.1.a |  | 1369.14 | q12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 1369.14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a |  | 122323.0912 | q15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13155.6 | 14482.7 | 13963.4 | 14036.83 | 15991.92 | 17261.12 | 33431.5212 | 122323.0912 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13155.6 | 14482.7 | 13963.4 | 14036.83 | 15991.92 | 17261.12 | 33431.5212 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45409.9 | 0 | 0 | 12484.09 | 41912.7 | 0 | 0 | 22516.4012 | 0 | 0 | 0
4.1.a |  | 231948.0763 | q1 | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 0 | 12204.64 | 11666.2 | 12486.68 | 12717.44 | 13298.32 | 11726.04 | 11620.4 | 12756.03 | 12386.29 | 11033.83 | 11445.7 | 18998.7 | 30607.8063 | 231948.0763 |  | 10000 | 12000 | 11000 | 12000 | 4000 | 0 | 0 | 0 | 0 | 12204.64 | 11666.2 | 12486.68 | 12717.44 | 13298.32 | 11726.04 | 11620.4 | 12756.03 | 12386.29 | 11033.83 | 11445.7 | 18998.7 | 30607.8063 |  | 45000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 49998 | 0 | 0 | 0 | 16600.88 | -845.12 | 51499.5 | 0 | 0 | 8498.29 | 36581.92 | 0 | 0 | 20614.6063 | 0 | 0 | 0
4.1.a |  | 243156.8825 | q2 |  | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 10053.12 | 11489.28 | 9469.68 | 10950.72 | 11515.52 | 11520.84 | 11026.08 | 12343.52 | 13265.92 | 12851.36 | 12384.66 | 14136 | 15732 | 30028.3125 | 243156.8825 |  | 0 | 6666.67 | 10500 | 10500 | 11489.28 | 11130.24 | 6103.68 | 0 | 10053.12 | 11489.28 | 9469.68 | 10950.72 | 11515.52 | 11520.84 | 11026.08 | 12343.52 | 13265.92 | 12851.36 | 12384.66 | 14136 | 15732 | 30028.3125 |  | 0 | 42000 | 0 | 7000 | 0 | 3440.43 | 3949.44 | 0 | 43758 | 0 | 0 | 1615.68 | 22971 | -329.84 | 12062.72 | 37258.58 | 0 | 11783.42 | 37423.14 | 0 | 0 | 20224.3125 | 0 | 0 | 0
4.1.a |  | 175131.92 | q2 | 0 | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7351.64 | 8059.12 | 7382.4 | 7653.76 | 8392.32 | 7986.24 | 8527.68 | 9017.92 | 9235.52 | 9682.4 | 9384.48 | 9510.44 | 10403.84 | 11059.2 | 21578.24 | 175131.92 |  | 0 | 1760 | 4400 | 0 | 8981.92 | 7628.48 | 7136.32 | 7351.64 | 8059.12 | 7382.4 | 7653.76 | 8392.32 | 7986.24 | 8527.68 | 9017.92 | 9235.52 | 9682.4 | 9384.48 | 9510.44 | 10403.84 | 11059.2 | 21578.24 |  | 0 | 6160 | 0 | 29991 | 0 | 0 | 0 | 18517.52 | 0 | 0 | 32994 | 0 | 0 | -236.88 | 36309 | 0 | 0 | 9435.64 | 27428.52 | 0 | 0 | 14533.12 | 0 | 0 | 0
4.1.a |  | 182167.06 | q2 |  | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7997.6 | 7505.44 | 7395.36 | 8121.6 | 8392.32 | 8392.32 | 8720 | 9235.52 | 9682.4 | 9235.52 | 9696.64 | 10485.76 | 10977.28 | 21578.24 | 182167.06 |  | 0 | 1760 | 6600 | 6600 | 7874.56 | 7628.48 | 6767.2 | 7520.82 | 7997.6 | 7505.44 | 7395.36 | 8121.6 | 8392.32 | 8392.32 | 8720 | 9235.52 | 9682.4 | 9235.52 | 9696.64 | 10485.76 | 10977.28 | 21578.24 |  | 0 | 32185.6 | 0 | 0 | 0 | 0 | 29914.1 | 0 | 0 | 0 | 32994 | 0 | 0 | -372.24 | 36309 | 0 | 0 | 8988.76 | 27614.72 | 0 | 0 | 14533.12 | 0 | 0 | 0
4.1.a |  | 0 | q18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.4 | 6802.75 | q10 |  | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 100% | [12 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6802.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6802.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.a |  | 64297.745 | q13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741.04 | 6015.06 | 6294.24 | 6598.8 | 6497.44 | 6812.48 | 7035.84 | 7594.24 | 14708.605 | 64297.745 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741.04 | 6015.06 | 6294.24 | 6598.8 | 6497.44 | 6812.48 | 7035.84 | 7594.24 | 14708.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4365.36 | 24745.5 | 0 | 0 | 6286.28 | 18994.24 | 0 | 0 | 9906.365 | 0 | 0 | 0
4.1.a |  | 76552.045 | q12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3785.12 | 5677.68 | 5631.52 | 6424 | 6294.24 | 6598.8 | 6395.76 | 6406.24 | 7035.84 | 7594.24 | 14708.605 | 76552.045 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3785.12 | 5677.68 | 5631.52 | 6424 | 6294.24 | 6598.8 | 6395.76 | 6406.24 | 7035.84 | 7594.24 | 14708.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22503 | 0 | -5654.6 | 24745.5 | 0 | 0 | 6431.78 | 18620 | 0 | 0 | 9906.365 | 0 | 0 | 0
4.1.d |  | 36750 | q13 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 8.762% | 22.86% | 0% | 8.571% | 9.524% | 4.762% | 5.714% | 17.14% | 17.14% | 5.524% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 8400 | 0 | 3150 | 3500 | 1750 | 2100 | 6300 | 6300 | 2030 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.9 | 25000 | q21 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
4.1.d | A.9 | 25000 | q21 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
4.1.d | A.10 | 357.14 | q20 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.14 | 0 | 0 | 0 | 0 | 0
4.1.d | A.10 | 232.14 | q20 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232.14 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 499.99 | q19 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.99 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499.99 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 1426.15 | q19 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426.15 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426.15 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 11000 | q21 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 5500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0
4.1.d | A.9 | 55000 | q21 |  |  |  |  | 0% | [5 empty] | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0 | 0 | 0 | 0
1.2.a |  | 318.43 | q8 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 884.24 | q8 | [5 empty] | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a |  | 144417.39 | q4 | 0 | 0 | 0 | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 9190.4 | 8616 | 8185.2 | 8400.6 | 9069.2 | 9651.2 | 8953.75 | 9500 | 10132.48 | 9657.52 | 9340.88 | 9974.16 |  |  | 144417.39 |  | 0 | 0 | 0 | 0 | 8041.6 | 8903.2 | 8185.2 | 8616 | 9190.4 | 8616 | 8185.2 | 8400.6 | 9069.2 | 9651.2 | 8953.75 | 9500 | 10132.48 | 9657.52 | 9340.88 | 9974.16 | 0 | 0 |  | 0 | 0 | 0 | 35002.5 | 0 | 0 | 0 | 35002.5 | -394.9 | 0 | 0 | 1256.5 | 18235.15 | 0 | 10028.2 | 27911.82 | 0 | 8351.38 | 9499.2 | -474.96 | 0 | 0 | 0 | 0 | 0
[73 empty] | 0 | 0 | 0
Recurring Expenses for which commitments will be made in same quarter as expense. | [72 empty] | 0 | 0 | 0
4.1.d | A.7 | 7441.48 |  |  | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2269.38 | 0 | 0 | 0 | 0 |  |  |  | 7441.48 |  | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2269.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1000 | 0 | 1672.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2269.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.5 | 1317.87 | q16 |  | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 0% |  |  |  | 0% |  | 100% | [6 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317.87 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | A.5 | 1237.5 | q20 |  | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 0% |  |  |  | 0% |  | 0% |  |  |  | 100% |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237.5 | 0 | 0 | 0 | 0 | 0
4.1.d |  | 3200 | q13 |  | 0% | 0% | 0% |  |  | 0 | 0 | 0 | 0% |  |  |  | 100% | [8 empty] | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.b |  | 58699.76 |  | 0 | 0 | 573.21 | 2945.3 | 276.14 | 0 | 2619.65 | 13337.34 | 4226.4 | 3660.32 | 161.88 | 632.48 | 3382.59 | 12580.91 | 4303.54 | 0 | 0 | 0 | 915.89 | 1159.39 | 2500 | 5424.72 | 58699.76 |  | 0 | 0 | 573.21 | 2945.3 | 276.14 | 0 | 2619.65 | 13337.34 | 4226.4 | 3660.32 | 161.88 | 632.48 | 3382.59 | 12580.91 | 4303.54 | 0 | 0 | 0 | 915.89 | 1159.39 | 2500 | 5424.72 |  | 0 | 0 | 573.21 | 2945.3 | 276.14 | 0 | 2619.65 | 13337.34 | 4226.4 | 3660.32 | 161.88 | 632.48 | 4719.59 | 11243.91 | 4303.54 | 0 | 0 | 0 | 1730.34 | 344.94 | 2500 | 5424.72 | 0 | 0 | 0
[73 empty] | 0 | 0 | 0
|  | 25986908.51 | [70 empty] | 0 | 25986908.51 | 25986908.51
[73 empty] | 0 | 0 | 0
1.1.a |  | 7593016.09 | [70 empty] | 0 | 7593016.09 | 7593016.09
1.1.b |  | 5511487.65 | [70 empty] | 0 | 5511487.65 | 5511487.65
1.2.a |  | 4275547.18 | [70 empty] | 0 | 4275547.18 | 4275547.18
1.3.a |  | 2944197.11 | [70 empty] | 0 | 2944197.11 | 2944197.11
1.3.b |  | 394305.9 | [70 empty] | 0 | 394305.9 | 394305.9
|  | 20718553.93 | [70 empty] | 0 | 20718553.93 | 20718553.93
2.1.a |  | 1361649.88 | [70 empty] | 0 | 1361649.88 | 1361649.88
|  | 1361649.88 | 1412145.29 | 50495.41 | [68 empty] | 0 | 1361649.88 | 1361649.88
2.2.a |  | 477302.5 | [70 empty] | 0 | 477302.5 | 477302.5
2.2.b |  | 1030229 | [70 empty] | 0 | 1030229 | 1030229
|  | 1507531.5 | 1548175.27 | 40643.77 | [68 empty] | 0 | 1507531.5 | 1507531.5
3.1.a |  | 470639.62 | [70 empty] | 0 | 470639.62 | 470639.62
3.1.b |  | 0 | [70 empty] | 0 | 0 | 0
3.1.c |  | 0 | [70 empty] | 0 | 0 | 0
3.1.d |  | 75189.01 | [70 empty] | 0 | 75189.01 | 75189.01
|  | 545828.63 | 603518.79 | 57690.16 | [68 empty] | 0 | 545828.63 | 545828.63
4.1.a |  | 1297893.8 | [70 empty] | 0 | 1297893.8 | 1297893.8
4.1.b |  | 58699.76 | [70 empty] | 0 | 58699.76 | 58699.76
4.1.c |  | 140000 | [70 empty] | 0 | 140000 | 140000
4.1.d |  | 246434.17 | [70 empty] | 0 | 246434.17 | 246434.17
|  | 1743027.73 | 1744086.26 | 1058.53 | [68 empty] | 0 | 1743027.73 | 1743027.73
[73 empty] | 0 | 0 | 0
|  | 103727000.36 | 5307925.61 | 159887.87 | 24587.92 | 42450.0418 | 49890.6052 | 60364.9505 | 62497.3875 | 61400.7598 | 68058.1914 | 72918.1652 | 85772.5927 | 69900.3699 | 80825.0083 | 89131.3833 | 100672.6007 | 96790.1183 | 107865.9537 | 115151.7114 | 111709.2687 | 110704.2315 | 121468.5329 | 127442.6049 | 241944.5722 |  | 0 | 10000 | 32521.4457 | 71394.6311 | 187699.2026 | 897773.5721 | 1112159.6868 | 1161252.3816 | 490485.58 | 1507988.41 | 2492864.4 | 1622558.2 | 2810659.98 | 2037176.28 | 1886031.65 | 2352734.97 | 1286794.43 | 753564.73 | 2330307.96 | 612014.91 | 319863.25 | 1297030.69 | 714032.15 |  | 45000 | 194969.19 | 346447.23 | 10604853.11 | 249800.41 | 3434986.27 | 351557.53 | 266594.97 | 5527721.58 | 67996.44 | 416426.44 | 35628.9 | 805244.14 | 46932.31 | 603934.1 | 292898.61 | 230979.59 | 178140.35 | 668124.37 | 1061328.06 | 389194.46 | 168150.4438 | 168150.45
|  | -96.18 | [25 empty] | 10000 | 42521.4457 | 113916.0769 | 301615.2794 | 1199388.8515 | 2311548.5384 | 3472800.92 | 3963286.5 | 5471274.91 | 7964139.31 | 9586697.51 | 12397357.49 | 14434533.77 | 16320565.42 | 18673300.39 | 19960094.82 | 20713659.55 | 23043967.51 | 23655982.42 | 23975845.67 | 25272876.36 | 25986908.51 |  | 45000 | 239969.19 | 586416.42 | 11191269.53 | 11441069.94 | 14876056.21 | 15227613.74 | 15494208.71 | 21021930.29 | 21089926.73 | 21506353.17 | 21541982.07 | 22347226.21 | 22394158.52 | 22998092.62 | 23290991.23 | 23521970.82 | 23700111.17 | 24368235.54 | 25429563.6 | 25818758.06 | 25986908.5038
[28 empty] | cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash cash, cash cash cash cash | [22 empty] | Q1: COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM COM
[46 empty] | 97088.34 |  | 432343.5633 | [20 empty] | 113144.47 | 13496.34
[46 empty] | 23558894.08 | [22 empty] | 24255091.07 | 1047831.72
23558536.94
0
[25 empty] | travel | 58699.76
0
Note on D4: Josue Andreé Ricart Vásquez: FHI
Note on D5: Josue Andreé Ricart Vásquez: Universidades Programas de Formación
Note on D19: Josue Andreé Ricart Vásquez: Firma Consultora para la Revisión de dos carreras y creación de dos nuevas ENCA
Note on D44: Josue Andreé Ricart Vásquez: FHI
Note on D45: Josue Andreé Ricart Vásquez: FHI
Note on D51: Josue Andreé Ricart Vásquez: PAGOS DICIEMBRE Y ENERO
Note on D52: Josue Andreé Ricart Vásquez: LAS DATABASE YA FUERON PAGADAS
Note on D53: pagado
Note on D55: Josue Andreé Ricart Vásquez: Lilian Merlo contrato 2018
Note on D57: Josue Andreé Ricart Vásquez: CONTRATACIONES 2018 Y PAGO DE FEBRERO 2018
Note on D71: investigadores de aduanas
Note on D77: Josue Ricart:
Note on D78: Josue Ricart:
Note on D79: Josue Ricart: aun estan en proceso pero si hay seguridad en su contratación q17
Note on D91: investigadores de aduanas
Note on D113: Josue Ricart: aun estan en proceso pero si hay seguridad en su contratación q17
Note on D114: Josue Andreé Ricart Vásquez: ya fue pagado en su totalidad PU-MCC-002-2016
Note on D117: Josue Andreé Ricart Vásquez: MGO
Note on D118: UNIVERSIDAD INTERNACIONES
Note on D121: Josue Andreé Ricart Vásquez: Deloitte
Note on D126: Josue Andreé Ricart Vásquez: ya están los terminos de referencia están en proceso de evaluación 02/09/2019
Note on D133: Josue Andreé Ricart Vásquez: incluye pago de corporación abiansha por 1652.68
Note on D134: Josue Andreé Ricart Vásquez: Incluye pago de rustika
Note on D141: Experto en escala vertical
Note on D166: Josue Andreé Ricart Grupo Sega
Note on D167: Josue Andreé Ricart Vásquez: Tecnasa
Note on D168: Josue Andreé Ricart Vásquez: Tecnasa
Note on D169: Josue Andreé Ricart Vásquez: 01-2017
Note on D172: Josue Andreé Ricart Vásquez: Reparación Impresora
Note on D175: Josue Andreé Ricart Vásquez: poliycom phone
Note on D176: Josue Andreé Ricart Vásquez: compra de credenzas
Note on D177: Josue Andreé Ricart Vásquez: PU-MCC-SNC-001-2016
Note on D178: Josue Andreé Ricart Vásquez: 03-2017
Note on D180: Josue Andreé Ricart Vásquez: 01-2018
Note on E5: Josue Andreé Ricart Vásquez: Cambia de 3M a 4M ya ***** ADJUDICADO*** UPANA 1,185,760.00 INTERNACIONES 1,866,155.00 UNIVERSIDAD DEL VALLE 972,082.83
Note on E19: Josue Andreé Ricart Vásquez: actualizar a 1,200,000.00 actualizado
Note on E21: Josue Andreé Ricart Vásquez: no saben el monto exacto, liseth dice un monto pero no se sabe, mejor asi como está, se estima que se van a pagar en noviembre
Note on E23: Josue Andreé Ricart Vásquez: inicialmente tenía 90 oeri es necesario rebajar porque si no se desfinancia el componente. Por rescición de contrato se rebaja el monto de 29954.00 a 1762.00
Note on E25: Josue Andreé Ricart Vásquez: se hará un nuevo evento pero la propuesta que mas barato había ofertado fue por un monto de alrededor de 10,000 dólares mas que la que ganó anteriormente
Note on E26: Josue Andreé Ricart Vásquez: Inicial mente se tenía contemplado un monto de 48,000 pero se fue una persona y le unieron dos contratos a marvin mas 2400 descontando un producto que el anterior ya no entrego es decir 1940 USD según contrato
Note on E31: Josue Ricart: verificar monto total
Note on E37: Josue Andreé Ricart Vásquez: No tienen información sobre para cuando exactamente **** se ampliará 150,000
Note on E40: Josue Ricart: SEGÚN PROGRAMACIÓN SOLO PODRÍA DARSE EN EL MES DE ENERO. ESTÁ EN QDRP AMPLIACIÓN
Note on E43: Josue Andreé Ricart Vásquez: solo 35,000 resto pasar a otra linea de los 90000 iniciales, monto varió en el q15, los 35000 resulta que eran quetzales pero el equipo de educación no informó bien, en q17 en la realización de la sd vimos que son aproximandamente 25,000.00
Note on E73: Josue Ricart: este monto varía con una ampliación se cambió de 93600 al monto que tiene
Note on E116: Josue Andreé Ricart Vásquez: pago del q13 reprogramar all q14
Note on E122: Josue Andreé Ricart Vásquez: no se va a pagar nada este trimestre
Note on E123: Josue Andreé Ricart Vásquez: Este monto surgió de una rebaja en el monto estimado de Metro Riel, ya que al momento de realizar la SD no se tenían monto suficiente para cubrir este compromiso.
Note on E125: Josue Andreé Ricart Vásquez: reprogramar 2020
Note on E126: Josue Andreé Ricart Vásquez: ES NECESARIO REBAJAR EL MONTO POR 75,000 DEBIDO A LA CAPACITACIÓN QUE TENDRAN CONGRESISTAS DE GUATEMALA EN EL REINO UNIDO, CASO CONTRARIO SE DESFINANCIA EL PROYECTO. ***De acuerdo a una nueva gestión se dividirá en dos fases Metro Riel. la primera se tiene un estimado de 900,000. y de la segunda desconozco el monto aun. según nueva información para el siguiente trimestre, estiman que el valor de la consultoría será de 1.3 millones (18 de febrero 2019)
Note on E135: Josue Andreé Ricart Vásquez: PARA LA ELABORACIÓN DEL Q13 CONSIGNAR VALOR PAGADO TOTAL DE 47118.49, PARA QUE AJUSTE CON MCDR DE ENERO
Note on E136: Josue Andreé Ricart Vásquez: original 45,000, se dejó de utilizar 6498.00 se reversó
Note on E220: Josue Ricart: Q16 increse 130,000.0
Note on E224: Josue Ricart: Increse 25,000
Note on BG195: Josue Andreé Ricart Vásquez: ojo se debe quitar un usd 1.00 solo ejecuto 24999

## Error checks (hidden)
Column Number
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | -1.8626e-09 | ok | 1.8626e-09 | -1221955.4078 | ok | ok | ok | ok
1.1.a Education Project Implementation Contract | ok | ok | ok | ok | ok | ok | ok | ok
1.1.b Grants to Universities for Teacher Training (Diplomados) | -9.3132e-10 | ok | ok | ok | ok | ok | ok | ok
1.1.c Other | ok | ok | ok | ok | ok | ok | ok | ok
1.2 Developing Technical and Vocational Education and Training (0400) | ok | ok | ok | 510340.59 | ok | ok | ok | ok
1.2.a TVET | ok | ok | ok | ok | ok | ok | ok | ok
1.3 Strengthening Institutional and Planning Capacity (0043) | -0.00625 | ok | 0.00625 | -99859.57 | ok | ok | ok | ok
1.3.a Education Project Implementation Contract | 4.6566e-10 | ok | ok | ok | ok | ok | ok | ok
1.3.b Education Project Coordination team* | -0.00625 | ok | ok | ok | ok | ok | ok | ok
1.3.c Other | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Education | -0.00625 | ok | 0.00625 | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok
2. Resource Mobilization Project (REV RFRM) | ok | ok | ok | ok | ok | ok | ok | ok
2.1 Improving Tax and Customs Administration (0443)** | 2.3283e-10 | ok | -2.3283e-10 | -197145.29 | ok | ok | ok | ok
2.1.a Tax and Customs | 2.3283e-10 | ok | ok | ok | ok | ok | ok | ok
2.2 Strengthening Public-Private Partnership Capacity (0414) | ok | ok | ok | 429224.73 | ok | ok | ok | ok
2.2.a Advisors | ok | ok | ok | ok | ok | ok | ok | ok
2.2.b Feasiblity Studies/ Transaction Advisory Services | ok | ok | ok | ok | ok | ok | ok | ok
2.2.c Other | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Resource Mobilization | 4.6566e-10 | ok | -2.3283e-10 | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok
3. M&E (MON & Eval) | ok | ok | ok | ok | ok | ok | ok | ok
Monitoring and Evaluation (0016) | -2.3283e-10 | ok | 2.3283e-10 | 827481.2103 | ok | ok | ok | ok
3.1.a Student Assessment | -1.1642e-10 | ok | ok | ok | ok | ok | ok | ok
3.1.b Teacher Evaluations | ok | ok | ok | 223962.4203 | ok | ok | ok | ok
3.1.c Voc Ed Tracer Studies | ok | ok | ok | ok | ok | ok | ok | ok
3.1 d Other | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - M&E | -2.3283e-10 | ok | 2.3283e-10 | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok
4. Program Admin (PGM ADMIN) | ok | ok | ok | ok | ok | ok | ok | ok
Program Administration (0017) | -0.02 | ok | 0.02 | -233086.2625 | ok | ok | ok | ok
4.1.a Staff Compensation* | 2.3283e-10 | ok | ok | ok | ok | ok | ok | ok
4.1.b Travel* | -7.276e-12 | ok | ok | ok | ok | ok | ok | ok
4.1.c Audit | ok | ok | ok | ok | ok | ok | ok | ok
4.1.d Other | -0.02 | ok | ok | ok | ok | ok | ok | ok
TOTAL - Program Admin | -0.02 | ok | 0.02 | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok
TOTAL MCA-Managed Threshold Funds

## Historico (hidden)
|  |  | 23584570 |  | Percent of disbursements by quarter | [14 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# |  | Contract name | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  | Contract name |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 1.1.a Education Project Implementation Contract | Exito Escolar 1.1 | 8500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 255000 | 425000 | 425000 | 425000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 0 | 0 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 1.1.a Education Project Implementation Contract | Pedagogical Resource centers | 200000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) | Diplomado Training | 3000000 | q6 | 2018-01-01: 12.5%; 2018-04-01: 12.5%; 2018-07-01: 12.5%; 2018-10-01: 12.5%; 2019-01-01: 12.5%; 2019-04-01: 12.5%; 2019-07-01: 12.5%; 2019-10-01: 12.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 1.2.a TVET | TVET place holder | 4000000 | q5 |  |  |  |  | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 100% | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 200000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 1.3.a Education Project Implementation Contract | Exito Escolar 1.3 | 2500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit | 140000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | Managaement coach for customs and audit (option 1) | 140000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | data subscriptions | 4000 | q3 | 2017-01-01: 100% | 100% | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | IT consultants | 100000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 2.1.a Tax and Customs | [18 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training | 150000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | Training option | 150000 | q6 | 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach | 73500 | q3 | 2017-01-01: 16.67%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 8.333% | 100% | 0 | 0 | 12250 | 18375 | 18375 | 18375 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 1 | 147000 | q6 | 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PPP coach option 2 | 147000 | q8 | 2018-10-01: 16.67%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 2.2.a Advisors | PP Financial Adivisor (for MINFIN and ANADIE) | 61250 | q2 | 2016-10-01: 20%; 2017-01-01: 60%; 2017-04-01: 20% | 100% | 0 | 12250 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Feasiblity Study | 500000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Airport Transaction Advisor | 200000 | q3 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Feasiblity Study | 350000 | [16 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Road Transaction Advisor | 200000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Feasiblity Study | 350000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 87500 | 87500 | 87500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services | Antigua Transaction Advisor | 50000 | q5 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | place holder | 500000 | q12 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 3 validadores para Pruebas de Educación de Nivel Medio | 7200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 2160 | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 6 redactores para Pruebas de Educación de Nivel Medio. | 19200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 5760 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | 1 curriculista para Pruebas de Educación de Nivel Medio. | 8000 | q3 | 2017-01-01: 50%; 2017-04-01: 50% | 100% | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 3.1.a Student Assessment | Un coordinador para Pruebas de Educación de Nivel Medio. | 72000 | q3 |  |  | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% |  | 100% | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 3.1.b Teacher Evaluations | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 100000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 3.1.c Voc Ed Tracer Studies | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.d | 3.1 d Other | place holder | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
4.1.c | 4.1.c Audit | Audit | 90000 | q5 | 2018-01-01: 16.67%; 2018-04-01: 16.67%; 2019-01-01: 16.67%; 2019-04-01: 16.67%; 2020-01-01: 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 4.1.d Other | IT Equipment | 11500 | q2 | 2016-10-01: 67%; 2017-01-01: 33% | 100% | 0 | 7705 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #N/A | tbd | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [35 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 1.3.b Education Project Coordination team* | Director de Proyecto de Educación | 121400 | q2 |  | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 121400 | 0 | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 31400 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 18000 | 0 | 0
1.3.b | 1.3.b Education Project Coordination team* | Asistente de Proyecto de Educación | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador MCC-THP | 181000 | q1 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 181000 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 49000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Asistente Administrativo Bilingüe | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista de Monitoreo y Evaluación | 147000 | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147000 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 21000 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Coordinador Administrativo Financiero (Especialista financiero) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista en Adquisiciones MCC (Especialista en adquisiciones) | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 4.1.a Staff Compensation* | Especialista Economista | 72000 | q4 |  |  |  | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 |  |  |  |  | 72000
1.2.a | 1.2.a TVET | FxT Coordinator | 144000 | q4 |  |  | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [50 empty] | 0
4.1.d | 4.1.d Other | Communications and Workshops | 20000 |  |  | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 19999.82 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 4.1.b Travel* | Travel | 35000 |  |  | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
| Total Comprometido a la fecha |  | 23584570
1.1.a | 1.1.a Education Project Implementation Contract |  | 8700000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 3000000
1.2.a | 1.2.a TVET |  | 4144000
1.3.a | 1.3.a Education Project Implementation Contract |  | 2500000
1.3.b | 1.3.b Education Project Coordination team* |  | 178400
| Education Project Total |  | 18522400 | 20889574.39 | 2367174.39
2.1.a | 2.1.a Tax and Customs |  | 384000
| Tax and Customs |  | 384000 | 1412145.29 | 1028145.29
2.2.a | 2.2.a Advisors |  | 728750
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 1650000
| PPPs |  | 2378750 | 1548175.27 | -830574.73
3.1.a | 3.1.a Student Assessment |  | 706400
3.1.b | 3.1.b Teacher Evaluations |  | 300000
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 300000
3.1.d | 3.1 d Other |  | 200000
| M&E |  | 1506400 | 603518.79 | -902881.21
4.1.a | 4.1.a Staff Compensation* |  | 636520
4.1.b | 4.1.b Travel* |  | 35000
4.1.c | 4.1.c Audit |  | 90000
4.1.d | 4.1.d Other |  | 31500
| Program Admin |  | 793020 | 1744086.26 | 951066.26