## DFP-Com
Detailed Financial Plan - Commitments
| Country: |  | Guatemala
| Accountable Entity: |  | PRONACOM
| Grant Number: |  | TR14GTM15001
| Date Submitted: |  | 2016-12-10
| Quarter # |  | 3
| Forecasted Commitments for -> | Cumulative | Current Period | Next Period | [15 empty] | TOTAL | TOTAL | Variance
|  | Actual Cumulative Commitments at Beginning of Current Period | Projected Commitments during Current Period | Grant Quarter #3 |  |  | Grant Quarter #3 | Grant Quarter #4 | Grant Quarter #5 | Grant Quarter #6 | Grant Quarter #7 | Grant Quarter #8 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Commitments As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)* | Projections vs. Approved Plan Under / (Over) Budget Difference
| Date/Month/Quarter -> | Sept´ 2016 | Oct '16 Dic '16 | Ene´17 | Feb`17 | Mar´17 | Jan '17 Mar '17 | Apr '17 Jun '17 | Jul '17 Aug '17 | Oct '17 Dec '17 | Jan '18 Mar '18 | Apr '18 Jun '18 | Jul '18 Aug '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Aug '19 | Oct '19 Dec '19 | Jan '20 Mar '20
| Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 | 1.1 Improving the Quality of Education (0277) | 0 | 0 | 0 | 8500000 | 0 | 8500000 | 0 | 0 | 3000000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11700000 | 12000000 | 300000
1.1.a | 1.1.a Education Project Implementation Contract |  | 0 |  | 8500000 |  | 8500000 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8700000
1.1.b | 1.1.b Grants to Universities for Teacher Training (Diplomados) |  | 0 |  |  |  | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000
1.1.c | 1.1.c Other |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 1.2 Developing Technical and Vocational Education and Training (0400) | 0 | 0 | 0 | 0 | 0 | 0 | 48000 | 4000000 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 4144000 | 4300000 | 156000
1.2.a | 1.2.a TVET |  | 0 |  |  | 0 | 0 | 48000 | 4000000 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 4144000
1.3 | 1.3 Strengthening Institutional and Planning Capacity (0043) | 0 | 40400 | 16500 | 2500000 | 0 | 2516500 | 0 | 0 | 36000 | 18000 | 0 | 0 | 36000 | 18000 | 0 | 0 | 18000 | 4500 | 2687400 | 3000000 | 312600
1.3.a | 1.3.a Education Project Implementation Contract |  | 0 |  | 2500000 |  | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000
1.3.b | 1.3.b Education Project Coordination team* |  | 40400 | 16500 | 0 |  | 16500 | 0 | 0 | 36000 | 18000 | 0 | 0 | 36000 | 18000 | 0 | 0 | 18000 | 4500 | 187400
1.3.c | 1.3.c Other |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTA | TOTAL - Education | 0 | 40400 | 16500 | 11000000 | 0 | 11016500 | 48000 | 4000000 | 3036000 | 218000 | 48000 | 0 | 36000 | 18000 | 48000 | 0 | 18000 | 4500 | 18531400 | 19300000 | 768600
2. R | 2. Resource Mobilization Project (REV RFRM)
2.1 | 2.1 Improving Tax and Customs Administration (0443)** | 0 | 0 | 100000 | 4000 | 0 | 104000 | 140000 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000 | 800000 | 416000
2.1.a | 2.1.a Tax and Customs |  | 0 | 100000 | 4000 | 0 | 104000 | 140000 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384000
2.2 | 2.2 Strengthening Public-Private Partnership Capacity (0414) | 0 | 61250 | 0 | 923500 | 0 | 923500 | 550000 | 50000 | 297000 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028750 | 3600000 | 1571250
2.2.a | 2.2.a Advisors |  | 61250 |  | 223500 | 0 | 223500 | 0 | 0 | 297000 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728750
2.2.b | 2.2.b Feasiblity Studies/ Transaction Advisory Services |  | 0 |  | 700000 | 0 | 700000 | 550000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
2.2.c | 2.2.c Other |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTA | TOTAL - Resource Mobilization | 0 | 61250 | 100000 | 927500 | 0 | 1027500 | 690000 | 50000 | 297000 | 140000 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2412750 | 4400000 | 1987250
3. M | 3. M&E (MON & Eval)
M | Monitoring and Evaluation (0016) | 0 | 0 | 80000 | 0 | 0 | 80000 | 226400 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 400000 | 1306400 | 1700000 | 393600
3.1.a | 3.1.a Student Assessment |  | 0 | 80000 |  | 0 | 80000 | 126400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 706400
3.1.b | 3.1.b Teacher Evaluations |  | 0 |  |  |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 300000
3.1.c | 3.1.c Voc Ed Tracer Studies |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 300000
3.1.d | 3.1 d Other |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
| TOTAL - M&E | 0 | 0 | 80000 | 0 | 0 | 80000 | 226400 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 400000 | 1306400 | 1700000 | 393600
4. Program Admin (PGM ADMIN)
| Program Administration (0017) | 73000 | 112458.4 | 3795 | 20500 | 2000 | 26295 | 3900 | 141900 | 98700 | 22900 | 3900 | 51900 | 98700 | 21900 | 3900 | 39900 | 51300 | 8332 | 758985.4 | 800000 | 41014.6
4.1.a | 4.1.a Staff Compensation* | 73000 | 102720 |  | 16500 |  | 16500 | 0 | 48000 | 94800 | 18000 | 0 | 48000 | 94800 | 18000 | 0 | 36000 | 47400 | 4500 | 601720
4.1.b | 4.1.b Travel* |  | 0 |  | 4000 |  | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000
4.1.c | 4.1.c Audit |  | 0 |  |  |  | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000
4.1.d | 4.1.d Other |  | 9738.4 | 3795 |  | 2000 | 5795 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 32265.4
| TOTAL - Program Admin | 73000 | 112458.4 | 3795 | 20500 | 2000 | 26295 | 3900 | 141900 | 98700 | 22900 | 3900 | 51900 | 98700 | 21900 | 3900 | 39900 | 51300 | 8332 | 758985.4 | 800000 | 41014.6
| TOTAL MCA-Managed Threshold Funds | 73000 | 214108.4 | 200295 | 11948000 | 2000 | 12150295 | 968300 | 4191900 | 3431700 | 480900 | 198900 | 51900 | 134700 | 39900 | 551900 | 39900 | 69300 | 412832 | 23009535.4 | 26200000 | 3190464.6
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.
78000

## DFP-CASH
Detailed Financial Plan - Cash
Country: |  | Guatemala
Accountable Entity: |  | PRONACOM
Grant Number: |  | TR14GTM15001
Date Submitted: |  | 2016-12-10
Quarter # |  | 3
Forecasted Cash for -> | Cumulative | Current Period |  | Next Period | [15 empty] | TOTAL | TOTAL | Variance
| Actual Cumulative Disbursements at Beginning of Current Period | Projected Disbursements during Current Period |  | Grant Quarter #3 |  |  | Grant Quarter #3 | Grant Quarter #4 | Grant Quarter #5 | Grant Quarter #6 | Grant Quarter #7 | Grant Quarter #8 | Grant Quarter #10 | Grant Quarter #11 | Grant Quarter #12 | Grant Quarter #13 | Grant Quarter #14 | Grant Quarter #15 | Grant Quarter #16 | Cash Disbursements As Currently Forecasted | As Per Current Approved Multi-Year Financial Plan (Should match with Schedule B)** | Projections vs. Approved Plan Under / (Over) Budget Difference
Date/Month/Quarter -> | July 01, 2016 | Jul '16 Sep '16 | Oct '16 Dic '16 | Ene´17 | Feb`17 | Mar´17 | Jan '17 Mar '17 | Apr '17 Jun '17 | Jul '17 Aug '17 | Oct '17 Dec '17 | Jan '18 Mar '18 | Apr '18 Jun '18 | Jul '18 Aug '18 | Oct '18 Dec '18 | Jan '19 Mar '19 | Apr '19 Jun '19 | Jul '19 Aug '19 | Oct '19 Dec '19 | Jan '20 Mar '20
Column Number | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column 19 | Column X | Column Y | Column Z
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 425000 | 425000 | 850000 | 1275000 | 1275000 | 1275000 | 1225000 | 1225000 | 1225000 | 1225000 | 1020000 | 11700000 | 12000000 | 300000
1.1.a Education Project Implementation Contract | [6 empty] | 0 | 255000 | 425000 | 425000 | 475000 | 900000 | 900000 | 900000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 8700000
1.1.b Grants to Universities for Teacher Training (Diplomados) | [6 empty] | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 3000000
1.1.c Other | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Developing Technical and Vocational Education and Training (0400) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 212000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 212000 | 4144000 | 4300000 | 156000
1.2.a TVET | [6 empty] | 0 | 12000 | 212000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 412000 | 212000 | 4144000
1.3 Strengthening Institutional and Planning Capacity (0043) | 0 | 0 | 4400 | 3000 | 4500 | 4500 | 12000 | 88500 | 138500 | 138500 | 138500 | 263500 | 263500 | 263500 | 263500 | 263500 | 263500 | 263500 | 313500 | 2674000 | 3000000 | 326000
1.3.a Education Project Implementation Contract | [6 empty] | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 2500000
1.3.b Education Project Coordination team* |  |  | 4400 | 3000 | 4500 | 4500 | 12000 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 | 174000
1.3.c Other | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL - Education | 0 | 0 | 4400 | 3000 | 4500 | 4500 | 12000 | 355500 | 775500 | 975500 | 1400500 | 1950500 | 1950500 | 1950500 | 1900500 | 1900500 | 1900500 | 1900500 | 1545500 | 18518000 | 19300000 | 782000
2. Resource Mobilization Project (REV RFRM)
2.1 Improving Tax and Customs Administration (0443)** | 0 | 0 | 0 | 0 | 4000 | 25000 | 29000 | 60000 | 60000 | 60000 | 70000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 384000 | 800000 | 416000
2.1.a Tax and Customs |  |  |  |  | 4000 | 25000 | 29000 | 60000 | 60000 | 60000 | 70000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 384000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 0 | 0 | 0 | 12250 | 12250 | 187000 | 211500 | 330625 | 380875 | 442875 | 280375 | 136750 | 74250 | 36750 | 36750 | 36750 | 36750 | 12250 | 0 | 2016500 | 3600000 | 1583500
2.2.a Advisors |  |  |  | 12250 | 12250 | 62000 | 86500 | 68125 | 55875 | 117875 | 80375 | 74250 | 74250 | 36750 | 36750 | 36750 | 36750 | 12250 | 0 | 716500
2.2.b Feasiblity Studies/ Transaction Advisory Services | [5 empty] | 125000 | 125000 | 262500 | 325000 | 325000 | 200000 | 62500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300000
2.2.c Other | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL - Resource Mobilization | 0 | 0 | 0 | 12250 | 16250 | 212000 | 240500 | 390625 | 440875 | 502875 | 350375 | 171750 | 109250 | 71750 | 36750 | 36750 | 36750 | 12250 | 0 | 2400500 | 4400000 | 1999500
3. M&E (MON & Eval)
Monitoring and Evaluation (0016) | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 67920 | 74480 | 56000 | 81000 | 31000 | 31000 | 31000 | 6000 | 231000 | 231000 | 231000 | 225000 | 1306400 | 1700000 | 393600
3.1.a Student Assessment | [5 empty] | 10000 | 10000 | 42920 | 49480 | 31000 | 31000 | 6000 | 6000 | 6000 | 6000 | 131000 | 131000 | 131000 | 125000 | 706400
3.1.b Teacher Evaluations | [6 empty] | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 300000
3.1.c Voc Ed Tracer Studies | [6 empty] | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 50000 | 50000 | 50000 | 50000 | 300000
3.1 d Other | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 200000
TOTAL - M&E | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 67920 | 74480 | 56000 | 81000 | 31000 | 31000 | 31000 | 6000 | 231000 | 231000 | 231000 | 225000 | 1306400 | 1700000 | 393600
4. Program Admin (PGM ADMIN)
Program Administration (0017) | 0 | 10000 | 54604.79 | 11900 | 21195 | 15400 | 48495 | 44100 | 44100 | 44100 | 60100 | 59100 | 44100 | 44100 | 59100 | 59100 | 44100 | 44100 | 74032 | 678627 | 800000 | 121373
4.1.a Staff Compensation* |  | 10000 | 54604.79 | 11900 | 13400 | 13400 | 38700 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 40200 | 531100
4.1.b Travel* |  |  |  |  | 4000 |  | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000
4.1.c Audit | [6 empty] | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 90000
4.1.d Other |  |  |  |  | 3795 | 2000 | 5795 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 22527
TOTAL - Program Admin | 0 | 10000 | 54604.79 | 11900 | 21195 | 15400 | 48495 | 44100 | 44100 | 44100 | 60100 | 59100 | 44100 | 44100 | 59100 | 59100 | 44100 | 44100 | 74032 | 678627 | 800000 | 121373
TOTAL MCA-Managed Threshold Funds | 0 | 10000 | 59004.79 | 27150 | 41945 | 241900 | 310995 | 858145 | 1334955 | 1578475 | 1891975 | 2212350 | 2134850 | 2097350 | 2002350 | 2227350 | 2212350 | 2187850 | 1844532 | 22903527 | 26200000 | 3296473
* This activity is MCC Managed (commitments and disbursements are reported on the quarterly MCC-Managed Report)
** These sub-activities that have amounts listed in Column Y are not part of Schedule B, but are being listed to comply with the Fiscal Accountability Plan's requirements for tracking/approving salary and travel budget changes.

## QFR - A
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2016-12-10
Schedule A. Multi-Year Financial Plan Adjustment Request Form
Disbursement Period:01-ene-17 to 31-mar-17
Amounts Expressed In US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Current Approved Multi-Year Financial Plan | Proposed Adjustments (Display all #'s as positive) |  | Proposed Adjusted Multi-Year Financial Plan
Project (code) |  | (from Schedule B, Final Column) | Increase (+) | Decrease (-) | (2+3-4)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | 19300000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 12000000 |  |  | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | 4300000 |  |  | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 3000000 |  |  | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 4400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 |  |  | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | 3600000 |  |  | 3600000
3. M&E (MON & EVAL) | 1700000 | 1700000 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 1700000 |  |  | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 800000 | 0 | 0 | 800000
Program Administration (0017) | 800000 | 800000 |  |  | 800000
Grand Total | 26200000 | 26200000 | 0 | 0 | 26200000
* This activity is partially MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 1800000 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 | 1800000 |  |  | 1800000
Grand Total | 1800000 | 1800000 | 0 | 0 | 1800000

## QFR - B
MCC Grant Quarterly Financial Report
| Country: | Guatemala
| Accountable Entity: | PRONACOM
| Grant Number: | TR14GTM15001
| Date Submitted: | 2016-12-10
Schedule B. Summary of Multi-Year Financial Plan Adjustments to Date
Disbursement Period:01-ene-17 to 31-mar-17
Amounts Expressed in US Dollars
Out of Cycle Report: Yes [ ] ¦ No [ x ]
| Original Program Multi-Year Financial Plan in Grant Agreement | Adjustment Reported/ Approved (Q1 - 9/10/2016) | Adjustment Reported/ Approved (insert date) | Adjustment Reported/ Approved (insert date) | Current Approved Multi-Year Financial Plan (to Schedule A, Column 2)
Project (code)
Activity (code) | 1 | 2 | 3 | 4 | 5
1. Education Project (EDU) | 19700000 | -400000 | 0 | 0 | 19300000
1.1 Improving the Quality of Education (0277) | 12000000 | 0 | 0 | 0 | 12000000
1.2 Developing Technical and Vocational Education and Training (0400) | 4700000 | -400000 | 0 | 0 | 4300000
1.3 Strengthening Institutional and Planning Capacity (0043) | 3000000 | 0 | 0 | 0 | 3000000
2. Resource Mobilization Project (REV RFRM) | 4000000 | 400000 | 0 | 0 | 4400000
2.1 Improving Tax and Customs Administration (0443)* | 0 | 800000 | 0 | 0 | 800000
2.2 Strengthening Public-Private Partnership Capacity (0414) | 4000000 | -400000 | 0 | 0 | 3600000
3. M&E (MON & EVAL) | 1700000 | 0 | 0 | 0 | 1700000
Monitoring and Evaluation (0016) | 1700000 | 0 | 0 | 0 | 1700000
4. Program Admin (PGM ADMIN) | 800000 | 0 | 0 | 0 | 800000
Program Administration (0017) | 800000 | 0 | 0 | 0 | 800000
Grand Total | 26200000 | 0 | 0 | 0 | 26200000
* This activity is MCC-Managed
MCC Managed Fund
2. Resource Mobilization Project (REV RFRM) | 1800000 | 0 | 0 | 0 | 1800000
2.1 Improving Tax and Customs Administration | 1800000 |  |  |  | 1800000
Grand Total | 1800000 | 0 | 0 | 0 | 1800000

## THP DR
DISBURSEMENT REQUEST
THRESHOLD PROGRAM GRANT AGREEMENT
Country | Guatemala
Projects | Theshold Program / Program Administration and Monitoring and Evaluation
Threshold Program Grant Agreement Date/ Entry into Force Date | April 8, 2015/May 15, 2016
Threshold Program Number | TR14GTM15001
Accountable Entity | PRONACOM
Fiscal Agent | MCC (Acting Fiscal Agent)
Request Date | 2016-12-10
Disbursement Period Beginning Date | 2017-01-01
Disbursement Period Ending Date | 2017-03-31
Disbursement Number | 3
Currency (Expressed in USD) | US Dollars
Exchange Rate used to calculate U.S. Dollar equivalent of any local currency balance for purposes of this MCC Disbursement Request
A. Disbursement Request: The undersigned hereby requests the Millennium Challenge Corporation to disburse funds under the Threshold Grant Agreement, dated as of August 28,2013 as follows:
1. Forecasted Cash Disbursement Requirements (from DFP Cash Column) | 310995
2. Interest to be Returned to the USG for Next Period (Interest Sum, Line 7)
3. Working Capital (FOR MCC USE ONLY)
4. Cash Balance at the End of the Current Period (Cash Req, Line 7) | 0
5. Disbursement Request Amount (Lines 1+2-4) | 310995
6. Amount Requested in Words
C. Compliance: the undersigned confirms that the MCC Disbursement requested herby is in accordance with the terms and conditions set forth in the Threshold Program Agreement, including the limitations on the use or treatment of MCC Funding set out in Section 2.4.
D. Authorization: the undersigned acknowledges that funds disbursed in accordance with this request will be either made (i) directly to third-party vendors for goods, works and services received by the accountable entity upon presentation of valid invoices utilizing MCC's Common Payment System, (ii) to the Permitted Account, or (iii) to the Petty Cash Account.
E. Certificates: Attached hereto are the certificates required under Section 5.2 and 5.3 of the Threshold Program Agreement.
F. Definitions: Capitalized terms used herein shall have the meanings assigned to such terms in the Threshold Program Agreement by and between the Government of Guatemala and the United States, acting through the Millennium Challenge Corporation, dated April 8, 2015, and entered into force on May 15, 2016.
Signed by the Executive Director of PRONACOM
By: _______________________________________________________________
Name: Fernando Suriano
Date: 8 de diciembre, 2016
Certified by the Minister of Economy
By: _______________________________________________________________
Name: Rubén Morales Monroy
Date: _____________________________________________________________
By: _______________________________________________________________
Name:
Date:

## Contract level (hidden)
| 23584570 |  | Percent of disbursements by quarter | [14 empty] | Total | Cash by quarter | [14 empty] | Committments by quarter
Act# | Value |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 |  | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | 2016-07-01 | 2016-10-01 | 2017-01-01 | 2017-04-01 | 2017-07-01 | 2017-10-01 | 2018-01-01 | 2018-04-01 | 2018-07-01 | 2018-10-01 | 2019-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01 | 2020-01-01 | check Cash=comm
Act# |  | Sign quarter | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15
1.1.a | 8500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 255000 | 425000 | 425000 | 425000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 1020000 | 0 | 0 | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.a | 200000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.b | 3000000 | q6 | 2018-01-01: 12.5%; 2018-04-01: 12.5%; 2018-07-01: 12.5%; 2018-10-01: 12.5%; 2019-01-01: 12.5%; 2019-04-01: 12.5%; 2019-07-01: 12.5%; 2019-10-01: 12.5% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.a | 4000000 | q5 |  |  |  |  | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 100% | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 200000 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.a | 2500000 | q3 |  |  |  | 3% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 12% | 100% | 0 | 0 | 0 | 75000 | 125000 | 125000 | 125000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 300000 | 0 | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 140000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 140000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 4000 | q3 | 2017-01-01: 100% | 100% | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | 100000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.a | [17 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 150000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 150000 | q6 | 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 37500 | 37500 | 37500 | 37500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 73500 | q3 | 2017-01-01: 16.67%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 8.333% | 100% | 0 | 0 | 12250 | 18375 | 18375 | 18375 | 6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 147000 | q6 | 2017-10-01: 16.67%; 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 147000 | q8 | 2018-10-01: 16.67%; 2019-01-01: 25%; 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 8.333% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24500 | 36750 | 36750 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.a | 61250 | q2 | 2016-10-01: 20%; 2017-01-01: 60%; 2017-04-01: 20% | 100% | 0 | 12250 | 36750 | 12250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 500000 | q3 | 2017-01-01: 25%; 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25% | 100% | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 200000 | q3 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 350000 | [16 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 200000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 350000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 87500 | 87500 | 87500 | 87500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.b | 50000 | q5 | 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25%; 2018-04-01: 25% | 100% | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 500000 | q12 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0
3.1.a | 7200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 2160 | 5040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 19200 | q4 | 2017-04-01: 30%; 2017-07-01: 70% | 100% | 0 | 0 | 0 | 5760 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 8000 | q3 | 2017-01-01: 50%; 2017-04-01: 50% | 100% | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.a | 72000 | q3 |  |  | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% |  | 100% | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 100000 | q4 | 2017-04-01: 25%; 2017-07-01: 25%; 2017-10-01: 25%; 2018-01-01: 25% | 100% | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.b | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.c | 100000 | q7 | 2018-01-01: 25%; 2018-04-01: 25%; 2018-07-01: 25%; 2018-10-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.c | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
3.1.d | 200000 | q15 | 2019-04-01: 25%; 2019-07-01: 25%; 2019-10-01: 25%; 2020-01-01: 25% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0
4.1.c | 90000 | q5 | 2018-01-01: 16.67%; 2018-04-01: 16.67%; 2019-01-01: 16.67%; 2019-04-01: 16.67%; 2020-01-01: 33.33% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.d | 11500 | q2 | 2016-10-01: 67%; 2017-01-01: 33% | 100% | 0 | 7705 | 3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Total | [30 empty] | 0
Salary Type Expenses | [33 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | 0
1.3.b | 121400 | q2 |  | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 121400 | 0 | 4400 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | 31400 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 18000 | 0 | 0
1.3.b | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 181000 | q1 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 181000 | 10000 | 15000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 49000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 36000 | 0 | 0 | 0
4.1.a | 57000 | q3 |  | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 57000 | 0 | 0 | 3000 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 16500 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 4500 | 0
4.1.a | 147000 | q2 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 147000 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 42000 | 0 | 0 | 0 | 21000 | 0 | 0
4.1.a | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 89760 | q2 |  | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 89760 | 0 | 3960 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 0 | 23760 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 26400 | 0 | 0 | 0 | 13200 | 0 | 0
4.1.a | 72000 | q4 |  |  |  | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 | 9000 |  |  |  |  | 72000
1.2.a | 144000 | q4 |  |  | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 48000 | 0 | 0 | 0 | 0
0
Recurring Expenses for which commitments will be made in same quarter as expense. | [48 empty] | 0
4.1.d | 20000 |  |  | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 19999.82 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0 | 1267.82 | 2000 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1332 | 0
4.1.b | 35000 |  |  | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 35000 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 4000 | 2500 | 2500 | 2500 | 3500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0
23584570
1.1.a | 8700000
1.1.b | 3000000
1.2.a | 4144000
1.3.a | 2500000
1.3.b | 178400
| 18522400 | 19300000 | 777600
2.1.a | 384000
| 384000 | 800000 | 416000
2.2.a | 728750
2.2.b | 1650000
| 2378750 | 3600000 | 1221250
3.1.a | 706400
3.1.b | 300000
3.1.c | 300000
3.1.d | 200000
| 1506400 | 1700000 | 193600
4.1.a | 636520
4.1.b | 35000
4.1.c | 90000
4.1.d | 31500
| 793020 | 800000 | 6980

## Error checks (hidden)
Column Number | total
| com-cash |  | cash before Com | [7 empty] | cash before Com
1. Education Project (EDU)
1.1 Improving the Quality of Education (0277) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.a Education Project Implementation Contract | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.b Grants to Universities for Teacher Training (Diplomados) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.1.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2 Developing Technical and Vocational Education and Training (0400) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.2.a TVET | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3 Strengthening Institutional and Planning Capacity (0043) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.a Education Project Implementation Contract | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.b Education Project Coordination team* | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
1.3.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Education | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2. Resource Mobilization Project (REV RFRM) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1 Improving Tax and Customs Administration (0443)** | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.1.a Tax and Customs | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2 Strengthening Public-Private Partnership Capacity (0414) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.a Advisors | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.b Feasiblity Studies/ Transaction Advisory Services | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
2.2.c Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Resource Mobilization | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3. M&E (MON & Eval) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Monitoring and Evaluation (0016) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error
3.1.a Student Assessment | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
3.1.b Teacher Evaluations | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error
3.1.c Voc Ed Tracer Studies | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error
3.1 d Other | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error | error | error
TOTAL - M&E | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | error
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4. Program Admin (PGM ADMIN) | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
Program Administration (0017) | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.a Staff Compensation* | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.b Travel* | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.c Audit | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
4.1.d Other | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL - Program Admin | error | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
| ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok | ok
TOTAL MCA-Managed Threshold Funds